## Inputs
Barnes & Noble - Colorado Springs, CO (3173 Cinema Point) ¦ METAL FRAMING & DRYWALL TAKEOFF
Bid set: Barnes _ Noble - Colorado Springs, CO - COMBINED BID SET - 250918.pdf · 2026-10-24 · Edit ONLY the yellow cells.
PARAMETER | VALUE | NOTE / SOURCE
Waste - ALL METAL, any type | 0.15 | Estimator standing rule: 15% on everything that is metal.
Waste - EVERYTHING THAT IS NOT METAL | 0.06 | Estimator standing rule: same figure as board.
Board sheet width (ft) | 4 | Sheet size is a parameter; buy the size that wastes least.
Board sheet length (ft) | 12 | Change it and every sheet count re-rounds.
SF per board sheet | 48 | Width x length.
Stud stock length (ft) | 20 | Stud, header, framed opening and stud blocking: sticks.
Track stock length (ft) | 10 | Track, sill track and purlin: runs.
Floor plan scale (pt/ft) | n/a | Project value (not used in this take-off: heights are per wall in the Partition Takeoff).
B.O. Deck (ft) | n/a | Project value (not used in this take-off: heights are per wall in the Partition Takeoff).
T.O. Parapet (ft) | n/a | Project value (not used in this take-off: heights are per wall in the Partition Takeoff).
Sealant coverage (LF per tube) | 25 | Sealant yield per tube - set your supplier's figure.
C.R. channel stock length (ft) | 16 | 1-1/2" cold-rolled channel (bracing, carrying channel).
Hat / furring channel stock (ft) | 12 | 7/8" hat furring channel.
Trim stick length (ft) | 10 | Corner bead, casing bead, shadow molding, PVC trim.
Hanger wire purchase | continuous coil (LF) | Bought by LF from a continuous coil; the hanger count goes on its own PCS row.
Drywall screws per SF of board | 1.2 | YIELD: estimator 1.2 / SF; products per A-410 note 8.E (Type S 25/20 ga, Type S-12 18/16/14 ga) and A-001A Div 09 A.5.
Framing screws per stud piece | 4 | YIELD: 2 per stud-to-track connection, each end.
Power-driven pin spacing (ft) | 1.3333 | YIELD: A-410 note 8.F spacing, one row @ 16" O.C. = 1.333 ft per pin (estimator decision 2026-10-27, RFI-ACC-slab-pins B).
Joint compound (lb per SF) | 0.072 | YIELD: 72 lb per 1,000 SF; Level 4 finish printed on A-001A Div 09 A.8 "PROVIDE AT A MINIMUM A LEVEL 4 FINISH".
Joint tape (LF per SF) | 0.37 | YIELD: 370 LF per 1,000 SF.
Expansion anchor spacing (ft) | 0.66667 | YIELD: exterior bottom track on slab.
2x lumber stock length (ft) | 16 | 2x wood / FRT blocking: 16 ft sticks (estimator decision 2026-10-27).
Drywall grid main tee length (ft) | 12 | USG DGLW26 main tee (manufacturer length).
Drywall grid cross tee length (ft) | 4 | USG DGLW424 cross tee (manufacturer length).
Grid channel / angle molding length (ft) | 12 | USG DGCM27 / DGWM24 molding (manufacturer length).
FRP panel (SF per panel) | 40 | FRP-1 panel 4'x10' (estimator to confirm the panel size).

## Partition Takeoff
ORGANIZED PARTITION TAKEOFF - Barnes & Noble - Colorado Springs, CO (3173 Cinema Point)
Grouped by partition type. Every row cites its DETAIL/SHEET and its status.
Partition / Scope | Wall # | Length (LF) | Height (FT) | Layers | Stud Size | Stud O.C. (in) | Board (SF) | Location | Source (DETAIL/SHEET) | Status
TYPE 2
2 #2-03+W2-06.5 - Men's Restroom 108 / Sales floor / hall + Corridor 110 / Men's Restroom 108 / Janitor Closet 107 | 2-03+W2-06.5 | 13.03 | 20 | 2 | 3-5/8" 20 | 16 | 360.86 | Men's Restroom 108 / Sales floor / hall + Corridor 110 / Men's Restroom 108 / Janitor Closet 107 ¦ Board by face: 2-03 A Men's Restroom 108 9.03 x 9 ft (5/8 regular); 2-03 B Sales floor / hall 9.03 x 20 ft (5/8 regular); W2-06.5 A Corridor 110 4 x 9.5 ft (5/8 type X); W2-06.5 B Men's Restroom 108 2.44 x 9 ft (5/8 type X WR); W2-06.5 B Janitor Closet 107 1.56 x 25 ft (5/8 type X WR) | 2/A-410 | [DERIVED]
2 #2-13 - West / exterior side (trash, loading) / Sales floor | 2-13 | 71.33 | 20 | 2 | 3-5/8" 20 | 16 | 2853.2 | West / exterior side (trash, loading) / Sales floor | 2/A-410 | [DERIVED]
2 #W2-01+2-11+2-12 - Furred cavity at north exterior wall / Sales floor + Furred cavity / Sales floor | W2-01+2-11+2-12 | 58.39 | 20 | 2 | 3-5/8" 20 | 16 | 2335.6 | Furred cavity at north exterior wall / Sales floor + Furred cavity / Sales floor | 2/A-410 | [DERIVED]
2 #W2-04+W2-03 - Sales Area 101 / Corridor 110 / Break Room 106 / Manager's Office 105 + Stock Room 111 / Sales Area 101 / Corridor 110 | W2-04+W2-03 | 70.14 | 20 | 2 | 3-5/8" 20 | 16 | 2592.48 | Sales Area 101 / Corridor 110 / Break Room 106 / Manager's Office 105 + Stock Room 111 / Sales Area 101 / Corridor 110 ¦ Board by face: W2-04 A Sales Area 101 57.2 x 25 ft (5/8 type X); W2-04 B Corridor 110 29.27 x 9.5 ft (5/8 type X); W2-04 B Break Room 106 19.18 x 9.5 ft (5/8 type X); W2-04 B Manager's Office 105 8.76 x 9.5 ft (5/8 type X); W2-03 A Stock Room 111 12.94 x 25 ft (5/8 type X); W2-03 B Sales Area 101 11.14 x 25 ft (5/8 type X); W2-03 B Corridor 110 1.8 x 9.5 ft (5/8 type X) | 2/A-410 | [DERIVED]
2 #W2-05 - Corridor 110 / Women's Restroom 109 | W2-05 | 12.92 | 20 | 2 | 3-5/8" 20 | 16 | 241.73 | Corridor 110 / Women's Restroom 109 ¦ Board by face: A Corridor 110 12.92 x 9.5 ft (5/8 type X); B Corridor 110 5.41 x 9.5 ft (5/8 type X); B Women's Restroom 109 7.51 x 9 ft (5/8 type X WR) | 2/A-410 | [DERIVED]
2 #W2-06.1 - Women's Restroom 109 / Sales floor / hall | W2-06.1 | 9.06 | 20 | 2 | 3-5/8" 20 | 16 | 262.74 | Women's Restroom 109 / Sales floor / hall ¦ Board by face: A Women's Restroom 109 9.06 x 9 ft (5/8 type X); B Sales floor / hall 9.06 x 20 ft (5/8 type X WR) | 2/A-410 | [DERIVED]
2 #W2-07 - Men's Restroom 108 / Janitor Closet 107 | W2-07 | 7.52 | 20 | 2 | 3-5/8" 20 | 16 | 218.08 | Men's Restroom 108 / Janitor Closet 107 ¦ Board by face: A Men's Restroom 108 7.52 x 9 ft (5/8 type X WR); B Janitor Closet 107 7.52 x 20 ft (5/8 type X WR) | 2/A-410 | [DERIVED]
2 #W2-08 - Corridor 110 / Janitor Closet 107 / Break Room 106 | W2-08 | 12.94 | 20 | 2 | 3-5/8" 20 | 16 | 362.08 | Corridor 110 / Janitor Closet 107 / Break Room 106 ¦ Board by face: A Corridor 110 5.41 x 9.5 ft (5/8 type X); A Janitor Closet 107 7.51 x 25 ft (5/8 type X WR); B Break Room 106 12.94 x 9.5 ft (5/8 type X) | 2/A-410 | [DERIVED]
2 #W2-09 - Break Room 106 / Manager's Office 105 | W2-09 | 12.94 | 20 | 2 | 3-5/8" 20 | 16 | 232.92 | Break Room 106 / Manager's Office 105 ¦ Board by face: A Break Room 106 12.94 x 9 ft (5/8 type X); B Manager's Office 105 12.94 x 9 ft (5/8 type X) | 2/A-410 | [DERIVED]
| SUBTOTAL TYPE 2 | 268.27 |  |  |  |  | 9459.69
TYPE 5
5 #5-01b - Women's Restroom 109 / Men's Restroom 108 | 5-01b | 4.22 | 20 | 2 | 6" 20 | 16 | 75.96 | Women's Restroom 109 / Men's Restroom 108 ¦ Board by face: A Women's Restroom 109 4.22 x 9 ft (5/8 MR); B Men's Restroom 108 4.22 x 9 ft (5/8 MR) | 5/A-410 | [DERIVED]
5 #W5-01 - Women's Restroom 109 / Men's Restroom 108 | W5-01 | 5.72 | 20 | 2 | 6" 20 | 16 | 102.96 | Women's Restroom 109 / Men's Restroom 108 ¦ Board by face: A Women's Restroom 109 5.72 x 9 ft (5/8 type X WR); B Men's Restroom 108 5.72 x 9 ft (5/8 type X WR) | 5/A-410 | [DERIVED]
| SUBTOTAL TYPE 5 | 9.94 |  |  |  |  | 178.92
TYPE 3
3 #W3-01 - Sales floor (display fixtures) | W3-01 | 3.67 | 8 | 1 | 3-5/8" 20 | 16 | 29.36 | Sales floor (display fixtures) | 3/A-410 | [DERIVED]
3 #W3-02 - Sales floor (display fixtures) | W3-02 | 12 | 8 | 1 | 3-5/8" 20 | 16 | 96 | Sales floor (display fixtures) | 3/A-410 | [DERIVED]
3 #W3-03 - Sales floor (display fixtures) | W3-03 | 12 | 8 | 1 | 3-5/8" 20 | 16 | 96 | Sales floor (display fixtures) | 3/A-410 | [DERIVED]
3 #W3-04 - Sales floor (display fixtures) | W3-04 | 3.67 | 8 | 1 | 3-5/8" 20 | 16 | 29.36 | Sales floor (display fixtures) | 3/A-410 | [DERIVED]
3 #W3-05 - Sales floor (display fixtures) | W3-05 | 3.67 | 8 | 1 | 3-5/8" 20 | 16 | 29.36 | Sales floor (display fixtures) | 3/A-410 | [DERIVED]
3 #W3-06 - Sales floor (display fixtures) | W3-06 | 3.67 | 8 | 1 | 3-5/8" 20 | 16 | 29.36 | Sales floor (display fixtures) | 3/A-410 | [DERIVED]
| SUBTOTAL TYPE 3 | 38.68 |  |  |  |  | 309.44
TYPE 4
4 #4-02 - Sales floor (feature wall) | 4-02 | 24.21 | 7.5 | 2 | 3-5/8" 20 | 16 | 363.16 | Sales floor (feature wall) | 4/A-410 | [DERIVED]
4 #4-03 - Sales floor (feature wall) | 4-03 | 24.21 | 7.5 | 2 | 3-5/8" 20 | 16 | 363.16 | Sales floor (feature wall) | 4/A-410 | [DERIVED]
4 #W4-28a - Sales floor (feature wall) | W4-28a | 9 | 7.5 | 1 | 3-5/8" 20 | 16 | 67.5 | Sales floor (feature wall) | 4/A-410 | [DERIVED]
4 #W4-31a - Sales floor (feature wall) | W4-31a | 9 | 7.5 | 1 | 3-5/8" 20 | 16 | 67.5 | Sales floor (feature wall) | 4/A-410 | [DERIVED]
| SUBTOTAL TYPE 4 | 66.42 |  |  |  |  | 861.32
TYPE H1
H1 #C-H1-N - Sales Area 101 / Grab & Go | C-H1-N | 25.3 | 20 | 1 | 6" 20 | 16 | 572.53 | Sales Area 101 / Grab & Go ¦ Board by face: A Sales Area 101 21.86 x 25 ft (5/8 type X); A Grab & Go 3.44 x 7.58 ft (5/8 type X) | G/A-221 | [DERIVED]
H1 #C-H1-W - Cafe Workroom 104 | C-H1-W | 13.22 | 20 | 1 | 6" 20 | 16 | 264.4 | Cafe Workroom 104 | G/A-221 | [DERIVED]
| SUBTOTAL TYPE H1 | 38.52 |  |  |  |  | 836.93
TYPE H2A
H2A #C-H2a - Cafe Sales | C-H2a | 4.49 | 20 | 1 | 3-5/8" 20 | 16 | 89.8 | Cafe Sales | G/A-221 | [DERIVED]
| SUBTOTAL TYPE H2A | 4.49 |  |  |  |  | 89.8
TYPE H2B
H2B #C-H2b - C-H2b | C-H2b | 2 | 20 | 0 | 3-5/8" 20 | 16 | 0 | C-H2b | G/A-221 | [DERIVED]
| SUBTOTAL TYPE H2B | 2 |  |  |  |  | 0
TYPE H3A
H3A #C-H3a - Grab & Go / Sales Area 101 | C-H3a | 3.99 | 20 | 2 | 6" 20 | 16 | 119.7 | Grab & Go / Sales Area 101 ¦ Board by face: B Grab & Go 3.99 x 20 ft (5/8 type X); A Sales Area 101 3.99 x 10 ft (5/8 type X) | H/A-221 | [DERIVED]
| SUBTOTAL TYPE H3A | 3.99 |  |  |  |  | 119.7
TYPE H3B
H3B #C-H3b - Cafe Workroom 104 | C-H3b | 6.76 | 20 | 1 | 6" 20 | 16 | 135.2 | Cafe Workroom 104 | H/A-221 | [DERIVED]
| SUBTOTAL TYPE H3B | 6.76 |  |  |  |  | 135.2
TYPE E2
E2 #C-E2 - Cafe Workroom 104 | C-E2 | 28.49 | 20 | 1 | 6" 20 | 16 | 569.8 | Cafe Workroom 104 | E/A-221 | [DERIVED]
| SUBTOTAL TYPE E2 | 28.49 |  |  |  |  | 569.8
TYPE E1
E1 #C-E1-S+C-E1-P.2 - Cafe 103 / concealed: behind the Workroom door pier and inside the SE box (no cement board) + Cafe Workroom 104 | C-E1-S+C-E1-P.2 | 23.6 | 20 | 0.84 | 6" 20 | 16 | 237.73 | Cafe 103 / concealed: behind the Workroom door pier and inside the SE box (no cement board) + Cafe Workroom 104 ¦ Board by face: C-E1-S A Cafe 103 16.14 x 12 ft (1/2 cement board); C-E1-S A concealed: behind the Workroom door pier and inside the SE box (no cement board) 3.79 x 0 ft (1/2 cement board); C-E1-P.2 A Cafe Workroom 104 3.67 x 12 ft (1/2 cement board) | E/A-221 | [DERIVED]
| SUBTOTAL TYPE E1 | 23.6 |  |  |  |  | 237.73
TYPE F
F #F-01 - F-01 | F-01 | 9.75 | 20 | 0 | 3-5/8" 20 | 16 | 0 | F-01 | F/A-221 | [PENDING]
| SUBTOTAL TYPE F | 9.75 |  |  |  |  | 0
TYPE I
I #I-02 - Cafe Sales | I-02 | 3.46 | 20 | 1 | 6" 20 | 16 | 69.2 | Cafe Sales | I/A-221 | [DERIVED]
I #I-03 - Grab & Go (end face) | I-03 | 0.53 | 20 | 1 | 6" 20 | 16 | 10.6 | Grab & Go (end face) | I/A-221 | [DERIVED]
I #I-05 - Cafe Sales (east face of box F) | I-05 | 3.25 | 20 | 1 | 6" 20 | 16 | 65 | Cafe Sales (east face of box F) | I/A-221 | [DERIVED]
| SUBTOTAL TYPE I | 7.24 |  |  |  |  | 144.8
TYPE A
A #C-A-1 - Customer side (counter) / Cafe side (counter) | C-A-1 | 10.44 | 2.708 | 2 | 3-5/8" 20 | 16 | 56.54 | Customer side (counter) / Cafe side (counter) | A/A-221 | [DERIVED]
A #C-A-2 - Customer side (counter) / Cafe side (counter) | C-A-2 | 3.97 | 2.708 | 2 | 3-5/8" 20 | 16 | 21.5 | Customer side (counter) / Cafe side (counter) | A/A-221 | [DERIVED]
A #C-A-3 - Customer side (counter) / Cafe side (counter) | C-A-3 | 6.34 | 2.708 | 2 | 3-5/8" 20 | 16 | 34.34 | Customer side (counter) / Cafe side (counter) | A/A-221 | [DERIVED]
| SUBTOTAL TYPE A | 20.75 |  |  |  |  | 112.38
TYPE B
B #C-B - Customer side (counter) / Cafe side (counter) | C-B | 2.75 | 2.708 | 2 | 3-5/8" 20 | 16 | 14.9 | Customer side (counter) / Cafe side (counter) | B/A-221 | [DERIVED]
| SUBTOTAL TYPE B | 2.75 |  |  |  |  | 14.9
TYPE D
D #C-D - Customer side (counter) / Cafe side (counter) | C-D | 6.15 | 2.708 | 2 | 3-5/8" 20 | 16 | 33.3 | Customer side (counter) / Cafe side (counter) | D/A-221 | [DERIVED]
| SUBTOTAL TYPE D | 6.15 |  |  |  |  | 33.3
TYPE C
C #C-C - Customer side (counter) / Cafe side (counter) | C-C | 2.23 | 2.708 | 2 | 3-5/8" 20 | 16 | 12.08 | Customer side (counter) / Cafe side (counter) | C/A-221 | [DERIVED]
| SUBTOTAL TYPE C | 2.23 |  |  |  |  | 12.08
| TOTAL - PARTITIONS (GRAND TOTAL) | 540.03 |  |  |  |  | 13115.99
TYPE OTHER FRAMING (NOT A PARTITION)
column_wrap #CW-01 - Sales floor | CW-01 | 8 | 8 | 1 | 3-5/8" 20 | 16 | 64 | Sales floor | C25/A-101 | [DERIVED]
column_wrap #CW-02 - Sales floor | CW-02 | 8 | 8 | 1 | 3-5/8" 20 | 16 | 64 | Sales floor | C25/A-101 | [DERIVED]
column_wrap #CW-03 - Sales floor | CW-03 | 8 | 8 | 1 | 3-5/8" 20 | 16 | 64 | Sales floor | C25/A-101 | [DERIVED]
column_wrap #CW-04 - Sales floor | CW-04 | 8 | 8 | 1 | 3-5/8" 20 | 16 | 64 | Sales floor | C25/A-101 | [DERIVED]
column_wrap #CW-05 - Sales floor | CW-05 | 8 | 8 | 1 | 3-5/8" 20 | 16 | 64 | Sales floor | C25/A-101 | [DERIVED]
column_wrap #CW-06 - Sales floor | CW-06 | 8 | 8 | 1 | 3-5/8" 20 | 16 | 64 | Sales floor | C25/A-101 | [DERIVED]
column_wrap #CW-07 - Sales floor | CW-07 | 8 | 8 | 1 | 3-5/8" 20 | 16 | 64 | Sales floor | C25/A-101 | [DERIVED]
column_wrap #CW-08 - Sales floor | CW-08 | 8 | 8 | 1 | 3-5/8" 20 | 16 | 64 | Sales floor | C25/A-101 | [DERIVED]
column_wrap #CW-09 - Sales floor | CW-09 | 8 | 8 | 1 | 3-5/8" 20 | 16 | 64 | Sales floor | C25/A-101 | [DERIVED]
soffit_side #SS-N - Cafe Sales / Grab & Go | SS-N | 22.67 | 1.92 | 2 | 3-5/8" 20 | 16 | 270.23 | Cafe Sales / Grab & Go ¦ Board by face: A Cafe Sales 22.67 x 10 ft (5/8 type X); B Grab & Go 22.67 x 1.92 ft (5/8 regular) | 6/A-221 | [DERIVED]
soffit_side #SS-GG - Cafe Sales / Grab & Go | SS-GG | 6.21 | 1.92 | 2 | 3-5/8" 20 | 16 | 23.84 | Cafe Sales / Grab & Go | 6/A-221 | [DERIVED]
stub #I-04 - Cafe Sales (end face) | I-04 | 0.44 | 20 | 1 | 6" 20 | 16 | 8.8 | Cafe Sales (end face) | I/A-221 | [DERIVED]

## Material Summary
MATERIAL SUMMARY - NET / WASTE / PURCHASE
Waste lives HERE, in its own column, applied ONCE: Pieces = ROUNDUP(Net x (1 + waste) / stock). Every stock length, coverage and yield is an Inputs cell.
Material | Unit | Net | Waste % | Waste | Purchase | Selling unit | Pieces to buy | Where it comes from | Yield check (live formula)
Bottom track 3-5/8" | LF | 425.16 | 0.15 | 63.774 | 488.934 | run 10 ft | 49 | N/SHEET: 2/A-410, 3/A-410, 4/A-410, G/A-221, E/A-221, A/A-221, B/A-221, D/A-221, C/A-221, F/A-221 ¦ Breakdown [DERIVED]: W2-01 48.33 + W2-03 12.94 + W2-04 57.2 + W2-05 12.92 + W2-06.1 9.06 + W2-06.5 4 + W2-07 7.52 + W2-08 12.94 + W2-09 12.94 + W3-01 3.67 + W3-02 12 + W3-05 3.67 + W3-03 12 + W3-06 3.67 + W3-04 3.67 + W4-28a 9 + W4-31a 9 + C-H2a 4.49 + C-H2b 2 + C-E1-P.2 3.67 + C-A-1 10.44 + C-A-2 3.97 + C-A-3 6.34 + C-B 2.75 + C-D 6.15 + C-C 2.23 + 2-03 9.03 + F-01 9.75 + 2-11 5.03 + 2-12 5.03 + 2-13 71.33 + 4-02 24.21 + 4-03 24.21 = 425.16 LF (wall length x rows) ¦ Track gauge = stud gauge (A-410 schedule note 2): 20 425.16 LF
Bottom track 6" | LF | 111.09 | 0.15 | 16.6635 | 127.7535 | run 10 ft | 13 | N/SHEET: 5/A-410, G/A-221, H/A-221, E/A-221, I/A-221 ¦ Breakdown [DERIVED]: W5-01 5.72 + C-H1-N 25.3 + C-H1-W 13.22 + C-H3a 3.99 + C-H3b 6.76 + C-E2 28.49 + C-E1-S 19.93 + 5-01b 4.22 + I-02 3.46 = 111.09 LF (wall length x rows) ¦ Track gauge = stud gauge (A-410 schedule note 2): 20 111.09 LF
Bottom track - other framing (not a partition type, see source) | LF | 72 | 0.15 | 10.8 | 82.8 | run 10 ft | 9 | N/SHEET: C25/A-101 ¦ Breakdown [DERIVED]: CW-01 8 + CW-02 8 + CW-03 8 + CW-04 8 + CW-05 8 + CW-06 8 + CW-07 8 + CW-08 8 + CW-09 8 = 72 LF (wall length x rows) ¦ Track gauge = stud gauge (A-410 schedule note 2): 20 72 LF
Top / deflection track 3-5/8" | LF | 425.16 | 0.15 | 63.774 | 488.934 | run 10 ft | 49 | N/SHEET: 2/A-410, 3/A-410, 4/A-410, G/A-221, E/A-221, A/A-221, B/A-221, D/A-221, C/A-221, F/A-221 ¦ Breakdown [DERIVED]: W2-01 48.33 + W2-03 12.94 + W2-04 57.2 + W2-05 12.92 + W2-06.1 9.06 + W2-06.5 4 + W2-07 7.52 + W2-08 12.94 + W2-09 12.94 + W3-01 3.67 + W3-02 12 + W3-05 3.67 + W3-03 12 + W3-06 3.67 + W3-04 3.67 + W4-28a 9 + W4-31a 9 + C-H2a 4.49 + C-H2b 2 + C-E1-P.2 3.67 + C-A-1 10.44 + C-A-2 3.97 + C-A-3 6.34 + C-B 2.75 + C-D 6.15 + C-C 2.23 + 2-03 9.03 + F-01 9.75 + 2-11 5.03 + 2-12 5.03 + 2-13 71.33 + 4-02 24.21 + 4-03 24.21 = 425.16 LF (wall length x rows) ¦ Track gauge = stud gauge (A-410 schedule note 2): 20 425.16 LF
Top / deflection track 6" | LF | 111.09 | 0.15 | 16.6635 | 127.7535 | run 10 ft | 13 | N/SHEET: 5/A-410, G/A-221, H/A-221, E/A-221, I/A-221 ¦ Breakdown [DERIVED]: W5-01 5.72 + C-H1-N 25.3 + C-H1-W 13.22 + C-H3a 3.99 + C-H3b 6.76 + C-E2 28.49 + C-E1-S 19.93 + 5-01b 4.22 + I-02 3.46 = 111.09 LF (wall length x rows) ¦ Track gauge = stud gauge (A-410 schedule note 2): 20 111.09 LF
Top / deflection track - other framing (not a partition type, see source) | LF | 72 | 0.15 | 10.8 | 82.8 | run 10 ft | 9 | N/SHEET: C25/A-101 ¦ Breakdown [DERIVED]: CW-01 8 + CW-02 8 + CW-03 8 + CW-04 8 + CW-05 8 + CW-06 8 + CW-07 8 + CW-08 8 + CW-09 8 = 72 LF (wall length x rows) ¦ Track gauge = stud gauge (A-410 schedule note 2): 20 72 LF
8" stud (all gauges) | LF | 25.33 | 0.15 | 3.7995 | 29.1295 | stick 20 ft | 2 | N/SHEET: 8/A-210 ¦ Breakdown [DERIVED]: VEST-BOX-BEAM-STUD 25.33 = 25.33 LF (per wall: field + jambs + nodes + cripples x height; plus listed elements)
6" metal stud (LF of material) | LF | 1960 | 0.15 | 294 | 2254 | stick 20 ft | 113 | N/SHEET: 5/A-410, G/A-221, H/A-221, E/A-221, I/A-221 ¦ Breakdown [DERIVED]: W5-01 140 + C-H1-N 400 + C-H1-W 220 + C-H3a 100 + C-H3b 140 + C-E2 460 + C-E1-S 320 + 5-01b 100 + I-02 80 = 1,960 LF (per wall: field + jambs + nodes + cripples x height; plus listed elements) ¦ By gauge (A-410 Metal Stud Schedule): 20 1,960 LF; elements (gauge in their operation) 0 LF
3-5/8" metal stud (LF of material) | LF | 7811.19 | 0.15 | 1171.6785 | 8982.8685 | stick 20 ft | 450 | N/SHEET: 2/A-410, 3/A-410, 4/A-410, G/A-221, E/A-221, A/A-221, B/A-221, D/A-221, C/A-221, 6/A-221, C25/A-101, F/A-221, 7/A-210 ¦ Breakdown [DERIVED]: W2-01 800 + W2-03 240 + W2-04 946 + W2-05 220 + W2-06.1 246 + W2-06.5 146 + W2-07 140 + W2-08 306 + W2-09 306 + W3-01 32 + W3-02 96 + W3-05 32 + W3-03 96 + W3-06 32 + W3-04 32 + W4-28a 75 + W4-31a 75 + C-H2a 159 + C-H2b 60 + C-E1-P.2 80 + C-A-1 29.79 + C-A-2 13.54 + C-A-3 16.25 + C-B 10.83 + C-D 21.66 + C-C 8.12 + SS-N 36.48 + SS-GG 11.52 + 2-03 246 + 2-11 100 + 2-12 100 + 2-13 1,100 + 4-02 150 + 4-03 150 + CW-01 96 + CW-02 96 + CW-03 96 + CW-04 96 + CW-05 96 + CW-06 96 + CW-07 96 + CW-08 96 + CW-09 96 + F-01 240 + DIAG-BRACES-T2 468 + VEST-POSTS-STUD 126 = 7,811.19 LF (per wall: field + jambs + nodes + cripples x height; plus listed elements) ¦ By gauge (A-410 Metal Stud Schedule): 20 7,217.19 LF; elements (gauge in their operation) 594 LF
Ceiling perimeter track at GWB ceilings (size not printed, RFI) | LF | 281.75 | 0.15 | 42.2625 | 324.0125 | run 10 ft | 33 | N/SHEET: 6/A-221, 1/A-121, 5/A-121 ¦ Breakdown [DERIVED]: SS-N 45.34 + SS-GG 12.42 + Women's Restroom 109 32.33 + Men's Restroom 108 32.33 + Cafe 103 - 11'-6" GWB band 52.51 + Cafe 103 - 9'-0" GWB band 43.33 + Grab & Go 20.49 + VEST-BOX-BEAM-TRACK 25.33 + VEST-LEDGER 12.67 + VEST-POSTS-TRACK 5 = 281.75 LF
Bracing 1-1/2" C.R. channel | LF | 1774.18 | 0.15 | 266.127 | 2040.307 | C.R. channel 16 ft | 128 | N/SHEET: 5/A-410, 2/A-410, 5/A-410, 3/A-410, 4/A-410, C25/A-101, G/A-221, H/A-221, E/A-221, I/A-221, F/A-221 ¦ Breakdown [DERIVED]: W2-01 193.32 + W2-03 51.76 + W2-04 228.8 + W2-05 51.68 + W2-06.1 36.24 + W2-06.5 16 + W2-07 30.08 + W2-08 51.76 + W2-09 51.76 + W5-01 22.88 + W3-01 3.67 + W3-02 12 + W3-05 3.67 + W3-03 12 + W3-06 3.67 + W3-04 3.67 + W4-28a 9 + W4-31a 9 + CW-01 8 + CW-02 8 + CW-03 8 + CW-04 8 + CW-05 8 + CW-06 8 + CW-07 8 + CW-08 8 + CW-09 8 + C-H1-N 101.2 + C-H1-W 52.88 + C-H2a 17.96 + C-H2b 8 + C-H3a 15.96 + C-H3b 27.04 + C-E2 113.96 + C-E1-S 79.72 + C-E1-P.2 14.68 + 2-03 36.12 + 5-01b 16.88 + I-02 13.84 + F-01 39 + 2-11 20.12 + 2-12 20.12 + 2-13 285.32 + 4-02 24.21 + 4-03 24.21 = 1,774.18 LF (rows = ROUNDUP(H x 12 / 48) - 1, x length)
Header / metal stud box beam | LF | 62.67 | 0.15 | 9.4005 | 72.0705 | stick 20 ft | 4 | N/SHEET: not applicable (see note)
Furring channel (ceilings) | LF | 286.44 | 0.15 | 42.966 | 329.406 | hat channel 12 ft | 28 | N/SHEET: 5/A-121, 1/A-121 ¦ Breakdown [DERIVED]: Women's Restroom 109 56.48 + Men's Restroom 108 56.41 + Cafe 103 - 11'-6" GWB band 100.05 + Cafe 103 - 9'-0" GWB band 42.67 + Grab & Go 30.84 = 286.45 LF
Carrying channel (ceilings) | LF | 159.16 | 0.15 | 23.874 | 183.034 | C.R. channel 16 ft | 12 | N/SHEET: 5/A-121, 1/A-121 ¦ Breakdown [DERIVED]: Women's Restroom 109 24.48 + Men's Restroom 108 24.44 + Cafe 103 - 11'-6" GWB band 60 + Cafe 103 - 9'-0" GWB band 38 + Grab & Go 12.24 = 159.16 LF
Hanger wire | LF | 1545.5 | 0.15 | 231.825 | 1777.325 | continuous coil (LF) | 1778 | N/SHEET: 5/A-121, 1/A-121 ¦ Breakdown [DERIVED]: Women's Restroom 109 144 + Men's Restroom 108 144 + Cafe 103 - 11'-6" GWB band 243 + Cafe 103 - 9'-0" GWB band 192 + Cafe Seating Area 102 - GWB cloud 715 + Grab & Go 107.5 = 1,545.5 LF (hangers @ 48" O.C. x drop to deck per room)
5/8" gypsum board, regular | SF | 4896.74 | 0.06 | 293.8044 | 5190.5444 | 4x12 ft sheet (Inputs) | 109 | N/SHEET: C25/A-101, 6/A-221, 2/A-410, I/A-221, 4/A-410, A-001A ¦ Breakdown [DERIVED]: CW-01 48 + CW-02 48 + CW-03 48 + CW-04 48 + CW-05 48 + CW-06 48 + CW-07 48 + CW-08 48 + CW-09 48 + SS-N 43.53 + SS-GG 23.84 + 2-03 261.87 + I-02 69.2 + 2-11 201.2 + 2-12 201.2 + 2-13 2,853.2 + 4-02 363.16 + 4-03 363.16 + I-03 10.6 + I-04 8.8 + I-05 65 = 4,896.76 SF (faces: length x face height x layers - openings; ceilings: RCP area)
5/8" gypsum board, MOISTURE RESISTANT | SF | 75.96 | 0.06 | 4.5576 | 80.5176 | 4x12 ft sheet (Inputs) | 2 | N/SHEET: 5/A-410, A-001A ¦ Breakdown [DERIVED]: 5-01b 75.96 = 75.96 SF (faces: length x face height x layers - openings; ceilings: RCP area)
Blocking FRT / 2X FRT wood | LF | 552.27 | 0.06 | 33.1362 | 585.4062 | 2x lumber 16 ft | 37 | N/SHEET: 7/A-413, 8A/A-413, 4/A-412, 6/A-412 ¦ Breakdown [DERIVED]: BLK-STOCK 387 + BLK-RECEIVING 69 + BLK-OFFICE 85.6 + BLK-BREAK 10.67 = 552.27 LF
5/8" gypsum board, Type X | SF | 8266.72 | 0.06 | 496.0032 | 8762.7232 | 4x12 ft sheet (Inputs) | 183 | N/SHEET: 2/A-410, 3/A-410, 4/A-410, C25/A-101, G/A-221, H/A-221, 6/A-221, 5/A-121, 4/A-121, 2/A-221, 4/A-210, A-001A ¦ Breakdown [DERIVED]: W2-01 1,933.2 + W2-03 619.08 + W2-04 1,973.4 + W2-05 174.14 + W2-06.1 81.54 + W2-06.5 38 + W2-08 174.33 + W2-09 232.92 + W3-01 29.36 + W3-02 96 + W3-05 29.36 + W3-03 96 + W3-06 29.36 + W3-04 29.36 + W4-28a 67.5 + W4-31a 67.5 + CW-01 16 + CW-02 16 + CW-03 16 + CW-04 16 + CW-05 16 + CW-06 16 + CW-07 16 + CW-08 16 + CW-09 16 + C-H1-N 572.53 + C-H1-W 264.4 + C-H2a 89.8 + C-H3a 119.7 + C-H3b 135.2 + SS-N 226.7 + ceiling Cafe 103 - 11'-6" GWB band 125.07 + ceiling Cafe 103 - 9'-0" GWB band 50.67 + ceiling Cafe Seating Area 102 - GWB cloud 573.69 + ceiling Cafe 103 - 11'-0" GWB zone 109.65 + ceiling Grab & Go 25.16 + VEST-GWB 105.5 + CLOUD-FASCIA-GWB 53.6 = 8,266.72 SF (faces: length x face height x layers - openings; ceilings: RCP area)
5/8" gypsum board, Type X W.R. (water resistant) | SF | 940.87 | 0.06 | 56.4522 | 997.3222 | 4x12 ft sheet (Inputs) | 21 | N/SHEET: 2/A-410, 5/A-410, 5/A-121, A-001A ¦ Breakdown [DERIVED]: W2-05 67.59 + W2-06.1 181.2 + W2-06.5 60.99 + W2-07 218.08 + W2-08 187.75 + W5-01 102.96 + ceiling Women's Restroom 109 61.19 + ceiling Men's Restroom 108 61.11 = 940.87 SF (faces: length x face height x layers - openings; ceilings: RCP area)
8" metal joist (ceiling box) | LF | 88 | 0.15 | 13.2 | 101.2 | stick 20 ft | 6 | N/SHEET: 4/A-210 ¦ 8" JOISTS @ 16" O.C.: ROUNDUP(152/16)+1 = 11 x (7'-8" + 2" + 2" = 8.0 ft) = 88.0 LF (1/A-210 12'-8" N-S)
USG drywall suspension main tee DGLW26 | LF | 194.16 | 0.15 | 29.124 | 223.284 | main tee 12 ft | 19 | N/SHEET: 4/A-121, 1/A-121 ¦ USG drywall suspension grid: main tee ROUNDUP(14.773/4.0)+1 = 5 x 38.833 = 194.16; cross tee ROUNDUP(38.833/1.333)+1 = 31 x 14.773 = 457.96; channel + angle molding 107.21 each
USG drywall suspension cross tee DGLW424 | LF | 457.96 | 0.15 | 68.694 | 526.654 | cross tee 4 ft | 132 | N/SHEET: 4/A-121, 1/A-121 ¦ USG drywall suspension grid: main tee ROUNDUP(14.773/4.0)+1 = 5 x 38.833 = 194.16; cross tee ROUNDUP(38.833/1.333)+1 = 31 x 14.773 = 457.96; channel + angle molding 107.21 each
USG channel molding DGCM27 | LF | 107.21 | 0.15 | 16.0815 | 123.2915 | molding 12 ft | 11 | N/SHEET: 4/A-121, 1/A-121 ¦ USG drywall suspension grid: main tee ROUNDUP(14.773/4.0)+1 = 5 x 38.833 = 194.16; cross tee ROUNDUP(38.833/1.333)+1 = 31 x 14.773 = 457.96; channel + angle molding 107.21 each
USG angle molding DGWM24 | LF | 107.21 | 0.15 | 16.0815 | 123.2915 | molding 12 ft | 11 | N/SHEET: 4/A-121, 1/A-121 ¦ USG drywall suspension grid: main tee ROUNDUP(14.773/4.0)+1 = 5 x 38.833 = 194.16; cross tee ROUNDUP(38.833/1.333)+1 = 31 x 14.773 = 457.96; channel + angle molding 107.21 each
METAL trim - corner bead, casing bead, shadow molding, gypsum edge trim | LF | 328 | 0.15 | 49.2 | 377.2 | trim stick 10 ft | 38 | N/SHEET: F/A-221 ¦ Breakdown [DERIVED]: CW-01..09 corner bead 288 + F-01 corner bead 40 = 328 LF
1/2" cement board / cementitious backer | SF | 980.19 | 0.06 | 58.8114 | 1039.0014 | 4x12 ft sheet (Inputs) | 22 | N/SHEET: E/A-221, A/A-221, B/A-221, D/A-221, C/A-221 ¦ Breakdown [DERIVED]: C-E2 Cafe Workroom 104 569.8 + C-E1-S Cafe 103 193.69 + C-E1-P.2 Cafe Workroom 104 44.04 + C-A-1 Customer side (counter) 28.27 + C-A-1 Cafe side (counter) 28.27 + C-A-2 Customer side (counter) 10.75 + C-A-2 Cafe side (counter) 10.75 + C-A-3 Customer side (counter) 17.17 + C-A-3 Cafe side (counter) 17.17 + C-B Customer side (counter) 7.45 + C-B Cafe side (counter) 7.45 + C-D Customer side (counter) 16.65 + C-D Cafe side (counter) 16.65 + C-C Customer side (counter) 6.04 + C-C Cafe side (counter) 6.04 = 980.19 SF
FRP panels | SF | 2001.38 | 0.06 | 120.0828 | 2121.4628 | FRP panel 40 SF (Inputs) | 54 | N/SHEET: 3/A-410, 4/A-410, 1/A-221, 1/A-226B, 2/A-226B, 3/A-226B, 4/A-226B, 9/A-200, 10/A-200, 11/A-200, 12/A-200, 1/A-225, 4/A-225, 6/A-225 ¦ Breakdown [DERIVED]: FRP-TYPES-3-4 936.74 + FRP-1-CAFE-WORKROOM 852.2 + FRP-1-JANITOR 155.44 + FRP-1-CAFE-BELOW-COUNTER 57 = 2,001.38 SF
Moment clip ClarkDietrich MC series with stiffening plate (A/A-410), one per stud of types 3 / 4 | PCS | 162 | 0.15 | 24.3 | 186.3 | piece | 187 | N/SHEET: A/A-410, 3/A-410, 4/A-410 ¦ Breakdown [DERIVED]: MOMENT-CLIPS-T3-T4 162 = 162 PCS ¦ one ClarkDietrich MC clip per stud: type 3 = 40 studs + type 4 = 122 studs = 162 (estimator decision 2026-10-27, RFI-28 A)
Hilti Kwik HUS-EZ 1/4" x 1-5/8" concrete screws at the moment clips (3/A-410, 4/A-410) | PCS | 324 | 0.15 | 48.6 | 372.6 | piece | 373 | N/SHEET: 3/A-410, 4/A-410 ¦ Breakdown [DERIVED]: HUS-EZ-T3-T4 324 = 324 PCS ¦ 3/A-410, 4/A-410 "(2)-1/4"ø X 1 5/8" HILTI KWIK HUSEZ CONCRETE SCREW AND MOMENT CLIP": 162 clips x 2 = 324 (estimator decision 2026-10-27, RFI-28 A)
#10-16 screws at the moment clips, (1) at each flange (A/A-410) | PCS | 324 | 0.15 | 48.6 | 372.6 | piece | 373 | N/SHEET: A/A-410 ¦ Breakdown [DERIVED]: SCREWS-10-16-MOMENT-CLIPS 324 = 324 PCS ¦ A/A-410 "(1) #10-16 SCREW @ EACH FLANGE": 162 clips x 2 = 324 (estimator decision 2026-10-27, RFI-28 A)
Metal corner guard 2"x2"x72" at outside corners (A-001A) | PCS | 72 | 0.15 | 10.8 | 82.8 | piece | 83 | N/SHEET: A-001A, A-101, A-221 ¦ Breakdown [DERIVED]: CORNER-GUARDS-METAL-72 72 = 72 PCS ¦ A-001A "INSTALL METAL CORNER GUARDS (2"X2"X72") AT ALL OUTSIDE CORNERS": C25 column surrounds 9 x 4 = 36 + type 3 posts 16 + type 4 hourglass caps 8 + type 2 (Storage SW 1, C26 alcove 4) 5 + Cafe 7 = 72 (estimator decision 2026-10-27, RFI-29)
Stainless steel corner guard 48" A.F.F. (C22/A-101) | PCS | 1 | 0 | 0 | 1 | piece | 1 | N/SHEET: C22/A-101 ¦ Breakdown [DERIVED]: CORNER-GUARD-STAINLESS-48 1 = 1 PCS ¦ C22/A-101 "STAINLESS STEEL CORNER GUARDS AT 48" A.F.F. FOR ALL OUTSIDE GYPSUM BOARD CORNERS AT STOCKROOM WALLS": the corner the C22 leader points to (loading zone bend) = 1 (estimator decision 2026-10-27, RFI-29)
Control joint, gypsum board walls (ASTM C840, 30 ft max) | LF | 250 | 0.15 | 37.5 | 287.5 | trim stick 10 ft | 29 | N/SHEET: A-101, A-410 ¦ Breakdown [DERIVED]: CONTROL-JOINTS-T2 250 = 250 LF ¦ ASTM C840 30 ft max: W2-01 48.77 LF -> 1, W2-03 94.24 LF -> 3, W2-04 56.76 LF -> 1 = 5 joints x 25.0 ft x 2 faces = 250.0 LF (estimator decision 2026-10-27, RFI-24 A)
#8 screws at diagonal brace ends, 2 per end (manufacturer rule; 3/A-410 prints none) | PCS | 512 | 0.15 | 76.8 | 588.8 | piece | 589 | N/SHEET: 3/A-410 ¦ Breakdown [DERIVED]: SCREWS-8-BRACE-ENDS 512 = 512 PCS ¦ diagonal braces 117 (type 2, 468.0 LF / 4.0) + 11 (Cafe, 44.0 LF / 4.0) = 128 braces x 2 ends x 2 = 512 (estimator decision 2026-10-27, RFI-51)
3-5/8" stud, framed soffit 2/A-221 (LF) | LF | 89.61 | 0.15 | 13.4415 | 103.0515 | stick 20 ft | 6 | N/SHEET: 2/A-221, 1/A-121 ¦ Breakdown [DERIVED]: Cafe 103 - 11'-0" GWB zone: framed_soffit: ROUNDUP(23.25/(16/12))+1 = 19 joists x 4.716 = 89.61 LF 3-5/8" joists = 89.61 LF (framed soffit joists, 2/A-221)
FRT plywood substrate (3/4 in.) | SF | 376.32 | 0.06 | 22.5792 | 398.8992 | 4x12 ft sheet (Inputs) | 9 | N/SHEET: 4/A-226A, 21/A-201, 5/A-210, 4/A-210, A/A-221, A-410 (ALL PLYWOOD NEEDS TO BE FRT) ¦ Breakdown [DERIVED]: MENU-BOARD-FRT 60.6 + RESTROOM-BACKING-FRT 17.77 + VEST-POSTS-PLYWOOD 105 + VEST-PLYWOOD 106.62 + COUNTER-CUST-PLY 86.33 = 376.32 SF (strip length x height)
FRT plywood substrate (5/8 in.) | SF | 3634.8 | 0.06 | 218.088 | 3852.888 | 4x12 ft sheet (Inputs) | 81 | N/SHEET: 1/A-226A, 3/A-410, 4/A-410, G/A-221, H/A-221, I/A-221, E/A-221, F/A-221, A-410 (ALL PLYWOOD NEEDS TO BE FRT) ¦ Breakdown [DERIVED]: SS-N-WD1-FRT 318.78 + TYPE-3-A-FRT 309.44 + TYPE-4-A-FRT 627.3 + H1-01-FRT 264.4 + H1-02-FRT 506 + H3-01-FRT 54.08 + I-01-FRT 79.8 + I-02-FRT 69.2 + H2-01-FRT 89.8 + E1-01-FRT 72.6 + H2-02-FRT 40 + H2-02-FRT 40 + E2-01-FRT 569.8 + E1-02-FRT 398.6 + F-01-FRT 195 = 3,634.8 SF (strip length x height)
5/8" FRT plywood at canopy column wraps | SF | 195 | 0.06 | 11.7 | 206.7 | 4x12 ft sheet (Inputs) | 5 | N/SHEET: F/A-221, A-410 (ALL PLYWOOD NEEDS TO BE FRT) ¦ Breakdown [DERIVED]: F-01 195 = 195 SF (strip length x height)
Hanger wire 12 ga - hanger count (one per hanger, height per room) | PCS | 109 | 0 | 0 | 109 | each | 109 | N/SHEET: 5/A-121, 1/A-121 ¦ Breakdown [DERIVED]: Women's Restroom 109 9 + Men's Restroom 108 9 + Cafe 103 - 11'-6" GWB band 18 + Cafe 103 - 9'-0" GWB band 12 + Cafe Seating Area 102 - GWB cloud 55 + Grab & Go 6 = 109 PCS (one per hanger)
Additional head track at openings over 4'-0" wide - extended to every door as a 2-piece track header (R.O. + 1'-4") x 2 (RFI-09) | LF | 62.67 | 0.15 | 9.4005 | 72.0705 | stick 20 ft | 4 | N/SHEET: 1/A-500 ¦ Door 4 (W2-04): (3.0 + 2 x 0.667) x 1 x 2 pieces = 8.67; Door 9 (W2-06.1): (3.0 + 2 x 0.667) x 1 x 2 pieces = 8.67; Door 7 (W2-06.5): (3.0 + 2 x 0.667) x 1 x 2 pieces = 8.67; Door 5 (W2-08): (3.0 + 2 x 0.667) x 1 x 2 pieces = 8.67; Door 6 (W2-09): (3.0 + 2 x 0.667) x 1 x 2 pieces = 8.67; DR-104 (C-H2a): (4.0 + 2 x 0.667) x 1 x 2 pieces = 10.67; Door 8 (2-03): (3.0 + 2 x 0.667) x 1 x 2 pieces = 8.67
Stud reinforcement at MEP penetrations | PCS | 10 | 0 | 0 | 10 | each | 10 | [DERIVED] N/SHEET: M-102, A-101 ¦ X01 (W2-03, 14" DIA) 1 + X02 (W2-06.1, 6" DIA) 1 + X03 (W2-06.5, 6" DIA) 1 + X04 (W5-01, 6" DIA) 1 + X05 (W2-07, 6" DIA) 1 + X06 (W2-08, 10" DIA) 1 + X07 (W2-09, 8" DIA) 1 + X08 (W2-01, 10" DIA) 1 + T01 (W2-03, TG-1 12"x10") 1 + T02 (W2-02, TG-1 14"x6") 1 = 10 plates
Extra framing - ATM recess (only what a detail prints at the recess; the wall stays in its type) | LF | 0 | 0.15 | 0 | 0 | stick 20 ft | 0 | [DERIVED] N/SHEET: A-101 ¦ none: no ATM / recessed equipment detail in the set (A-410 / A-221 / A-200 read) (A-101)
2-1/2" CFMF @ 16" O.C. at coiling grille head (detail per plans) | LF | 0 | 0.15 | 0 | 0 | stick 20 ft | 0 | N/SHEET: A-000, A-101, A-410, A-500 ¦ none: no parapet infill, coiling grille or duct sleeve detail in the set (A-000 index; A-101, A-410, A-500)
Gypsum board jamb return at openings | SF | 0 | 0.06 | 0 | 0 | 4x12 ft sheet (Inputs) | 0 | [RFI] N/SHEET: A-101, A-200, A-221, A-121, DR-104 ¦ RFI: No opening detail in the sheets read (A-101, A-200, A-221, A-121) shows gypsum board returning at jambs/head of cased or storefront openings; per estimator rule jamb return is counted only where a detail draws it. Delta: Carried at 0 SF. If confirmed gypsum returns at openings: + (R.O. width + 2 x head height) x wall thickness x layers per opening, DR-4..DR-9, DR-104.
PVC trim - edge trim molding and inside corner molding at the FRP, incl. outside corners, door edges and division bars every 4' (see breakdown) | LF | 887.62 | 0.06 | 53.2572 | 940.8772 | trim stick 10 ft | 95 | [DERIVED] N/SHEET: 3/A-225, 1/A-225, 1/A-221, 9/A-200, 10/A-200, 11/A-200, 12/A-200, 3/A-410, 4/A-410, 4/A-225 ¦ PVC-CAFE-WORKROOM: J-mold at bottom (3/A-225 "FRP J-MOLD AT BOTTOM OF FRP PANEL") 85.22 - door 3 4.0 = 81.22 + top edge 85.22 + inside corners 6 x 10.0 = 60.0 + outside corners (stub C-H2b end) 2 x 10.0 = 20.0 + door 3 edge trim 2 x 8.0 + 4.0 = 20.0 = 266.44 LF (estimator decision 2026-10-28); PVC-JANITOR: J-mold at bottom 19.43 - door 7 3.0 = 16.43 + top edge at 8'-0" 19.43 + inside corners 4 x 8.0 = 32.0 + door 7 edge trim 2 x 7.0 + 3.0 = 17.0 = 84.86 LF (estimator decision 2026-10-28); PVC-TYPES-3-4: J-mold at bottom 122.32 + type 3 vertical edge trim 2 walls x 2 ends x 8.0 = 32.0 (top: corner bead already carried; hourglass cap outside corners: metal corner guard A-001A governs, no PVC) = 154.32 LF (estimator decision 2026-10-28); PVC-CAFE-BELOW-COUNTER: 4/A-225 "FRP J-MOLD AT BOTTOM OF FRP PANEL" above B-2 on the C-E1-S Cafe face: 19.0 LF (estimator decision 2026-10-28); FRP-DIVISION-BARS: division bars at every 4' panel joint: Work Room 18 x 10.0 = 180 + Janitor 2 x 8.0 = 16 + type 3 4 x 8.0 = 32 + type 4 18 x 7.5 = 135 = 363 LF (estimator decision 2026-10-28; A-001A FRP per manufacturer)
Power-driven fasteners and duct sleeves - duct sleeves at the duct crossings (M-102) | PCS | 8 | 0 | 0 | 8 | each | 8 | [DERIVED] N/SHEET: M-102, A-101 ¦ duct sleeves = X01 (W2-03) 1 + X02 (W2-06.1) 1 + X03 (W2-06.5) 1 + X04 (W5-01) 1 + X05 (W2-07) 1 + X06 (W2-08) 1 + X07 (W2-09) 1 + X08 (W2-01) 1 = 8
Access panel | PCS | 0 | 0 | 0 | 0 | each | 0 | [DERIVED] N/SHEET: A-121 ¦ none: no access panel markers read in A-121 for GWB ceilings (A-121)
Drywall screws #7 x 1-1/4" Type S bugle head (board on 25/20 ga studs) | PCS | 17016.35 | 0 | 0 | 17016.35 | each | 17017 | [DERIVED] N/SHEET: GA-216 ¦ Inputs!B20 (Drywall screws per SF of board = 1.2) x 14180.3 SF of board | 17016.36
Framing screws #8-18 x 1/2" pan head (25/20 ga studs) | PCS | 2580 | 0 | 0 | 2580 | each | 2580 | [DERIVED] N/SHEET: A-410 note 8.A ¦ Inputs!B21 (Framing screws per stud piece = 4) x 645 stud pieces ¦ Breakdown [DERIVED]: 4 x 645 stud pieces of the 25/20 ga walls and other framing [2-03 13 + 2-11 5 + 2-12 5 + 2-13 55 + 4-02 20 + 4-03 20 + 5-01b 5 + C-A-1 11 + C-A-2 5 + C-A-3 6 + C-B 4 + C-C 3 + C-D 8 + C-E1-P.2 4 + C-E1-S 16 + C-E2 23 + C-H1-N 20 + C-H1-W 11 + C-H2a 9 + C-H2b 3 + C-H3a 5 + C-H3b 7 + I-02 4 + SS-GG 6 + SS-N 19 + W2-01 40 + W2-03 12 + W2-04 48 + W2-05 11 + W2-06.1 13 + W2-06.5 8 + W2-07 7 + W2-08 16 + W2-09 16 + W3-01 4 + W3-02 12 + W3-03 12 + W3-04 4 + W3-05 4 + W3-06 4 + W4-28a 10 + W4-31a 10 + W5-01 7 (walls 525); CW-01 12; CW-02 12; CW-03 12; CW-04 12; CW-05 12; CW-06 12; CW-07 12; CW-08 12; CW-09 12; F-01 12; I-03.6" 0; I-04.6" 0; I-05.6" 0] = 2580 | 2580
Power-driven fasteners, slab pins for the bottom track | PCS | 456.19 | 0 | 0 | 456.19 | each | 457 | [DERIVED] N/SHEET: A-410 note 8.F (9/A-410 = alternate) ¦ 608.25 LF of interior bottom track on slab / Inputs!B22 (Power-driven pin spacing (ft) = 1.33333) | 456.1876
Expansion anchors Hilti 1/4" Kwik Bolt II, exterior bottom track @ 8" O.C. | PCS | 0 | 0 | 0 | 0 | each | 0 | [DERIVED] N/SHEET: 1/DM-101 ¦ none: no new exterior wall on slab - perimeter walls 1 / 1A / 1B / 1C are EXISTING (RFI-01; 1/DM-101, A-101) | 0
Joint compound, all purpose | LB | 1020.98 | 0 | 0 | 1020.98 | lb | 1021 | [DERIVED] N/SHEET: A-001A Div 09 A.8 ¦ Inputs!B23 (Joint compound (lb per SF) = 0.072) x 14180.3 SF of board | 1020.9816
Joint tape, paper | LF | 5246.71 | 0 | 0 | 5246.71 | LF | 5247 | [DERIVED] N/SHEET: A-001A Div 09 A.8 ¦ Inputs!B24 (Joint tape (LF per SF) = 0.37) x 14180.3 SF of board | 5246.711
Level 5 finish | SF | 0 | 0.06 | 0 | 0 | SF | 0 | [DERIVED] N/SHEET: A-101, A-121, A-200, A-221 ¦ RFI: No finish schedule tag or key note reading LEVEL 5 was found in the sheets read (A-101, A-121, A-200, A-221); finish level is not printed. Delta: Carried at 0 SF (Level 4 assumed per Clarifications). If Level 5 is required: add SF = sum of L x (height - base) of the tagged faces.
Deflection clips at non-load-bearing walls to structure | PCS | 0 | 0 | 0 | 0 | each | 0 | [DERIVED] N/SHEET: 5/A-410 ¦ none: A-410 note 8 typical fasteners / slip track detail 5/A-410 draw slip track in the type; no clip note found in general notes
Heavy-gauge framing screws #10-16 x 3/4" pan head (18/16/14 ga studs) | PCS | 0 | 0 | 0 | 0 | each | 0 | [DERIVED] N/SHEET: A-410 ¦ none in the set
Type S-12 drywall screws #6 x 1-1/4" (board on 18/16/14 ga studs) | PCS | 0 | 0 | 0 | 0 | each | 0 | [DERIVED] N/SHEET: A-410 ¦ none in the set

## Pending Items
RFI | Question / condition | Delta of each alternative
RFI-ACC-slab-pins | CLOSED - estimator decision 2026-10-27: One row @ 16" O.C. (A-410 note 8.F spacing). N/SHEET: A-410 note 8.F; 9/A-410. | Applied: slab pins 777.43 -> 388.72 (518.29 LF / 1.333; -388.71).
RFI-ACC-gypsum-board-jamb-return | gypsum board jamb return: No opening detail in the sheets read (A-101, A-200, A-221, A-121) shows gypsum board returning at jambs/head of cased or storefront openings; per estimator rule jamb return is counted only where a detail draws it. | Carried at 0 SF. If confirmed gypsum returns at openings: + (R.O. width + 2 x head height) x wall thickness x layers per opening, DR-4..DR-9, DR-104.
RFI-ACC-level-5-finish | Level 5 finish: No finish schedule tag or key note reading LEVEL 5 was found in the sheets read (A-101, A-121, A-200, A-221); finish level is not printed. | Carried at 0 SF (Level 4 assumed per Clarifications). If Level 5 is required: add SF = sum of L x (height - base) of the tagged faces.
RFI-ACC-stud-reinforcement-mep | CLOSED - estimator decision 2026-10-27: Counted on M-102 + A-101: 8 duct crossings at the full-height walls (types 2 / 5) + 2 TG-1 transfer grille openings (W2-03, W2-02). N/SHEET: M-102; A-101. | Applied: stud reinforcement plates 0 -> 10 (8 ducts x 1 + 2 TG-1); duct sleeves 0 -> 8.
RFI-ACC-pvc-trim-at-frp | PVC trim at FRP: FRP-1 is called at the cafe side of counters / cafe workroom (A-221) but its perimeter is not measured in this reading (FRP panel SF carried as RFI-07), so PVC edge trim LF cannot be derived. | Carried at 0 LF. If FRP-1 is confirmed in scope: 2 x net FRP perimeter (doors deducted) + inside corners x top height, per estimator rule PVC trim at FRP.
RFI-01 | CLOSED - estimator decision 2026-10-24 (rev1): perimeter walls types 1 / 1A / 1B / 1C are EXISTING (1/DM-101 legend solid = to remain + key note 3 "EXTERIOR WALL PATCH AND REPAIR AS REQUIRED TO MAINTAIN EXISTING FIRE RATING"; A-101 Construction Legend "EXISTING EXTERIOR WALL" / "EXISTING PARTITION"; A-002 "PERIMETER STUDS, INSULATION, VAPOR BARRIER F/I BY LL"). Perimeter framing (studs, track, bracing, 1B sheathing) EXCLUDED. Interior face patch & repair (1/DM-101 key note 3, A-101 C5) = ALLOWANCE, amount: $ ________ (blank, estimator to fill). rev2 (estimator decision 2026-10-25): break room kitchenette W.R. on existing EXT-07 (6/A-412, 7/A-412) is INSIDE this patch & repair allowance; allowance amount stays BLANK (decided). A-410 types 1, 1A, 1B, 1C label the interior board "5/8" GYP BD BY FUTURE TENANT": EXCLUDED with that citation, consistent with this decision. A-413 7/8A general note "IF SHELVING IS TO BE INSTALLED ON EXISTING WALL, G.C. IS TO REMOVE AND REPLACE GYP. BOARD AS REQUIRED FOR INSTALLATION OF WOOD BLOCKING": inside this patch & repair allowance. | Applied: - 417.43 LF of perimeter walls (17 walls); 3-5/8" stud 16,812.96 -> 10,120.39 LF; 8" stud 2,332.99 -> 0; 1/2" exterior sheathing 2,469.22 -> 0 SF; bottom / top track 1,051.87 -> 634.44 LF each; bracing 5,230.74 -> 2,827.81 LF. Allowance: blank.; board by future tenant on the existing perimeter (A-410 types 1 / 1A / 1B / 1C): upper bound 417.43 LF x 25.0 = 10,436 SF 5/8" Type X if it were ever in our scope.
RFI-02 | N/A after RFI-01 (perimeter walls existing, rev1): the north 1A / 1 boundary no longer affects the take-off (both types are existing, excluded). | none
RFI-03 | CLOSED - estimator decision 2026-10-27: B.O. deck 25'-0" kept. N/SHEET: 1/A-400A; 1/A-400B. | No change.
RFI-04 | CLOSED - Review Item rev3 (estimator decision 2026-10-26): type 2 > 22 ft: 3-5/8" 14 ga SJ + diagonal braces @ 32" O.C. to structure (3/A-410 Top Track Detail "PROVIDE DIAGONAL BRACING AT 32" O.C. TO STRUCTURE ABOVE (TYP.)"); brace member / length not printed - estimator choice 3-5/8" 20 ga stud x 4 ft at 45 deg. same precedent applied to the Cafe 3-5/8" walls to deck (C-H2a, C-H2b, C-F): 14 ga SJ + 11 diagonal braces = 44.0 LF. | Applied: 117 braces x 4.0 ft = 468.0 LF (type 2) + 44.0 LF (Cafe) 3-5/8" 20 ga stud (member and length = estimator choice). Citation history: rev0-rev2 cited the partition type 3 section, rev3-rev6 cited 8/A-410 (that bubble is the Typ. Connection Detail); the Top Track Detail is bubble 3/A-410.
RFI-05 | CLOSED - estimator decision 2026-10-27: Closed: types E1 / E2 counted once; type 1 existing per RFI-01. N/SHEET: E/A-221; A-410. | No change.
RFI-06 | CLOSED - Review Item rev3 (estimator decision 2026-10-26): Cafe walls H1, H2a, H2b, H3a, H3b, F studs TO DECK 25'-0" (1/A-400B draws the Cafe walls floor to B.O. DECK; A-226A elevations break at the top; no section prints a stud top). Board per face = ceiling + 6" (A-410 partition note 3): Workroom ACT-1 10'-0" -> 10'-6"; Grab & Go GWB 7'-1" -> 7'-7"; Cafe open-to-deck strip at H2a (1/A-121 PT-6 OPEN TO DECK) -> to deck. | Applied (faces already at these heights in rev2; RCP evidence on 1/A-121).
RFI-07 | N/A after RFI-01 (perimeter walls existing, rev1): exterior furring 3-5/8" over 22'-0" (types 1, 1A, 1C) is existing, excluded. | none
RFI-08 | CLOSED - Review Item rev3 (estimator decision 2026-10-26): type I WD-1 top = 15'-0" A.F.F. (6/A-226A; elevation bubble on 1/A-221 looks west at the type I face, verified). | Applied (rev3 + rev5): type I 5/8" FRT plywood floor to 15'-0" (6/A-226A) = (C-I 2.31 + C-I-P.1 1.00 + end faces C-I-E1 / C-I-E2 1.21) 4.52 LF x 15.0 = 67.74 SF; GWB 15'-0" to deck 4.52 x 10.0 = 45.16 SF.
RFI-09 | CLOSED - estimator decision 2026-10-27: 2-piece track header at every door. N/SHEET: A-500 door schedule; 1/A-500. | Applied: head track at door openings 10.67 -> 83.32 LF ((R.O. + 1'-4") x 2 at every door in a new wall; replaces RFI-31).
RFI-10 | N/A after RFI-01 (perimeter walls existing, rev1): doors 10, 12, 13 are existing doors in existing perimeter walls (A-500 EXISTING V.I.F.); no framing in our scope. | none
RFI-11 | CLOSED - estimator decision RFI-11 (rev1) + W.R. gypsum board on all faces of Women's 109, Men's 108, Janitor 107 and the drinking fountain alcove (A-410 Partition Notes 2 "PROVIDE WATER RESISTANT GYPSUM BOARD IN ALL BATHROOMS AND JANITOR'S CLOSET FOR WALL AND CEILING CONSTRUCTION", note 7, "*" note, 2/A-410, 5/A-410; A-001A Div 09 A.4) and on the restroom GWB ceilings (same note 2; 1/A-121 GWB 9'-0"). Cafe Work Room 104: NO W.R. - G/A-221 draws only 5/8" FRT plywood on the Work Room side (FRP-1 finish, A-510); there is no gypsum board on that face (rev6 removes the 570.36 SF GWB faces). | Applied (rev7): 5/8" Type X W.R. = 1,092.59 SF = walls (Women's 222.93 + Men's 223.02 + Janitor 485.75 + alcove corridor 88.63) + restroom ceilings 122.30 - 1'-2" cement board base 50.04 (22/A-201).
RFI-12 | CLOSED (base) / OPEN (installer of tile)(rev7): 22/A-201 Tile Base Detail prints "5/8" CEMENT BOARD" with "1'-2" CEMENT BOARD BASE" and 5/8" W.R. GYP. BD. above (A-001A Div 09 J.2). Corridor 110 wall tile (A-510) backer: not detailed. | Applied: + 50.04 SF cement board base on the restroom faces of new walls and the same SF out of W.R. Open: Corridor 110 wall tile backer - each 1 ft of tile height = 93.44 SF cement board instead of Type X.
RFI-13 | CLOSED - estimator decision 2026-10-27: FRP-1 in our scope. N/SHEET: A-510; 1-4/A-226B; 9-12/A-200. | Applied: FRP + 1,030.64 SF (Cafe Work Room 875.20 + Janitor 155.44) + PVC trim (J-mold top / bottom + inside corners). Revised by RFI-55 (estimator decision 2026-10-28): Work Room FRP 852.20 SF (finished dimensions, 1/A-221); PVC trim per real corners / edges + division bars.
RFI-14 | CLOSED - estimator answer (rev4): Cafe soffit bottom = 11'-0" (A-121 RCP governs over 1/A-226A 9'-0"); north face sign band WD-1 top = 15'-0" (same as east face, 6/A-226A). Both faces: WD-1 11'-0" to 15'-0" with 5/8" FRT plywood behind; GWB above to deck and at the soffit bottom (2/A-221). | Applied: SS-N FRT 22.77 x 4.0 = 91.08 SF (rev3 45.54 at 9'-0"/11'-0"); SS-N GWB 14 -> 10 ft; SS-E unchanged (FRT 40.48 SF, GWB 10 ft).
RFI-15 | CLOSED - Review Item rev3 (estimator decision 2026-10-26): Cafe Seating cloud = USG drywall suspension grid as drawn on 4/A-121 (DGLW26 main tee, DGLW424 cross tee, DGCM27 channel molding, DGWM24 angle molding); carrying channel direction E-W confirmed (joists N-S: 1/A-400A joists cut in section, 2/A-400A joists in profile). | Applied: main tee 194.16 LF (5 x 38.833, @ 48" USG standard), cross tee 457.96 LF (31 x 14.773 = 124 pcs, @ 16" USG standard; 24" alt. = 22 rows / 88 pcs), DGCM27 107.21 LF, DGWM24 107.21 LF; removed from the cloud: furring -310.23 LF, carrying -194.17 LF, ceiling track -107.21 LF.
RFI-16 | CLOSED - estimator answer (rev4): vestibule post sheathing = 3/4" FRT plywood, 4 faces, full height (5/A-210 "5/8 GYP. BOARD SHEATHING AS REQUIRED" -> estimator: plywood). | Applied: 6 posts x 4 faces x 5" x 10.5 ft = 105.0 SF 3/4" FRT plywood (6 posts per 1/A-210).
RFI-17 | CLOSED - estimator answer (rev4): column surrounds C25 stud spacing = 16" O.C. (as carried); count 9. | none (as carried)
RFI-18 | CLOSED - Review Item rev3 (estimator decision 2026-10-26): type 4 curved walls = face-average arc 25.68 LF each (estimator choice vs printed 25'-1"). | Applied: + 1.17 LF type 4 (83.64 LF).
RFI-19 | CLOSED - Review Item rev3 (estimator decision 2026-10-26): board height where a ceiling exists = ceiling + 6" (2/A-410, A-410 partition note 3). Kept. | none
RFI-20 | CLOSED - audit rev4 row 6 (rev5): Grab & Go header soffit QUANTIFIED from the plan: 6'-2" HOLD (1/A-221) x (B.O. deck 25'-0" - Grab & Go GWB 7'-1", 1/A-121) with 6" metal studs @ 16" O.C. (3/A-221); 5/8" FRT plywood substrate on the east face, GWB at the soffit bottom. T.O. WD-1 not printed -> RFI-34. | Applied: SS-GG 6" studs 6 x 17.917 = 107.5 LF; ceiling / soffit track 6.167 x 2 = 12.33 LF; bracing 4 rows x 6.167 = 24.67 LF (5/A-410); 5/8" FRT plywood 6.167 x 17.917 = 110.49 SF; bottom GWB 3.73 SF.
RFI-21 | CLOSED - estimator decision 2026-10-27: Fascia GWB at the Cafe Seating cloud. N/SHEET: 4/A-121. | Applied: 5/8" Type X + 53.6 SF (107.21 LF x 0.5 ft); edge trim already carried.
RFI-22 | CLOSED - estimator decision 2026-10-27: One face of types 3 / 4 (122.32 LF) = 5/8" FRT plywood + FRP (A-410 building dept note: all plywood FRT). N/SHEET: 3/A-410; 4/A-410. | Applied: 5/8" FRT plywood + 936.74 SF, FRP + 936.74 SF, 5/8" Type X - 936.74 SF on that face, PVC trim + 244.64 LF. Revised by RFI-55 (estimator decision 2026-10-28): types 3 / 4 PVC 154.32 LF (hourglass cap corners take the metal corner guard) + division bars 167 LF.
RFI-23 | CLOSED - estimator decision 2026-10-24 (rev1): FRT blocking taken off with the counts and rows per detail: stock room shelving 7/A-413 (3 rows), receiving table 8A/A-413 (4 rows), Manager's Office 3, 4/A-412 (4 rows), break room cabinets 6/A-412 (2 rows); restroom backing 21, 26/A-201 (10 pcs 3/4" FRT plywood); Cafe menu boards 4/A-226A continuous 3/4" FRT plywood 31" high x C-E1-S. | Applied: FRT blocking 568.27 LF FRT + 2X wood 0.00 LF (2/A-500) (387.0 + 69.0 + 85.6 + 10.67 + FE cabinets 16.0, rev7); 3/4" FRT plywood + 60.61 SF menu boards (23.46 x 31/12) + 17.78 SF restroom backing (10 pcs x 16" bay x 16" high, rev2 (estimator decision 2026-10-25): 13.33 x 16/12). rev5: water heater backing (P-201) carried conservatively -> RFI-32; janitor 3/4" FRT plywood area (11/A-200) carried 17.0 SF -> RFI-33; W-3 surface blocking (1/A-414, 7/A-414) -> RFI-36.
RFI-24 | CLOSED - estimator decision 2026-10-27: Control joints per ASTM C840 (30 ft max). N/SHEET: A-101; A-410. | Applied: control joint + 250.0 LF (W2-01 1, W2-03 3, W2-04 1 = 5 joints x 25.0 ft x 2 faces).
RFI-25 | Merged into RFI-01 allowance (rev1): demising / perimeter wall patch & repair (A-101 C5, 1/DM-101 key note 3) = ALLOWANCE, amount blank. | Allowance: $ ________ (blank)
RFI-26 | N/A after RFI-01 (perimeter walls existing, rev1): type 1B (and its 1/2" exterior gyp sheathing) is existing, excluded. | none
RFI-27 | CLOSED - estimator decision 2026-10-24 (rev1): all 5/8" gyp bd on new walls AND GWB ceilings = Type X (A-001A Div 09 A.2; 4/A-121, 5/A-121 - rev2 (estimator decision 2026-10-25): ceilings to Type X); W.R. faces = 5/8" Type X W.R. No 5/8" regular remains. | Applied (rev7): 5/8" Type X 14,266.95 SF = walls 13,204.92 + GWB ceilings 884.24 (Cafe 103 - 11'-6" GWB band 125.07, Cafe 103 - 9'-0" GWB band 50.67, Cafe Seating Area 102 - GWB cloud 573.69, Cafe 103 - 11'-0" GWB zone 109.65, Grab & Go 25.16) + VEST-GWB 105.5 + SS-GG-BOTTOM-GWB 3.73 + VEST-GWB-BANDS 14.96 + CLOUD-FASCIA-GWB 53.6; Type X W.R. 1,092.59 SF; 5/8" regular 0.
RFI-28 | CLOSED - estimator decision 2026-10-27: Moment clip at every stud of types 3 / 4. N/SHEET: A/A-410; 3/A-410; 4/A-410. | Applied: + 162 moment clips, + 324 Kwik HUS-EZ 1/4" x 1-5/8", + 324 #10-16 screws.
RFI-29 | CLOSED - estimator decision 2026-10-27: Both: (a) stainless steel corner guard 48" at the corner the C22 leader points to (existing perimeter, the plan asks for it); (b) metal corner guards 2"x2"x72" at all outside corners. N/SHEET: C22/A-101; A-001A. | Applied: stainless 48" = 1; metal 2"x2"x72" = 72 (C25 36, type 3 16, type 4 8, type 2 5, Cafe 7).
RFI-30 | CLOSED - estimator decision 2026-10-27: EXCLUDED: access panels by GC / tenant contractor (M-100 GN 30, E GN 12 GC installs; A-002 F/I tenant contractor); quantity not shown. N/SHEET: M-100; A-002. | Not carried (Scope Checklist ALC-17).
RFI-31 | CLOSED - estimator decision 2026-10-27: Additional head track removed: inside the door headers of RFI-09 (no double count). N/SHEET: A-500. | Applied: - 10.67 LF (now inside the 83.32 LF of RFI-09).
RFI-32 | CLOSED - estimator decision 2026-10-27: Water heater backing kept. N/SHEET: P-201. | No change: 10.67 LF 3-5/8" stud.
RFI-33 | CLOSED - estimator decision 2026-10-27: Janitor 3/4" FRT plywood kept. N/SHEET: 11/A-200. | No change: 17.0 SF.
RFI-34 | CLOSED(rev7): T.O. WD-1 at the Grab & Go header = 15'-0" (5/A-226A 11'-0" + 4'-0" WD-1; 6/A-226A 15'-0"). 3/A-221: 5/8" FRT plywood full face, 5/8" GWB over it above T.O. WD-1. | Applied: + 6.167 x 10.0 = 61.67 SF 5/8" Type X (15'-0" to deck); FRT plywood unchanged (110.49 SF).
RFI-35 | CLOSED - estimator decision 2026-10-27: Fire stop track at ceiling line kept. N/SHEET: 3/A-410 (TYP.). | No change: 264.21 LF.
RFI-36 | CLOSED - estimator decision 2026-10-27: EXCLUDED: W-3 surface-mounted 3/4" FRT plywood blocking BY GC / FIXTURE INSTALLER. N/SHEET: 1/A-414; 7/A-414. | Not carried (Scope Checklist ALC-16).
RFI-37 | CLOSED - resolved from the plan (rev6): the Sales / Cafe faces of C-H1-N and C-H2a are 5/8" gypsum board only. G/A-221 draws one layer on the Sales Floor side ("5/8" GYPSUM BOARD"); C-H1-N Sales face = Sales Area 101 PAINTED GYP. BD. (A-510); C-H2a Cafe face = PT-3 painted wall around door 3 (1/A-225 finish plan, 5/A-226A Cafe Service Line Elevation); the narrow WD-1 left of the door is the type I return C-I-P.1 (already carried). images 12-14. | Applied: - 951.75 SF 5/8" FRT plywood (C-H1-N A 25.90 x 25.0 = 647.50 + C-H2a B 12.17 x 25.0 = 304.25), carried since rev0; GWB on those faces unchanged.
RFI-38 | CLOSED - estimator decision 2026-10-27: Seismic bracing per 5/A-121 kept (the plan governs). N/SHEET: 5/A-121. | No change: splay wires 743.29 LF + 16 ga wire 131.42 LF.
RFI-39 | CLOSED - estimator decision 2026-10-27: FE cabinet FRT 2x kept (covers the 12-13/16" fire-rated R.O. of JL 1017F10). N/SHEET: 4/A-101. | No change: 16.0 LF.
RFI-40 | CLOSED - estimator decision 2026-10-27: Nested inner runner kept. N/SHEET: 3/A-410. | No change: 479.85 LF.
RFI-41 | CLOSED - estimator decision 2026-10-27: Joists at 5'-0". N/SHEET: 8/A-410; A-400A; A-400B. | No change: cross members 705.0 LF; #8 screws 775 (2 per cross member, verified by the independent review); the 2-per-wall-stud reading (+ 98) stays as a note.
RFI-42 | CLOSED - estimator decision 2026-10-27: Soffit cross bracing kept (2/A-221 "as req'd", conservative). N/SHEET: 2/A-221. | No change: 90.0 LF.
RFI-43 | CLOSED - estimator decision 2026-10-27: E1 cement board to 12'-0" (TL-4 / WD-1 to 11'-6" on 4/A-226A + 6"; 11'-6" at C-E1-B). N/SHEET: E/A-221; 4/A-226A; 1/A-121. | Applied: 1/2" cement board - 305.62 SF (C-E1-S 19.0 x 13.0 + C-E1-P.2 2.11 x 13.0 + C-E1-B 2.31 x 13.5).
RFI-44 | CLOSED - estimator decision 2026-10-27: T.O. WD-1 on the H3a Sales face = 15'-0" (precedent 6/A-226A). N/SHEET: H/A-221; 6/A-226A. | Applied: 5/8" FRT plywood - 40.8 SF; 5/8" Type X + 40.8 SF (4.08 x 10.0).
RFI-45 | CLOSED - estimator decision 2026-10-27: Kept (conservative). N/SHEET: G/A-221. | No change: 66.7 SF on C-H2a.
RFI-46 | CLOSED - estimator decision 2026-10-27: Kept (estimator decision 2026-10-26). N/SHEET: F/A-221; 3/A-410; 4/A-410. | No change: 6.52 + 122.32 LF.
RFI-47 | CLOSED - estimator decision 2026-10-27: FRT (A-410 building dept note: all plywood FRT); thickness per the A-221 sections (5/8", conservative). N/SHEET: A-410; A-221. | No change.
RFI-48 | CLOSED - estimator decision 2026-10-27: In-partition FRT 2x, 3 rows kept (conservative + FRT note). N/SHEET: 7/A-413. | No change: 387 LF.
RFI-49 | CLOSED - estimator decision 2026-10-27: Resolved on the plan: 0 cased openings (A-500 schedule / types; no 2/A-500 bubble on any sheet). "2/A-500 detail not referenced on any plan". N/SHEET: 2/A-500; A-500. | Applied: 2x wood blocking - 17.0 LF.
RFI-50 | CLOSED - estimator decision 2026-10-27: EXCLUDED: server room 4'x8' FRT plywood BY GC. N/SHEET: 2/E-103; E-301. | Applied: 3/4" FRT plywood - 32.0 SF (Scope Checklist ALC-10).
RFI-52 | CLOSED - estimator decision 2026-10-27: Kept (11'-3 1/2" printed). N/SHEET: 2/A-210; 3/A-210. | No change: 14.96 SF.
RFI-53 | CLOSED - estimator decision 2026-10-27: Fixture hanger wire kept. N/SHEET: 5/A-121. | No change: 401.0 LF.
RFI-51 | CLOSED - estimator decision 2026-10-27: Kept as carried + diagonal brace end screws 2 per end (manufacturer rule where the plan prints none); 8/A-210 read as 8 per station @ 16" O.C. N/SHEET: 3/A-410; 7/A-210; 8/A-210. | Applied: + 512 #8 screws at brace ends (128 braces x 2 ends x 2); 520 Tek screws at 8/A-210 kept.
RFI-54 | CLOSED - estimator decision 2026-10-27: Perimeter track kept (conservative); 8" ledger = 16 ga like the 8/A-210 nested members. N/SHEET: 5/A-121; 4/A-210; 8/A-210. | No change in LF.
RFI-55 | CLOSED - estimator decision 2026-10-28: PVC trim and FRP per the targeted review (real corners and edges; division bars every 4'; hourglass cap corners take the metal corner guard, not PVC; Work Room FRP at finished dimensions; FRP-1 below the Cafe countertop). N/SHEET: 3/A-225; 4/A-225; 1/A-225; 6/A-225; 1/A-221; 9-12/A-200; A-001A. | Applied: PVC trim + division bars 530.54 -> 887.62 LF (trim 524.62 + division bars 363.0); FRP 1,967.38 -> 2,001.38 SF (Work Room - 23.0, Cafe below countertop + 57.0).

## Review Items
0 questions in total, asked ONE at a time in this order: floor plan (partition types A-Z), then the details the floor plan calls, in order
# | Phase | Type / order | Item | Sheet + detail | Image

## Scope Checklist
Scope ID | Scope | Status | Note (quantity, NOT APPLICABLE + sheet, or RFI)
ALC-01 | Interior partition framing (studs + tracks) | QUANTIFIED | Quantified (rev1): partition types 2, 5, 3, 4 (A-410) and Cafe types H1, H2a, H2b, H3a, H3b, E2, E1, F, I, A, B, D, C (A-221) on A-101 / A-221; 3-5/8" and 6" stud families in Material Summary. Perimeter types 1 / 1A / 1B / 1C EXISTING - EXCLUDED (RFI-01).
ALC-02 | Exterior wall framing (CFMF) | NOT APPLICABLE | NOT APPLICABLE (rev1, estimator decision RFI-01): perimeter walls types 1 / 1A / 1B / 1C are existing; their interior board is labeled "5/8" GYP BD BY FUTURE TENANT" on 1, 1A, 1B, 1C/A-410 - EXCLUDED with that citation.
ALC-03 | Parapet framing | NOT APPLICABLE | NOT APPLICABLE: no parapet framing in scope - partition schedule A-410 and sections A-400A, A-400B show no parapet type; M-301 (p50) mention is a mechanical roof-edge note
ALC-04 | Top / deflection and bottom track | QUANTIFIED | Bottom track and top / deflection track = partition LF per type (A-101, A-221; 2/A-410, 3/A-410); + fire stop track at ceiling line (own rows by size, 3/A-410) (3/A-410, RFI-35) and additional head track 83.32 LF (RFI-31); M-302 (p51) mention is plumbing expansion fittings; nested inner runner at deflection heads (3/A-410, RFI-40); 8/A-410 #8 pan head screws + P.A.F. + #8 screws (own rows); X-EDNI 8.C = alternative in RFI-51; cross members at walls parallel to joists (8/A-410 Typ. Connection, RFI-41).
ALC-05 | Headers, sills and jambs at openings | RFI | RFI-09 door headers: no header schedule in the set and 1/A-500 shows no header; jambs carried as studs; sill track not called (A-500 door schedule)
ALC-06 | Bracing / bridging | QUANTIFIED | Bracing C.R. channel @ 4'-0" O.C. per A-410 partition note 4 and 5/A-410 = 2,883.65 LF; diagonal bracing type 2 > 22'-0" per 3/A-410 Top Track Detail (RFI-04 CLOSED rev3: 117 braces = 468.0 LF) + 2" x 2" 16 ga clip angles at every stud per bracing row (5/A-410) and 2/A-221 soffit cross bracing (RFI-42).
ALC-07 | Gypsum board on walls (layers per type) | QUANTIFIED | Quantified (rev6): 5/8" Type X 14,266.95 SF + 5/8" Type X W.R. 1,092.59 SF (A-410, A-001A, RFI-27, RFI-11); no 5/8" regular. Perimeter walls existing (RFI-01).
ALC-08 | Moisture / abuse / special board at wet zones | QUANTIFIED | Quantified (rev6): 5/8" Type X W.R. 1,092.59 SF = all faces of Women's 109, Men's 108, Janitor 107 and drinking fountain alcove corridor faces (A-410 Partition Notes 2 and 7, '*' note, 2/A-410, 5/A-410) + restroom GWB ceilings 122.30 SF (A-410 Partition Notes 2); Cafe Work Room 104 = FRT plywood + FRP-1, no gypsum (G/A-221, A-510); existing EXT-07 faces = patch allowance.
ALC-09 | Exterior gypsum / glass mat sheathing | NOT APPLICABLE | NOT APPLICABLE (rev1): the only sheathing in the set is 1/2 in exterior gyp sheathing of type 1B (1B/A-410), an EXISTING perimeter wall - EXCLUDED (RFI-01, 1/DM-101, A-002); M-301 (p50) 'plastic sheathing' is temporary protection.
ALC-10 | FRT plywood sheathing / substrate | QUANTIFIED | FRT plywood 5/8" 2,686.45 SF (Cafe types G, H, E2, F, I and Grab & Go soffit 3/A-221; soffit faces 2/A-221) + 3/4" 370.46 SF (counters A/B, menu boards 4/A-226A, restroom backing 21/A-201, vestibule 4/A-210, 5/A-210, janitor 11/A-200) - breakdown in Material Summary EXCLUDED (estimator decision 2026-10-27, RFI-50): server room 4'x8' FRT plywood BY GC (2/E-103). Types 3 / 4 one face 5/8" FRT plywood + FRP added (RFI-22).
ALC-11 | Gypsum board ceilings | QUANTIFIED | Quantified (rev7): suspended GWB ceilings and soffits per A-121 (5/A-121, 4/A-121) and 2/A-221 = 1,006.54 SF (incl. Grab & Go 7'-1" 25.16 SF): 5/8" Type X + restroom ceilings 5/8" Type X W.R. (A-410 Partition Notes 2).
ALC-12 | Ceiling suspension (furring / carrying channel / hanger wire / ceiling track) | QUANTIFIED | Furring channel @ 24", carrying channel @ 48", hanger wire 109 pcs at 48" + 29 at light fixtures, ceiling track per 5/A-121 on A-121; carrying direction E-W (RFI-15 CLOSED rev3: joists N-S on 1/A-400A, 2/A-400A); Cafe Seating cloud = USG drywall suspension grid 4/A-121; M-100 (p46), M-101 (p47), M-102 (p48) hangers are MEP; Grab & Go GWB ceiling 7'-1" added; additional hangers at light fixtures and seismic splay wires per 5/A-121 (RFI-38); 16 ga tie wire (5/A-121) = consumable of the furring / carrying install, no separate row.
ALC-13 | Soffits and bulkheads (framing + board) | QUANTIFIED | Quantified: framed soffit 2/A-221 (SS-N, SS-E, SS-IN-N, SS-IN-E) and Grab & Go header soffit 3/A-221 (SS-GG, RFI-20 CLOSED rev5; T.O. WD-1 RFI-34); E-102 (p36) bulkhead is signage (by others)
ALC-14 | Canopy / marquee framing and sheathing | NOT APPLICABLE | NOT APPLICABLE: E-102 (p36) 'MOUNT WITHIN CANOPY BULKHEAD' is an electrical sign note at the existing canopy; no canopy framing on A-101, A-121, A-210
ALC-15 | Column furring / wraps | QUANTIFIED | Column wraps C25 x 9 on A-101, studs @ 16" O.C. (RFI-17 CLOSED rev4), carried under OTHER FRAMING
ALC-16 | Blocking (FRT wood / metal) for millwork and accessories | QUANTIFIED | Quantified (rev1, RFI-23): FRT blocking 568.27 LF (7/A-413 387.0, 8A/A-413 69.0, 3-4/A-412 85.6, 6/A-412 10.67, 4/A-101 FE cabinets 16.0) + 3/4" FRT plywood menu boards 60.61 SF (4/A-226A) + restroom backing 17.78 SF (21/A-201) + janitor 17.0 SF (11/A-200, RFI-33); water heater backing P-201 10.67 LF 3-5/8" stud (RFI-32); W-3 surface blocking 1/A-414 RFI-36. EXCLUDED (estimator decision 2026-10-27, RFI-36): W-3 surface-mounted 3/4" FRT plywood blocking BY GC / FIXTURE INSTALLER (1/A-414, 7/A-414). 2/A-500 cased opening blocking removed: 0 cased openings (RFI-49).
ALC-17 | Framed openings (MEP, access panels, diffusers) | QUANTIFIED | QUANTIFIED: stud reinforcement plates 10 + duct sleeves 8 (M-102 count, estimator decision 2026-10-27). Access panels EXCLUDED (estimator decision 2026-10-27, RFI-30): access panels by GC / tenant contractor (M-100 GN 30, E GN 12 GC installs; A-002 F/I tenant contractor); quantity not shown. recessed FE cabinets framed per 4/A-101 (FRT header + base, RFI-39); no framed MEP opening drawn in GWB walls (A-121, M-102, P-101A).
ALC-18 | Trim: corner bead, casing bead, control joints, reveals | QUANTIFIED | Metal trim (corner bead, J-bead) per A-410, A-121, A-510 Finish Notes 8 (incl. soffit bottom edges 65.31 LF); control joints not printed - carried per ASTM C840 (estimator decision 2026-10-27, RFI-24). Control joints 250.0 LF (ASTM C840, RFI-24); corner guards metal 2"x2"x72" 72 + stainless 48" 1 (RFI-29).
ALC-19 | Acoustical sealant / sound attenuation (EXCLUDED: estimator standing order, all projects) | NOT APPLICABLE | EXCLUDED: EXCLUDED in all projects (estimator standing order): no acoustical sealant row and no quantity
ALC-20 | FRP / cement board / tile backer | QUANTIFIED | QUANTIFIED (estimator decision 2026-10-27): FRP-1 Cafe Work Room + Janitor (RFI-13) and one face of types 3 / 4 (RFI-22) + PVC trim; cement board E1 to 12'-0" (RFI-43). Cement board at wet walls (A-510 tile finishes, RFI-12 incl. Corridor 110 wall tile); FRP-1 extent RFI-13 / RFI-22 not carried
ALC-21 | Shaft walls / area separation walls | NOT APPLICABLE | NOT APPLICABLE: no shaft wall / area separation wall in partition schedule A-410 or plan A-101
ALC-22 | Rated assemblies (UL designs) and their board type | NOT APPLICABLE | NOT APPLICABLE: all partition types are Non-Rated per A-410 titles (2/A-410, 3/A-410, 4/A-410, 5/A-410); E-201 (p40), E-202 (p42), E-301 (p44), M-100 (p46) mentions are generic penetration notes
ALC-23 | Special panels (ballistic, lead-lined, abuse) | NOT APPLICABLE | NOT APPLICABLE: no ballistic, lead-lined or abuse panels in A-410 schedule or A-510 finish schedule
ALC-24 | Finish level (Level 4 / Level 5) | QUANTIFIED | QUANTIFIED: Level 4 finish printed - A-001A Div 09 A.8 "PROVIDE AT A MINIMUM A LEVEL 4 FINISH" (joint compound / tape yields per Inputs); no Level 5 (A-510).
ALC-X40 | Acoustical lay-in ceilings ACT-1 / ACT-3 (tile + Prelude XL grid + wires) | NOT APPLICABLE | EXCLUDED: Div 09 51 acoustical ceilings by the ACT contractor - A-002 lists "ACOUSTICAL CEILING SYSTEM" as its own line (F/I tenant contractor); ACT-1 Cafe Workroom 10'-0", ACT-3 Corridor, Break Room, Manager's Office 9'-0" (1/A-121, A-510 finish legend); ACT portion of 5/A-121. Wall board heights use these ceilings + 6".
ALC-X41 | Unistrut space frame / strut channel | NOT APPLICABLE | EXCLUDED: A-001A Div 05 D "UNISTRUT SPACE FRAME GRID SYSTEM ... AS REQUIRED FOR LIGHTING, CEILING ACCESSORIES OR MECHANICAL SYSTEMS SUSPENSION" and A-002 cafe signage "STRUT CHANNEL" = lighting / sign / MEP supports by those trades; the sign blocking is carried (4/A-226A menu boards).
ALC-X42 | Caulk at the base of wet-area walls | NOT APPLICABLE | EXCLUDED: A-101 general note 8 "BOTTOM OF THE WALL CAULKED AT FLOOR LEVEL" = joint sealant (Div 07), excluded like all sealants (estimator standing order).
ALC-X43 | Partition seismic bracing (A-002 Div 10) | NOT APPLICABLE | EXCLUDED as a separate item: A-002 Div 10 "SEISMIC BRACING" is listed with the specialties; partition lateral bracing is carried per 5/A-410 and 3/A-410; ceiling bracing per 5/A-121 carried under RFI-38.
ALC-X44 | Remove & replace existing GWB for shelving blocking (7/A-413) | RFI | Inside the RFI-01 patch & repair allowance (existing perimeter walls): A-413 general note "G.C. IS TO REMOVE AND REPLACE GYP. BOARD AS REQUIRED FOR INSTALLATION OF WOOD BLOCKING".
ALC-X30 | batt insulation | NOT APPLICABLE | EXCLUDED (estimator criterion: no insulation)

## _reglas (hidden)
reglas.py compuerta OK
{"canon": "30328baae8a109373483e25954cb34b9d553393b9a6064bfc8f8b3a24584bd94", "evidencias": "82f4ec13c901d7191f9772989e98854d158340ab19499f6cfbada96ca6cbd21e", "familias_out": "efd452b69a59a44adaa0688741a3a30591b17914b1817021a5318c284e429a7e", "reglas": "72bf0be21e40184db31d6df02ebb10ea5608c6ccc6004bdc86763c869879d378", "version": "v73"}