## Takeoff
Wall # | Partition / Scope | Location | Length (LF) | Stud Height (FT) | Layers (total both faces) | 6" Metal Stud (LF) | 3-5/8" Metal Stud (LF) | 1-5/8" Metal Stud (LF) | Stud designation | O.C. (in) | Stud pcs | Side 1 room | Side 1 board height (FT) | Side 1 layers | Side 2 room | Side 2 board height (FT) | Side 2 layers | Openings deduction (SF per face) | 5/8" Gyp Board (SF) | 3/8" Gyp Board (SF) | 3/8" UL752 Fiberglass (SF) | 3/4" FRT Plywood (SF) | FRP-1 (SF) | FRP-2 (SF) | Durock (SF) | Demolition (SF) | Bottom Track (LF) | Top Track (LF) | Top track condition | Bracing C.R. channel (LF) | Clips (ea) | Header (LF) | Insulation (SF) | Acoustical sealant (LF) | Blocking | Labor (Hrs) | Status | Detail sequence (plan -> detail -> schedule) | Seal
8 | A1 - 3-5/8" MST @ 16" O.C. (362S137-33) - board per face, see Side 1 / Side 2 (1 instance) | Corridor 111 east / Break Room 118, Electrical 120, NER 121 west | 20.93 | 13.052 | 2 |  | 304.8 |  | 362S137-33 | 16 | 25 | Corridor 111 | 9 | 1 | Break Room 118 | 9 | 1 | 23.89 | 399.48 | [7 empty] | 20.93 | 20.93 | CONTINUOUS SLIP TRACK per 3/A12.01 | 62.79 | 150 | 4.33 | 249.25 | 41.86 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tags A1 @1213,1406 and @1220,1515) -> 3/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling -> A00.30 HEAD 10/A12.02, JAMB 11/A12.02 | d67b0b4d817598c1
1 | A1 - 3-5/8" MST @ 16" O.C. (362S137-33) - board per face, see Side 1 / Side 2 (1 instance) | Calling Cubes 122 north / Waiting 104 | 17.02 | 15.375 | 2 |  | 230.63 |  | 362S137-33 | 16 | 15 | Calling Cubes 122 | 9 | 1 | Waiting 104 | 11.5 | 1 | 0 | 348.91 | [7 empty] | 17.02 | 17.02 | CONTINUOUS SLIP TRACK per 3/A12.01 | 51.06 | 90 |  | 261.68 | 34.04 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag A1 @1382,996) -> 3/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | c0fa7673fe7ef80d
5 | A1 - 3-5/8" MST @ 16" O.C. (362S137-33) - board per face, see Side 1 / Side 2 (1 instance) | Calling Cubes 122 south / Break Room 118 | 15.23 | 13.052 | 2 |  | 182.73 |  | 362S137-33 | 16 | 14 | Calling Cubes 122 | 9 | 1 | Break Room 118 | 9 | 1 | 0 | 274.14 | [7 empty] | 15.23 | 15.23 | CONTINUOUS SLIP TRACK per 3/A12.01 | 45.69 | 84 |  | 198.83 | 30.46 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag A1 @1376,1297) -> 3/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | 34d325ae99bba374
9 | A1 - 3-5/8" MST @ 16" O.C. (362S137-33) - board per face, see Side 1 / Side 2 (1 instance) | Work Room 119 north / Cash Window 116 & Break Room | 11.67 | 13.052 | 2 |  | 213.43 |  | 362S137-33 | 16 | 18 | Work Room 119 | 9 | 1 | Cash Window 116 | 9.5 | 1 | 23.89 | 168.115 | [7 empty] | 11.67 | 11.67 | CONTINUOUS SLIP TRACK per 3/A12.01 | 35.01 | 108 | 4.33 | 128.39 | 23.34 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag A1 @1740,1472) -> 3/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling -> A00.30 HEAD 10/A12.02, JAMB 11/A12.02 | 1a56c960b1d3effc
4 | A1 - 3-5/8" MST @ 16" O.C. (362S137-33) - board per face, see Side 1 / Side 2 (1 instance) | Corridor 111 north (door 111) | 5.59 | 15.375 | 2 |  | 190.75 |  | 362S137-33 | 16 | 14 | Corridor 111 | 9 | 1 | Central Zone 103 | 12 | 1 | 27.22 | 62.95 | [7 empty] | 5.59 | 5.59 | CONTINUOUS SLIP TRACK per 3/A12.01 | 16.77 | 84 | 4.33 | 58.67 | 11.18 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag A1 @1147,1254) -> 3/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling -> A00.30 HEAD 10/A12.02, JAMB 11/A12.02 | 56e6e995594b5b5c
2 | A1 - 3-5/8" MST @ 16" O.C. (362S137-33) - board per face, see Side 1 / Side 2 (1 instance) | MW01 alcove east (Calling Cubes 122) | 3.13 | 15.375 | 2 |  | 76.88 |  | 362S137-33 | 16 | 5 | Calling Cubes 122 | 9 | 1 | MW01 alcove | 9 | 1 | 0 | 56.34 | [7 empty] | 3.13 | 3.13 | CONTINUOUS SLIP TRACK per 3/A12.01 | 9.39 | 30 |  | 48.07 | 6.26 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag A1 @1299,1000) -> 3/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | a434297db62f6466
3 | A1 - 3-5/8" MST @ 16" O.C. (362S137-33) - board per face, see Side 1 / Side 2 (1 instance) | MW01 alcove south (Calling Cubes 122) | 2.02 | 15.375 | 2 |  | 61.5 |  | 362S137-33 | 16 | 4 | Calling Cubes 122 | 9 | 1 | MW01 alcove | 9 | 1 | 0 | 36.36 | [7 empty] | 2.02 | 2.02 | CONTINUOUS SLIP TRACK per 3/A12.01 | 6.06 | 24 |  | 31.06 | 4.04 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag A1 @1246,1063) -> 3/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | e21a491f82924ae8
6 | A1 - 3-5/8" MST @ 16" O.C. (362S137-33) - board per face, see Side 1 / Side 2 (1 instance) | jog SE of Calling Cubes 122 (vertical) | 1.73 | 13.052 | 2 |  | 52.21 |  | 362S137-33 | 16 | 4 | Break Room 118 | 9 | 1 | Central Zone 103 | 9.5 | 1 | 0 | 32.005 | [7 empty] | 1.73 | 1.73 | CONTINUOUS SLIP TRACK per 3/A12.01 | 5.19 | 24 |  | 22.62 | 3.46 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag A1 @1508,1343) -> 3/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | e58a73e29e60d087
7 | A1 - 3-5/8" MST @ 16" O.C. (362S137-33) - board per face, see Side 1 / Side 2 (1 instance) | jog SE of Calling Cubes 122 (horizontal) | 1.3 | 13.052 | 2 |  | 39.16 |  | 362S137-33 | 16 | 3 | Break Room 118 | 9 | 1 | Central Zone 103 | 9.5 | 1 | 0 | 24.05 | [7 empty] | 1.3 | 1.3 | CONTINUOUS SLIP TRACK per 3/A12.01 | 3.9 | 18 |  | 16.97 | 2.6 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag A1 @1540,1335) -> 3/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | fc92c8164bc5f2ef
10 | A1K - 3-5/8" 14 GA MST @ 24" O.C. (362S137-68) - board per face, see Side 1 / Side 2 (1 instance) | Teller line west (Cash Window 116 / customer side) | 12.01 | 15.375 | 2 |  | 131.41 |  | 362S137-68 | 24 | 9 | Cash Window 116 (teller side) | 15.375 | 1 | Central Zone 103 (customer side) | 15.375 | 1 | 0 | 344.04 | 88.57 | 96.08 | [5 empty] | 12.01 | 12.01 | CONTINUOUS SLIP TRACK per 4/A12.01 | 36.03 | 54 |  | 172.02 | 48.04 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tags A1K @1659,1150 and @1662,1332) -> 4/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | d49b7c0ce1434ab5
13 | A1K - 3-5/8" 14 GA MST @ 24" O.C. (362S137-68) - board per face, see Side 1 / Side 2 (1 instance) | Future FCAM north | 5.65 | 13.052 | 2 |  | 65.26 |  | 362S137-68 | 24 | 5 | Future FCAM | 13.052 | 1 | Central Zone 103 | 13.052 | 1 | 0 | 147.4876 | 28.54 | 45.2 | [5 empty] | 5.65 | 5.65 | CONTINUOUS SLIP TRACK per 4/A12.01 | 16.95 | 30 |  | 73.79 | 22.6 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag A1K @1644,1335) -> 4/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | c32dac1b6b7f6a0e
11 | A1K - 3-5/8" 14 GA MST @ 24" O.C. (362S137-68) - board per face, see Side 1 / Side 2 (1 instance) | Teller line north cap | 2.98 | 15.375 | 2 |  | 61.5 |  | 362S137-68 | 24 | 4 | Cash Window 116 | 15.375 | 1 | Office 108 side | 15.375 | 1 | 0 | 91.635 | 21.98 | 23.84 | [5 empty] | 2.98 | 2.98 | CONTINUOUS SLIP TRACK per 4/A12.01 | 8.94 | 24 |  | 45.82 | 11.92 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (hatch KEVLAR legend A02.01 (no own tag)) -> 4/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | b8f5af71bcddbc9c
12 | A1K - 3-5/8" 14 GA MST @ 24" O.C. (362S137-68) - board per face, see Side 1 / Side 2 (1 instance) | Teller line south cap | 2.98 | 13.052 | 2 |  | 52.21 |  | 362S137-68 | 24 | 4 | Cash Window 116 | 13.052 | 1 | Future FCAM | 13.052 | 1 | 0 | 77.7899 | 15.05 | 23.84 | [5 empty] | 2.98 | 2.98 | CONTINUOUS SLIP TRACK per 4/A12.01 | 8.94 | 24 |  | 38.89 | 11.92 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (hatch KEVLAR legend A02.01 (no own tag)) -> 4/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | 3e5fa2f93e7f3207
15 | A5 - 6" MST @ 16" O.C. (600S137-33) - board per face, see Side 1 / Side 2 (1 instance) | Calling Cubes 122 east / Central Zone 103 | 19.41 | 15.375 | 2 | 267.46 |  |  | 600S137-33 | 16 | 18 | Calling Cubes 122 | 9 | 1 | Central Zone 103 | 9.5 | 1 | 0 | 359.09 | [7 empty] | 19.41 | 19.41 | CONTINUOUS SLIP TRACK per 3/A12.01 | 58.23 | 108 |  | 288.35 | 38.82 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag A5 @1543,1118) -> 3/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | 1573b37c962264a2
14 | A5 - 6" MST @ 16" O.C. (600S137-33) - board per face, see Side 1 / Side 2 (1 instance) | Calling Cubes 122 west / Central Zone & Corridor 111 (door 122) | 19 | 15.375 | 2 | 340.53 |  |  | 600S137-33 | 16 | 24 | Calling Cubes 122 | 9 | 1 | Central Zone 103 / Corridor 111 | 12 | 1 | 23.89 | 351.22 | [7 empty] | 19 | 19 | CONTINUOUS SLIP TRACK per 3/A12.01 | 57 | 144 | 4.33 | 259.16 | 38 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tags A5 @1209,1129 and @1264,1240) -> 3/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling -> A00.30 HEAD 10/A12.02, JAMB 11/A12.02 | 449509c616dd77f5
16 | A5 - 6" MST @ 16" O.C. (600S137-33) - board per face, see Side 1 / Side 2 (1 instance) | Future FCAM west / Break Room 118 | 3.71 | 13.052 | 2 | 65.26 |  |  | 600S137-33 | 16 | 5 | Future FCAM | 9.5 | 1 | Break Room 118 | 9 | 1 | 0 | 68.635 | [7 empty] | 3.71 | 3.71 | CONTINUOUS SLIP TRACK per 3/A12.01 | 11.13 | 30 |  | 48.47 | 7.42 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag A5 @1650,1410) -> 3/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | fb8ae23bcf90dd29
19 | B - 3-5/8" MST @ 16" O.C. (362S137-33) - board per face, see Side 1 / Side 2 (1 instance) | Electrical 120 & NER 121 east / Break Room 118 | 14.15 | 13.052 | 2 |  | 309.4 |  | 362S137-33 | 16 | 27 | Electrical 120 / NER 121 | 13.052 | 1 | Break Room 118 | 13.052 | 1 | 47.78 | 273.8116 | [7 empty] | 14.15 | 14.15 | CONTINUOUS SLIP TRACK per 1/A12.01 | 42.45 | 162 | 8.67 | 136.87 | 56.6 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag B @1400,1584) -> 1/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling -> A00.30 HEAD 10/A12.02, JAMB 11/A12.02 | 2381d0116a0ab104
22 | B - 3-5/8" MST @ 16" O.C. (362S137-33) - board per face, see Side 1 / Side 2 (1 instance) | Janitor Closet 112 & Storage 117 / Wellness 115 | 11.73 | 13.052 | 2 |  | 143.57 |  | 362S137-33 | 16 | 11 | Janitor Closet 112 / Storage 117 | 13.052 | 1 | Wellness 115 | 13.052 | 1 | 0 | 306.1999 | [7 empty] | 11.73 | 11.73 | CONTINUOUS SLIP TRACK per 1/A12.01 | 35.19 | 66 |  | 153.14 | 46.92 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tags B @944,1567 and @1101,1607) -> 1/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | 3f44e25de778249d
20 | B - 3-5/8" MST @ 16" O.C. (362S137-33) - board per face, see Side 1 / Side 2 (1 instance) | Mens Restroom 113 south / Janitor Closet 112 & Storage 117 north | 11.73 | 13.052 | 2 |  | 213.43 |  | 362S137-33 | 16 | 18 | Mens Restroom 113 | 13.052 | 1 | Janitor Closet 112 / Storage 117 | 13.052 | 1 | 23.89 | 258.4199 | [7 empty] | 11.73 | 11.73 | CONTINUOUS SLIP TRACK per 1/A12.01 | 35.19 | 108 | 4.33 | 129.26 | 46.92 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag B @1052,1497) -> 1/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling -> A00.30 HEAD 10/A12.02, JAMB 11/A12.02 | 90cb13724e02a18e
17 | B - 3-5/8" MST @ 16" O.C. (362S137-33) - board per face, see Side 1 / Side 2 (1 instance) | Electrical 120 north / Break Room 118 | 9.58 | 13.052 | 2 |  | 130.52 |  | 362S137-33 | 16 | 10 | Electrical 120 | 13.052 | 1 | Break Room 118 | 13.052 | 1 | 0 | 250.0763 | [7 empty] | 9.58 | 9.58 | CONTINUOUS SLIP TRACK per 1/A12.01 | 28.74 | 60 |  | 125.04 | 38.32 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag B @1380,1457) -> 1/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | 5d100aa0ef19de8d
18 | B - 3-5/8" MST @ 16" O.C. (362S137-33) - board per face, see Side 1 / Side 2 (1 instance) | Electrical 120 / NER 121 | 9.58 | 13.052 | 2 |  | 130.52 |  | 362S137-33 | 16 | 10 | Electrical 120 | 13.052 | 1 | NER 121 | 13.052 | 1 | 0 | 250.0763 | [7 empty] | 9.58 | 9.58 | CONTINUOUS SLIP TRACK per 1/A12.01 | 28.74 | 60 |  | 125.04 | 38.32 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag B @1383,1572) -> 1/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | 0da09bcddeb876a5
21 | B - 3-5/8" MST @ 16" O.C. (362S137-33) - board per face, see Side 1 / Side 2 (1 instance) | Janitor Closet 112 / Storage 117 | 3.5 | 13.052 | 2 |  | 65.26 |  | 362S137-33 | 16 | 5 | Janitor Closet 112 | 13.052 | 1 | Storage 117 | 13.052 | 1 | 0 | 91.364 | [7 empty] | 3.5 | 3.5 | CONTINUOUS SLIP TRACK per 1/A12.01 | 10.5 | 30 |  | 45.68 | 14 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag B @1048,1532) -> 1/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | a3d71077804295b1
23 | B2 - 6" MST @ 16" O.C. (600S137-33) - board per face, see Side 1 / Side 2 (1 instance) | Corridor 111 west / Restrooms 114 & 113, Storage 117, Wellness 115 east (incl. drinking fountain alcove) | 29.19 | 15.375 | 2 | 677.77 |  |  | 600S137-33 | 16 | 53 | Corridor 111 | 15.375 | 1 | Restrooms / Storage / Wellness | 15.375 | 1 | 95.55 | 573.56 | [7 empty] | 29.19 | 29.19 | CONTINUOUS SLIP TRACK per 1/A12.01 | 87.57 | 318 | 17.33 | 286.78 | 116.76 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tags B2 @1146,1314 @1154,1438 @1152,1597) -> 1/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling -> A00.30 HEAD 10/A12.02, JAMB 11/A12.02 | 458761b4503a992b
25 | B2 - 6" MST @ 16" O.C. (600S137-33) - board per face, see Side 1 / Side 2 (1 instance) | Break Room 118 / Work Room 119 (door 116) | 15.07 | 13.052 | 2 | 252.59 |  |  | 600S137-33 | 16 | 21 | Break Room 118 | 13.052 | 1 | Work Room 119 / FCAM | 13.052 | 1 | 23.89 | 345.6073 | [7 empty] | 15.07 | 15.07 | CONTINUOUS SLIP TRACK per 1/A12.01 | 45.21 | 126 | 4.33 | 172.85 | 60.28 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tags B2 @1603,1493 and @1652,1622) -> 1/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling -> A00.30 HEAD 10/A12.02, JAMB 11/A12.02 | cb2d3f1223928700
24 | B2 - 6" MST @ 16" O.C. (600S137-33) - board per face, see Side 1 / Side 2 (1 instance) | ATM Room 102 east / 24 HR Vestibule & Central Zone (door 102) | 6.64 | 15.375 | 2 | 190.75 |  |  | 600S137-33 | 16 | 14 | ATM Room 102 | 15.375 | 1 | Central Zone 103 | 15.375 | 1 | 31.3 | 141.58 | [7 empty] | 6.64 | 6.64 | CONTINUOUS SLIP TRACK per 1/A12.01 | 19.92 | 84 | 4.83 | 70.77 | 26.56 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag B2 @1110,746) -> 1/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling -> A00.30 HEAD 10/A12.02, JAMB 11/A12.02 | 60a2d1639746e592
26 | B2K - 6" 14 GA MST @ 24" O.C. (600S137-68) - board per face, see Side 1 / Side 2 (1 instance) | Teller line NW corner (Office 108 / Cash Window) | 2.21 | 15.375 | 2 | 61.5 |  |  | 600S137-68 | 24 | 4 | Office 108 side | 15.375 | 1 | Cash Window 116 | 15.375 | 1 | 0 | 67.9575 | 16.3 | 17.68 | [5 empty] | 2.21 | 2.21 | CONTINUOUS SLIP TRACK per 4/A12.01 | 6.63 | 24 |  | 33.93 | 8.84 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag B2K @1637,1136) -> 4/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | d1261f240244c6f3
28 | C1 - 3-5/8" furring MST @ 16" O.C. (362S137-33) - board per face, see Side 1 / Side 2 (1 instance) | Plumbing chase - Mens Restroom 113 face | 10.03 | 13.052 | 1 |  | 130.52 |  | 362S137-33 | 16 | 10 | Mens Restroom 113 | 9 | 1 |  |  |  | 0 | 90.27 | [7 empty] | 10.03 | 10.03 | CONTINUOUS SLIP TRACK per 6/A12.01 | 30.09 | 60 |  | 130.9 | 20.06 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag C1 @1004,1400) -> 6/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | a26e1d399994acda
27 | C1 - 3-5/8" furring MST @ 16" O.C. (362S137-33) - board per face, see Side 1 / Side 2 (1 instance) | Plumbing chase - Womens Restroom 114 face | 10.03 | 13.052 | 1 |  | 130.52 |  | 362S137-33 | 16 | 10 | Womens Restroom 114 | 9 | 1 |  |  |  | 0 | 90.27 | [7 empty] | 10.03 | 10.03 | CONTINUOUS SLIP TRACK per 6/A12.01 | 30.09 | 60 |  | 130.9 | 20.06 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag C1 @1005,1342) -> 6/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | 840b092a020d88ff
29 | C1 - 3-5/8" furring MST @ 16" O.C. (362S137-33) - board per face, see Side 1 / Side 2 (1 instance) | Display monitor furring - Waiting 104 face of wall 1 (keynote 7) | 9.29 | 15.375 | 1 |  | 138.38 |  | 362S137-33 | 16 | 9 | Waiting 104 | 11.5 | 1 |  |  |  | 0 | 106.835 | [7 empty] | 9.29 | 9.29 | CONTINUOUS SLIP TRACK per 6/A12.01 | 27.87 | 54 |  | 142.89 | 18.58 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag C1 @1304,943) -> 6/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | b32b408f4cb23acc
30 | F - 3-5/8" MST @ 16" O.C. (362S137-33) - board per face, see Side 1 / Side 2 (1 instance) | ATM wall (inclined 30 deg) 24 HR Vestibule 101 / ATM Room 102 | 16.92 | 15.375 | 2 |  | 317.5 |  | 362S137-33 | 16 | 23 | 24 HR Vestibule 101 | 10 | 1 | ATM Room 102 | 9 | 1 | 6.05 | 309.38 |  |  | 260.15 |  |  |  |  | 16.92 | 16.92 | CONTINUOUS SLIP TRACK per 12/A12.01 | 50.76 | 138 | 3.25 | 260.15 | 33.84 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag F @1073,672) -> 12/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling -> A00.30 HEAD 10/A12.02, JAMB 11/A12.02 | 2703fea400bb2cd3
32 | G - 1-5/8" double row MST @ 16" O.C. (162S125-33 (DERIVED)) - board per face, see Side 1 / Side 2 (1 instance) | Office 107 / Office 108 | 11.77 | 15.375 | 4 |  |  | 338.25 | 162S125-33 (DERIVED) | 16 | 22 | Office 107 | 15.375 | 2 | Office 108 | 15.375 | 2 | 0 | 723.855 | [7 empty] | 23.54 | 23.54 | CONTINUOUS SLIP TRACK per 5/A12.01 | 70.62 | 132 |  | 180.91 | 47.08 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag G @1716,937) -> 5/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | 85ea94924962db6a
31 | G - 1-5/8" double row MST @ 16" O.C. (162S125-33 (DERIVED)) - board per face, see Side 1 / Side 2 (1 instance) | Office 106 / Office 107 | 11.77 | 15.375 | 4 |  |  | 338.25 | 162S125-33 (DERIVED) | 16 | 22 | Office 106 | 15.375 | 2 | Office 107 | 15.375 | 2 | 0 | 723.855 | [7 empty] | 23.54 | 23.54 | CONTINUOUS SLIP TRACK per 5/A12.01 | 70.62 | 132 |  | 180.91 | 47.08 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag G @1713,742) -> 5/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | dfca61ea510ec211
40 | G - 1-5/8" double row MST @ 16" O.C. (162S125-33 (DERIVED)) - board per face, see Side 1 / Side 2 (1 instance) | Office 110 / Womens Restroom 114 | 11.63 | 15.375 | 4 |  |  | 338.25 | 162S125-33 (DERIVED) | 16 | 22 | Office 110 | 15.375 | 2 | Womens Restroom 114 | 15.375 | 2 | 0 | 715.245 | [7 empty] | 23.26 | 23.26 | CONTINUOUS SLIP TRACK per 5/A12.01 | 69.78 | 132 |  | 178.76 | 46.52 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag G @1010,1211) -> 5/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | 95c0914f7f854aa7
38 | G - 1-5/8" double row MST @ 16" O.C. (162S125-33 (DERIVED)) - board per face, see Side 1 / Side 2 (1 instance) | ATM Room 102 / Office 109 | 11.63 | 15.375 | 4 |  |  | 338.25 | 162S125-33 (DERIVED) | 16 | 22 | ATM Room 102 | 15.375 | 2 | Office 109 | 15.375 | 2 | 0 | 715.245 | [7 empty] | 23.26 | 23.26 | CONTINUOUS SLIP TRACK per 5/A12.01 | 69.78 | 132 |  | 178.76 | 46.52 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag G @1052,818) -> 5/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | d1b5c3aba3cc8c73
39 | G - 1-5/8" double row MST @ 16" O.C. (162S125-33 (DERIVED)) - board per face, see Side 1 / Side 2 (1 instance) | Office 109 / Office 110 | 11.63 | 15.375 | 4 |  |  | 338.25 | 162S125-33 (DERIVED) | 16 | 22 | Office 109 | 15.375 | 2 | Office 110 | 15.375 | 2 | 0 | 715.245 | [7 empty] | 23.26 | 23.26 | CONTINUOUS SLIP TRACK per 5/A12.01 | 69.78 | 132 |  | 178.76 | 46.52 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag G @1053,1049) -> 5/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | 90c02d1bb0f0e82e
33 | G - 1-5/8" double row MST @ 16" O.C. (162S125-33 (DERIVED)) - board per face, see Side 1 / Side 2 (1 instance) | Office 108 / Cash Window 116 | 7.09 | 15.375 | 4 |  |  | 246 | 162S125-33 (DERIVED) | 16 | 16 | Office 108 | 15.375 | 2 | Cash Window 116 | 15.375 | 2 | 0 | 436.035 | [7 empty] | 14.18 | 14.18 | CONTINUOUS SLIP TRACK per 5/A12.01 | 42.54 | 96 |  | 109.06 | 28.36 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag G @1766,1129) -> 5/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | 79103f4c2266d860
35 | G - 1-5/8" double row MST @ 16" O.C. (162S125-33 (DERIVED)) - board per face, see Side 1 / Side 2 (1 instance) | pier between office fronts 105/106 | 3.47 | 15.375 | 4 |  |  | 153.75 | 162S125-33 (DERIVED) | 16 | 10 | Office 105/106 | 15.375 | 2 | Central Zone 103 | 15.375 | 2 | 0 | 213.405 | [7 empty] | 6.94 | 6.94 | CONTINUOUS SLIP TRACK per 5/A12.01 | 20.82 | 60 |  | 53.3 | 13.88 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag G @1602,546) -> 5/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | cae17a4876408c84
36 | G - 1-5/8" double row MST @ 16" O.C. (162S125-33 (DERIVED)) - board per face, see Side 1 / Side 2 (1 instance) | pier between office fronts 106/107 | 3.26 | 15.375 | 4 |  |  | 153.75 | 162S125-33 (DERIVED) | 16 | 10 | Office 106/107 | 15.375 | 2 | Central Zone 103 | 15.375 | 2 | 0 | 200.49 | [7 empty] | 6.52 | 6.52 | CONTINUOUS SLIP TRACK per 5/A12.01 | 19.56 | 60 |  | 50.05 | 13.04 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag G @1605,749) -> 5/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | dd057e416849fff8
37 | G - 1-5/8" double row MST @ 16" O.C. (162S125-33 (DERIVED)) - board per face, see Side 1 / Side 2 (1 instance) | pier between office fronts 107/108 | 3.25 | 15.375 | 4 |  |  | 153.75 | 162S125-33 (DERIVED) | 16 | 10 | Office 107/108 | 15.375 | 2 | Central Zone 103 | 15.375 | 2 | 0 | 199.875 | [7 empty] | 6.5 | 6.5 | CONTINUOUS SLIP TRACK per 5/A12.01 | 19.5 | 60 |  | 49.99 | 13 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag G @1602,940) -> 5/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | 0ebe6d3c4508cb16
34 | G - 1-5/8" double row MST @ 16" O.C. (162S125-33 (DERIVED)) - board per face, see Side 1 / Side 2 (1 instance) | pier north of office front 105 | 2.42 | 15.375 | 4 |  |  | 123 | 162S125-33 (DERIVED) | 16 | 8 | Office 105 | 15.375 | 2 | Central Zone 103 | 15.375 | 2 | 0 | 148.83 | [7 empty] | 4.84 | 4.84 | CONTINUOUS SLIP TRACK per 5/A12.01 | 14.52 | 48 |  | 37.21 | 9.68 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (untagged; measured 6.16in = G (schedule 6 1/8)) -> 5/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | 80032d977dab8796
41 | G1 - 1-5/8" double row MST @ 16" O.C. (162S125-33 (DERIVED)) - board per face, see Side 1 / Side 2 (1 instance) | Office 105 / Office 106 | 11.77 | 15.375 | 4 |  |  | 338.25 | 162S125-33 (DERIVED) | 16 | 22 | Office 105 | 15.375 | 2 | Office 106 | 15.375 | 2 | 0 | 723.855 | [7 empty] | 23.54 | 23.54 | CONTINUOUS SLIP TRACK per 5/A12.01 | 70.62 | 132 |  | 180.91 | 47.08 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag G1 @1714,548) -> 5/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | ac841e41d57e14fd
42 | G1 - 1-5/8" double row MST @ 16" O.C. (162S125-33 (DERIVED)) - board per face, see Side 1 / Side 2 (1 instance) | pier between office fronts 109/110 | 3.84 | 15.375 | 4 |  |  | 153.75 | 162S125-33 (DERIVED) | 16 | 10 | Office 109/110 | 15.375 | 2 | Central Zone 103 | 15.375 | 2 | 0 | 236.16 | [7 empty] | 7.68 | 7.68 | CONTINUOUS SLIP TRACK per 5/A12.01 | 23.04 | 60 |  | 59.02 | 15.36 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (tag G1 @1149,1008) -> 5/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | 177e848d82f0ca08
43 | G1 - 1-5/8" double row MST @ 16" O.C. (162S125-33 (DERIVED)) - board per face, see Side 1 / Side 2 (1 instance) | pier south of office front 110 | 3.35 | 15.375 | 4 |  |  | 153.75 | 162S125-33 (DERIVED) | 16 | 10 | Office 110 | 15.375 | 2 | Central Zone 103 | 15.375 | 2 | 0 | 206.025 | [7 empty] | 6.7 | 6.7 | CONTINUOUS SLIP TRACK per 5/A12.01 | 20.1 | 60 |  | 51.47 | 13.4 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (untagged; measured 8.48in = G1) -> 5/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | ebdbc3d7525d3f8c
44 | G1 - 1-5/8" double row MST @ 16" O.C. (162S125-33 (DERIVED)) - board per face, see Side 1 / Side 2 (1 instance) | pier north of office front 109 | 1.34 | 15.375 | 4 |  |  | 123 | 162S125-33 (DERIVED) | 16 | 8 | Office 109 | 15.375 | 2 | Central Zone 103 | 15.375 | 2 | 0 | 82.41 | [7 empty] | 2.68 | 2.68 | CONTINUOUS SLIP TRACK per 5/A12.01 | 8.04 | 48 |  | 20.59 | 5.36 | PENDING (see Blocking sheet) |  | [DERIVADO] vector A02.01 | A02.01 (untagged; measured 8.48in = G1) -> 5/A12.01 -> 7/S5.20 -> S2.20 B.O.D. -> A04.01 ceiling | 70cc5fbe8a86464b
| TOTALS - INTERIOR PARTITIONS |  | 402.23 |  |  | 1855.86 | 3372.09 | 3290.25 |  |  | 610 | [6 empty] | 327.35 | 12038.1854 | 170.44 | 206.64 | 260.15 |  |  |  |  | 500.45 | 500.45 |  | 1501.35 | 3660 | 60.06 | 5395.94 | 1274.9

## Exterior
Closure | Facade / segment (axis kept separate) | Length (LF) | Stud height (FT) | 6" Metal Stud 600S137-33 (LF) | Parapet stud 600S162-54 (LF) | Stud pcs | Bottom track (LF) | Top / deflection track (LF) | Header (LF) | Sill track (LF) | Bracing (LF) | Clips (ea) | 5/8" Gyp Board interior face (SF) | 5/8" Glass Mat Sheathing (SF) | 5/8" Exterior Gypsum Sheathing - parapet (SF) | ALT: 5/8" FRT ply + 2 1/2" polyiso (SF) - not in base | Box beam over storefront (LF) | 3/4" FRT plywood at opening (LF) | Gyp jamb return (LF) | Sealant (LF) | Detail sequence | Seal
X45_EXT-E | East facade grid 8, interior face x=1843.08 (offices 105-108, cash window, work room) | 75.33 | 15.375 | 1483.49 |  | 131 | 75.33 | 75.33 | 36 | 32 | 225.99 | 786 | 1036.56 | 1036.56 |  | 1036.56 |  |  |  | 75.33 | A02.01 plan face -> C/A09.21 WALL SECTION -> 5/A09.26 SECTION DETAIL @ ACM BASE -> 7/S5.20 METAL STUD SCHEDULE -> S2.20 B.O.D. | c51aeb1bbc1b4523
X47_EXT-S | South facade grid A, interior face y=1693.44 (wellness, NER, break, work room) | 51.73 | 13.052 | 601.99 |  | 48 | 51.73 | 51.73 | 4.33 |  | 155.19 | 288 | 648 | 648 |  | 648 |  |  |  | 51.73 | A02.01 plan face -> C/A09.21 WALL SECTION -> 5/A09.26 SECTION DETAIL @ ACM BASE -> 7/S5.20 METAL STUD SCHEDULE -> S2.20 B.O.D. | 56d6250c0df3c737
X48_EXT-W1 | West facade grid 1, interior face x=911.88 (offices 109/110, restrooms, janitor, wellness) | 47.41 | 15.375 | 850.36 |  | 74 | 47.41 | 47.41 | 18 | 16 | 142.23 | 444 | 639.29 | 639.29 |  | 639.29 |  |  |  | 47.41 | A02.01 plan face -> C/A09.21 WALL SECTION -> 5/A09.26 SECTION DETAIL @ ACM BASE -> 7/S5.20 METAL STUD SCHEDULE -> S2.20 B.O.D. | d5847a382bbdaba4
X50_EXT-W2 | West facade grid 1 north, interior face x=841.56 (24 HR vestibule 101 / ATM room 102, Day 1 ATM) | 21.42 | 15.375 | 379.16 |  | 27 | 21.42 | 21.42 | 3.18 | 2.18 | 64.26 | 162 | 323.69 | 323.69 |  | 323.69 |  |  |  | 21.42 | A02.01 plan face -> C/A09.21 WALL SECTION -> 5/A09.26 SECTION DETAIL @ ACM BASE -> 7/S5.20 METAL STUD SCHEDULE -> S2.20 B.O.D. | 64bdc98b68e72143
X51_EXT-W3 | West facade jog south of ATM room, y=840.72 from x 841.56 to 911.88 | 3.91 | 15.375 | 76.88 |  | 5 | 3.91 | 3.91 |  |  | 11.73 | 30 | 60.07 | 60.07 |  | 60.07 |  |  |  | 3.91 | A02.01 plan face -> C/A09.21 WALL SECTION -> 5/A09.26 SECTION DETAIL @ ACM BASE -> 7/S5.20 METAL STUD SCHEDULE -> S2.20 B.O.D. | 393d2e8f17c63e31
X52_EXT-N1 | North facade grid G/F east part, interior face y=337.44 (office 105 + NE pier) | 12.64 | 15.375 | 184.5 |  | 12 | 12.64 | 12.64 |  |  | 37.92 | 72 | 194.31 | 194.31 |  | 194.31 |  |  |  | 12.64 | A02.01 plan face -> C/A09.21 WALL SECTION -> 5/A09.26 SECTION DETAIL @ ACM BASE -> 7/S5.20 METAL STUD SCHEDULE -> S2.20 B.O.D. | 3ade2cb2b104d9ea
X53_SFband | North storefront head band, Central Zone 103 (26.68 ft storefront 1135.4->1615.6 A02.01) | 26.68 | 6.88 | 144.48 |  | 21 | 26.68 | 26.68 |  |  | 26.68 | 42 | 183.56 | 183.56 |  |  | 26.68 | 26.68 | 26.68 | 26.68 | A02.01 storefront (Div 08) -> A09.01 elevation T/GLAZING 8-6 -> A/A09.21 SECTION A @ ENTRANCE DOOR -> 11/A09.27 storefront head | 67827df3e54a04c5
X54_SFband | North storefront head band, Vestibule 100 (841.6->1126.4 A02.01, incl. C1 columns) | 15.82 | 6.88 | 82.56 |  | 12 | 15.82 | 15.82 |  |  | 15.82 | 24 | 108.84 | 108.84 |  |  | 15.82 | 15.82 | 15.82 | 15.82 | A02.01 storefront (Div 08) -> A09.01 elevation T/GLAZING 8-6 -> A/A09.21 SECTION A @ ENTRANCE DOOR -> 11/A09.27 storefront head | 3f117f156f6fe858
X55_SFband | West storefront head band, Vestibule 100 (x~832, 318.6->454.4 A02.01) | 7.54 | 6.88 | 41.28 |  | 6 | 7.54 | 7.54 |  |  | 7.54 | 12 | 51.88 | 51.88 |  |  | 7.54 | 7.54 | 7.54 | 7.54 | A02.01 storefront (Div 08) -> A09.01 elevation T/GLAZING 8-6 -> A/A09.21 SECTION A @ ENTRANCE DOOR -> 11/A09.27 storefront head | 7417b96c54632d83
X56_parapet | Parapet infill above B.O.D., E-HI 50.50 + N1 12.64 + N2 26.68 + W1-HI 22.58 + W2 21.42 + W3 3.91 | 137.73 | 2.04 |  | 326.4 | 160 | 137.73 | 137.73 | [6 empty] | 280.97 | 280.97 |  |  |  |  | S2.20 6/S5.10 & 10/S5.10 burbujas -> 6/S5.10 SECTION AT PERIMETER -> 11/S5.10 PARAPET INFILL FRAMING -> C/A09.21 T/STUD LP | 2b33264997a757ad
X57_parapet | Parapet infill above B.O.D., E-LO 24.84 + S 51.73 + W1-LO 24.84 | 101.41 | 4.37 |  | 520.03 | 119 | 101.41 | 101.41 |  |  | 101.41 | 238 |  |  | 443.16 | 443.16 |  |  |  |  | S2.20 6/S5.10 & 10/S5.10 burbujas -> 6/S5.10 SECTION AT PERIMETER -> 11/S5.10 PARAPET INFILL FRAMING -> C/A09.21 T/STUD LP | 7ac1e1ac8bc480a2
X58_parapet | Parapet infill above B.O.D., N3 15.82 + W4 7.54 (T.O. PARAPET 2 20 ft grids 2-4 A09.01) | 23.36 | 4.29 |  | 120.12 | 28 | 23.36 | 23.36 |  |  | 23.36 | 56 |  |  | 100.21 | 100.21 |  |  |  |  | S2.20 6/S5.10 & 10/S5.10 burbujas -> 6/S5.10 SECTION AT PERIMETER -> 11/S5.10 PARAPET INFILL FRAMING -> C/A09.21 T/STUD LP | 595fdb38d54331c5
| TOTALS - EXTERIOR (each facade stays on its own row above) | 524.98 |  | 3844.7 | 966.55 | 643 | 524.98 | 524.98 | 61.51 | 50.18 | 812.13 | 2154 | 3246.2 | 3246.2 | 824.34 | 3726.26 | 50.04 | 50.04 | 50.04 | 262.48

## Opening Bands
Closure | Opening / band | Length = opening width (LF) | Band height (FT) | 1-5/8" Metal Stud (LF) | Stud pcs | Bottom track on box beam (LF) | Top slip track (LF) | Box beam 2-362CSJ20 (LF) | 5/8" Gyp Board (SF) 2 layers x 2 faces | 3/4" FRT plywood blocking (LF) | Corner bead (LF) | Shadow molding (LF) | Insulation (SF) | Sealant (LF) | Sill band (lower) | Detail sequence | Seal
BH_105 | Office bulkhead over office front DFC-1A, Office 105 / Central Zone 103 | 7.5 | 7.38 | 118 | 16 | 15 | 15 | 7.5 | 221.26 | 7.5 | 15 | 7.5 | 55.31 | 30 | 0 - office front DFC-1A installs on structural slab (9/A12.01), no sill band | A02.01 DFC-1A office front + note E (office front by bank vendor) -> 8/A12.01 OFFICE BULKHEAD DETAIL @ DOOR -> 9/A12.01 OFFICE BULKHEAD DETAIL @ GLASS PANEL -> 2/A11.04 office front height | 35d0b2d27e682e3a
BH_106 | Office bulkhead over office front DFC-1A, Office 106 / Central Zone 103 | 7.5 | 7.38 | 118 | 16 | 15 | 15 | 7.5 | 221.26 | 7.5 | 15 | 7.5 | 55.31 | 30 | 0 - office front DFC-1A installs on structural slab (9/A12.01), no sill band | A02.01 DFC-1A office front + note E (office front by bank vendor) -> 8/A12.01 OFFICE BULKHEAD DETAIL @ DOOR -> 9/A12.01 OFFICE BULKHEAD DETAIL @ GLASS PANEL -> 2/A11.04 office front height | 3ab0d73d20ded81e
BH_107 | Office bulkhead over office front DFC-1A, Office 107 / Central Zone 103 | 7.5 | 7.38 | 118 | 16 | 15 | 15 | 7.5 | 221.26 | 7.5 | 15 | 7.5 | 55.31 | 30 | 0 - office front DFC-1A installs on structural slab (9/A12.01), no sill band | A02.01 DFC-1A office front + note E (office front by bank vendor) -> 8/A12.01 OFFICE BULKHEAD DETAIL @ DOOR -> 9/A12.01 OFFICE BULKHEAD DETAIL @ GLASS PANEL -> 2/A11.04 office front height | ba867ca02ffed8b6
BH_108 | Office bulkhead over office front DFC-1A, Office 108 / Central Zone 103 | 7.5 | 7.38 | 118 | 16 | 15 | 15 | 7.5 | 221.26 | 7.5 | 15 | 7.5 | 55.31 | 30 | 0 - office front DFC-1A installs on structural slab (9/A12.01), no sill band | A02.01 DFC-1A office front + note E (office front by bank vendor) -> 8/A12.01 OFFICE BULKHEAD DETAIL @ DOOR -> 9/A12.01 OFFICE BULKHEAD DETAIL @ GLASS PANEL -> 2/A11.04 office front height | e5cbc3f44add6d0f
BH_109 | Office bulkhead over office front DFC-1A, Office 109 / Central Zone 103 | 7.5 | 7.38 | 118 | 16 | 15 | 15 | 7.5 | 221.26 | 7.5 | 15 | 7.5 | 55.31 | 30 | 0 - office front DFC-1A installs on structural slab (9/A12.01), no sill band | A02.01 DFC-1A office front + note E (office front by bank vendor) -> 8/A12.01 OFFICE BULKHEAD DETAIL @ DOOR -> 9/A12.01 OFFICE BULKHEAD DETAIL @ GLASS PANEL -> 2/A11.04 office front height | 66ce7f3cedd8c7ab
BH_110 | Office bulkhead over office front DFC-1A, Office 110 / Central Zone 103 | 7.5 | 7.38 | 118 | 16 | 15 | 15 | 7.5 | 221.26 | 7.5 | 15 | 7.5 | 55.31 | 30 | 0 - office front DFC-1A installs on structural slab (9/A12.01), no sill band | A02.01 DFC-1A office front + note E (office front by bank vendor) -> 8/A12.01 OFFICE BULKHEAD DETAIL @ DOOR -> 9/A12.01 OFFICE BULKHEAD DETAIL @ GLASS PANEL -> 2/A11.04 office front height | 2aa750f74f13cc3b
| TOTALS - OFFICE BULKHEADS | 45 |  | 708 | 96 | 90 | 90 | 45 | 1327.56 | 45 | 90 | 45 | 331.86 | 180
Exterior opening bands: storefront head bands are closures X53-X55 (sheet Exterior); window head/sill cripples are inside X45/X48 (B/GLAZING 6'-6", T/GLAZING 8'-6"); Day 1 ATM band PENDING (RFI-19); interior storefront 101 / coiling grille 103 band PENDING (RFI-20).

## Ceilings GWB
ID | Room | Ceiling tag | Height A.F.F. (FT) | Area (SF) | Area derivation | Transition / edge (LF) | Suspension | Seal
CEIL-1 | Vestibule 100 + 24 HR Vestibule 101 | GB 10'-0" | 10 | 271.22 | Vestibule 100 rectangle: x 841.60-1126.40, y 331.10-460.40 A04.01/A02.01: 284.80 x 129.30 pt / 324 = 113.65 ¦ 24 HR Vestibule 101 polygon: x 841.56-1130.28 between storefront y 460.40 and F wall north face y=553.80+tan30*(x-841.44): width 288.72 x mean depth 176.83 pt / 324 = 157.57 |  | PENDING RFI-11: GB ceiling suspension system (carrying/furring channel or drywall grid) not detailed in A09.33 / no spec book | 341d6f2afbffa8b6
CEIL-2 | Waiting 104 | GB 11'-0" | 11 | 510.8 | Waiting 104: A04.01 boundary lines x 1223.88 & 1530.36, y 427.44-967.44: 306.48 x 540.00 pt / 324 (540 pt = 30'-0" printed A04.01) = 510.8 | 77.03 | PENDING RFI-11: GB ceiling suspension system (carrying/furring channel or drywall grid) not detailed in A09.33 / no spec book | 14c469c07c1c1c93
CEIL-3 | Womens Restroom 114 | GB 8'-6" | 8.5 | 82.36 | Womens Restroom 114: x 911.88-1123.08, y 1236.36-1362.72 (A02.01 faces): 11.73 x 7.02 ft = 82.36 |  | PENDING RFI-11: GB ceiling suspension system (carrying/furring channel or drywall grid) not detailed in A09.33 / no spec book | a2026b0fb0a58199
CEIL-4 | Mens Restroom 113 | GB 8'-6" | 8.5 | 82.36 | Mens Restroom 113: x 911.88-1123.08, y 1382.16-1508.52: 11.73 x 7.02 ft = 82.36 |  | PENDING RFI-11: GB ceiling suspension system (carrying/furring channel or drywall grid) not detailed in A09.33 / no spec book | b25a0e8001600121
| TOTAL GWB CEILINGS |  |  | 946.74 |  | 77.03
ACT ceilings (Div 09 51 00, not ours): ACT-4 / ACT-5 per A04.01 - listed for reference only. Open to structure: Janitor 112, Storage 117, Electrical 120, NER 121 (A04.01 key note 1).

## Soffits
ID | Soffit | Tag | Height (FT) | Bottom (SF) | Vertical face (SF) | Edge trim (LF) | Framing | Seal
SOFF-1 | CSR soffit over teller line, Cash Window 116 | GB 8'-0" | 8 | 35.79 | 12.01 | 12.01 | 3 5/8" CFMF @ 16" O.C. (10/A09.33) - piece count PENDING (RFI-23) | c22edd66ddd140d2
S-canopy | Exterior canopy soffit (EPS-1 ACM / PT-4 stucco soffit band, A04.01 top band) | - | 10'-6" B/CANOPY | PENDING | PENDING | PENDING | canopy framing per 3/A09.26 and D/A09.22 not quantified - RFI-21

## MEP crossings
# | Wall | Duct (label read on M01.01) | Treatment
1 | wall 5 A1 | 10"ø R-1B | framed opening: head + sill track 5.0 LF, 2 jamb studs (6/S5.20, 9/S5.20)
2 | wall 9 A1 | 8"ø | framed opening: head + sill track 5.0 LF, 2 jamb studs (6/S5.20, 9/S5.20)
3 | wall 9 A1 | S-1A duct (size not legible in crop) | framed opening: head + sill track 5.0 LF, 2 jamb studs (6/S5.20, 9/S5.20)
4 | wall 15 A5 | duct (size not legible) | framed opening: head + sill track 5.0 LF, 2 jamb studs (6/S5.20, 9/S5.20)
5 | wall 16 A5 | 14"x12" | framed opening: head + sill track 5.0 LF, 2 jamb studs (6/S5.20, 9/S5.20)
6 | wall 21 B | 8"x8" | framed opening: head + sill track 5.0 LF, 2 jamb studs (6/S5.20, 9/S5.20)
7 | wall 23 B2 | 12"x10" | framed opening: head + sill track 5.0 LF, 2 jamb studs (6/S5.20, 9/S5.20)
8 | wall 23 B2 | 10"x10" | framed opening: head + sill track 5.0 LF, 2 jamb studs (6/S5.20, 9/S5.20)
9 | wall 23 B2 | 8"x8" | framed opening: head + sill track 5.0 LF, 2 jamb studs (6/S5.20, 9/S5.20)
10 | wall 23 B2 | 8"ø | framed opening: head + sill track 5.0 LF, 2 jamb studs (6/S5.20, 9/S5.20)
11 | wall 32 G | 8"x10" | framed opening: head + sill track 5.0 LF, 2 jamb studs (6/S5.20, 9/S5.20)
12 | wall 32 G | 10"ø | framed opening: head + sill track 5.0 LF, 2 jamb studs (6/S5.20, 9/S5.20)
13 | wall 33 G | 10"ø | framed opening: head + sill track 5.0 LF, 2 jamb studs (6/S5.20, 9/S5.20)
14 | wall 38 G | 8"x10" | framed opening: head + sill track 5.0 LF, 2 jamb studs (6/S5.20, 9/S5.20)
15 | wall 39 G | 8"ø | framed opening: head + sill track 5.0 LF, 2 jamb studs (6/S5.20, 9/S5.20)
16 | wall 40 G | 8"x10" | framed opening: head + sill track 5.0 LF, 2 jamb studs (6/S5.20, 9/S5.20)
17 | wall 40 G | 12"x10" | framed opening: head + sill track 5.0 LF, 2 jamb studs (6/S5.20, 9/S5.20)
18 | wall 41 G1 | 8"x10" | framed opening: head + sill track 5.0 LF, 2 jamb studs (6/S5.20, 9/S5.20)
19 | wall 43 G1 | 12"x10" (same run as #7?) | framed opening: head + sill track 5.0 LF, 2 jamb studs (6/S5.20, 9/S5.20)
| TOTAL framed openings | 19 | track 95.0 LF, jamb studs 38 ea
| Registration | M01.01 offset dx=-571.92 dy=21.84 voted with mep.registro (vy=124 >=25) and verified on F wall diagonal (1413.36,531.96) -> A02.01 (841.44,553.80)
| Excluded | #0 wall 1: duct runs alongside, not through (crop #0) -> not counted; wall 43 single lw1.56 line = door frame, not duct
| Pending | P01.01/P01.02 (plumbing) NOT registered: mep.registro votes vx=1 vy=3 <25 -> no geometric crossing; restroom chase C1 carries piping (RFI-16). E02.x not crossed (conduit in walls normally by electrician).

## Blocking
Item | Derivation | Qty | Unit | Status | Source / RFI
Wall stops (A00.30 sheet note D "PROVIDE BLOCKING AT EACH WALL STOP") | doors 111(04A),113(08),114(08),115(16),116(11),117(10),118A(11B),118B(11),119(12) = 9 hardware groups listing 1 EA WALL STOP WS407CCV (A00.30 HARDWARE GROUPS); 2'-0" per stop (stop not located on plan) | 18 | LF | DERIVADO | A00.30 note D + hardware groups
Mens Restroom 113 toilet accessories (FRT blocking, A08.01 sheet note E) | TA-3 42" grab bar 4.5 + TA-4 36" grab bar 4.0 + TA-5 18" grab bar 2.5 + TA-7 mirror 2 runs x 2.0 + TA-8 soap 2.0 + TA-10 TP 2.0 + TA-16 baby changing 2 x 3.0 + TA-17 seat cover 2.0 + coat hook 2.0 | 29 | LF | DERIVADO | A08.01 TOILET ACCESSORY LEGENDS + note E
Womens Restroom 114 toilet accessories (FRT blocking, A08.01 sheet note E) | same as 113 + TA-9 sanitary napkin 2.0 | 31 | LF | DERIVADO | A08.01 TOILET ACCESSORY LEGENDS + note E
Janitor Closet 112 utility hook TA-6 | 1 x 2.0 | 2 | LF | DERIVADO | A08.01 TA-6
Wellness 115 mirror TA-19 | 2 runs x 2.0 | 4 | LF | DERIVADO | A08.01 TA-19
85" display monitor, key note 7 A02.01 ("PROVIDE BLOCKING IN WALL AS REQUIRED") | 2 runs x 10'-0" recess width printed A02.01 (C1 #29 zone) | 20 | LF | DERIVADO | A02.01 key note 7
Lockers, key note 5 A02.01 | locker bank width not dimensioned | PENDING | LF | PENDIENTE | RFI-12
Roof hatch & ladder, RCP key note 9 / A09.30 | ladder bracket blocking - detail 9/A09.30 not quantified | PENDING | LF | PENDIENTE | RFI-13
Millwork MW01, MW05, MW06A, MW07, MW08, MW11, MW12, MW13, MW18, MW21 (A12.03-A12.06, A02.01 note C) | base = 1 run, upper = 2 runs; millwork details not opened in this unattended run | PENDING | LF | PENDIENTE | RFI-INT-01
3/4" FRT plywood backboard Electrical 120 / NER 121, key note 6 A02.01 (A11.03) | area per A11.03 elevations not measured; normally Div 06 | PENDING | SF | PENDIENTE | RFI-14
TOTAL quantified FRT blocking |  | 104 | LF |  | FRT blocking per A08.01 note E; 2x lumber vs 20 GA steel blocking not specified -> RFI-15

## Wet Zones
Item | Derivation | Qty | Unit | Status
5/8" moisture resistant gypsum board (RECLASSIFIED from regular, not added) - C1 chase face Womens 114 (toilet + lavatory wall) | A08.01 sheet note F "USE MOISTURE RESISTANT GYPSUM BOARD BEHIND TOILET AND LAVATORY": toilet tank and lavatory both on the chase face (A02.01/A08.01 plan) = W27 BOARD 90.27 SF | 90.27 | SF | DERIVADO
5/8" moisture resistant gypsum board (RECLASSIFIED) - C1 chase face Mens 113 | idem = W28 BOARD 90.27 SF | 90.27 | SF | DERIVADO
FRP-1 restroom walls Womens 114 | A08.01 "5'-0\" TO TOP OF FRP" over ceramic tile cove base (3/A08.01): band 5.0 - 0.5 cove (RFI-24, cove height not dimensioned) = 4.5 ft x perimeter 2x(11.73+7.02) - door 3.33 = 34.17 LF | 153.75 | SF | DERIVADO
FRP-1 restroom walls Mens 113 | idem | 153.75 | SF | DERIVADO
FRP-2 mop sink Janitor 112 (A05.01 key note 6 "FRP FROM FLOOR TO 4'-0\" AFF, WIDTH TO MATCH WIDTH OF MOP SINK AT BOTH SIDES") | height 4'-0" printed; mop sink width not dimensioned -> 24 in assumed both sides = 2 x 2.0 x 4.0 (RFI-25) | 16 | SF | DERIVADO
Break Room 118 sink (MW08) | no FRP / W.R. note on A05.01 for 118 -> RFI-INT-01 + alternate, not quantified | PENDING | SF | PENDIENTE
Census | 4 rooms with plumbing fixtures (A02.01 / A08.01 / P01.01): Womens 114, Mens 113, Janitor 112 (mop sink), Break Room 118 (MW08 sink). Resolved: 3 quantified, 1 RFI (118).

## Purchase Summary
Material | Family | Unit | NET | Waste % | WASTE | BUY | Stock / unit | Purchase units | Source
3-5/8" metal stud 362S137-33 | METAL | LF | 3061.71 | 0.15 | 459.26 | 3520.97 | 20 | 177 | Takeoff col H (A1,B,C1,F)
3-5/8" metal stud 14 GA 362S137-68 | METAL | LF | 310.38 | 0.15 | 46.56 | 356.94 | 20 | 18 | Takeoff col H (A1K, 4/A12.01)
6" metal stud 600S137-33 (interior) | METAL | LF | 1794.36 | 0.15 | 269.15 | 2063.51 | 20 | 104 | Takeoff col G (A5,B2)
6" metal stud 14 GA 600S137-68 | METAL | LF | 61.5 | 0.15 | 9.23 | 70.73 | 20 | 4 | Takeoff col G (B2K)
1-5/8" metal stud (G/G1 double row + bulkheads) | METAL | LF | 3998.25 | 0.15 | 599.74 | 4597.99 | 20 | 230 | Takeoff col I + Opening Bands col E
6" metal stud 600S137-33 (exterior + storefront bands) | METAL | LF | 3844.7 | 0.15 | 576.71 | 4421.41 | 20 | 222 | Exterior col E
6" parapet stud 600S162-54 | METAL | LF | 966.55 | 0.15 | 144.98 | 1111.53 | 20 | 56 | Exterior col F (11/S5.10)
Bottom track - interior (all sizes; split by stud size in Takeoff) | METAL | LF | 590.45 | 0.15 | 88.57 | 679.02 | 10 | 68 | Takeoff col AB + bulkheads
Top slip track - interior | METAL | LF | 590.45 | 0.15 | 88.57 | 679.02 | 10 | 68 | Takeoff col AC + bulkheads
Bottom track exterior 600T125-33 / parapet 600T125-54 | METAL | LF | 524.98 | 0.15 | 78.75 | 603.73 | 10 | 61 | Exterior col H
Top deflection track exterior 600T200-97 / parapet 600T125-54 | METAL | LF | 524.98 | 0.15 | 78.75 | 603.73 | 10 | 61 | Exterior col I
Header (track headers / CSJ) + box beams | METAL | LF | 216.61 | 0.15 | 32.49 | 249.1 | 10 | 25 | Takeoff AG + Exterior J,R + bulkhead box beam
Sill track exterior windows | METAL | LF | 50.18 | 0.15 | 7.53 | 57.71 | 10 | 6 | Exterior col K
1 1/2" C.R. channel bracing | METAL | LF | 2313.48 | 0.15 | 347.02 | 2660.5 | 16 | 167 | F/1/S5.20
Clips at bracing | METAL | EA | 5814 | 0.15 | 872.1 | 6686.1 |  |  | F/1/S5.20
MEP framed openings track | METAL | LF | 95 | 0.15 | 14.25 | 109.25 | 10 | 11 | MEP crossings sheet
5/8" gypsum board regular (walls) | NOT METAL | SF | 16431.4054 | 0.06 | 985.88 | 17417.2854 | 48 | 363 | Takeoff T + bulkheads + exterior interior face - MR reclassified
5/8" moisture resistant gypsum board (reclassified, A08.01 note F) | NOT METAL | SF | 180.54 | 0.06 | 10.83 | 191.37 | 48 | 4 | Wet Zones
FRP-1 restroom wall panels + PVC trims | NOT METAL | SF | 307.5 | 0.06 | 18.45 | 325.95 |  |  | A08.01, 3/A08.01
FRP-2 mop sink | NOT METAL | SF | 16 | 0.06 | 0.96 | 16.96 |  |  | A05.01 key note 6
5/8" gypsum board (ceilings + CSR soffit) | NOT METAL | SF | 994.54 | 0.06 | 59.67 | 1054.21 | 48 | 22 | Ceilings GWB + Soffits
3/8" gypsum board (A1K/B2K customer side) | NOT METAL | SF | 170.44 | 0.06 | 10.23 | 180.67 | 48 | 4 | 4/A12.01
3/8" UL752 Level-2 fiberglass ballistic panel | NOT METAL | SF | 206.64 | 0.06 | 12.4 | 219.04 |  |  | 4/A12.01
5/8" glass mat sheathing (exterior face) | NOT METAL | SF | 3246.2 | 0.06 | 194.77 | 3440.97 | 48 | 72 | 5/A09.26, 9/A09.27
5/8" exterior gypsum sheathing (parapet roof side) | NOT METAL | SF | 824.34 | 0.06 | 49.46 | 873.8 | 48 | 19 | C/A09.21
3/4" FRT plywood (F wall public side) | NOT METAL | SF | 260.15 | 0.06 | 15.61 | 275.76 |  |  | 12/A12.01
3/4" FRT plywood strips (bulkheads + storefront heads) | NOT METAL | LF | 95.04 | 0.06 | 5.7 | 100.74 |  |  | 8/A12.01, 11/A09.27
Corner bead | METAL | LF | 102.01 | 0.15 | 15.3 | 117.31 | 10 | 12 | 8/A12.01, 10/A09.33
Shadow molding | METAL | LF | 45 | 0.15 | 6.75 | 51.75 | 10 | 6 | 8/A12.01
Ceiling transition GB 11-0 to ACT 11-6 (kicker framing, 7/A09.33) | METAL | LF | 77.03 | 0.15 | 11.55 | 88.58 |  |  | 7/A09.33
Batt insulation (interior partitions + bulkheads) | NOT METAL | SF | 5727.8 | 0.06 | 343.67 | 6071.47 |  |  | A12.01 schedule INSULATION YES
Acoustical sealant | NOT METAL | LF | 1717.38 | 0.06 | 103.04 | 1820.42 | 25 | 73 | A12.01 details
FRT blocking (quantified part) | NOT METAL | LF | 104 | 0.06 | 6.24 | 110.24 |  |  | Blocking sheet
Fasteners, screws, joint compound, tape: yields per SF, no waste (not plan quantities). PENDING items are never in these totals - see sheet PARA REVISAR EN LA MANANA.

## RFIs
RFI | Sheet / detail | Issue | Delta | Image (Planos marcados/revisar)
RFI-01 | 5/A12.01 PARTITION G / G1 | Top line of detail 5 is not labeled (no UNDERSIDE OF STRUCTURE note). Quoted: 2 layers 5/8" per face to deck (consistent with 8/A12.01 and 9/A12.01 "2 LAYERS ... TO UNDERSIDE OF DECK"). Alternate: board 6" above ceiling. | -2,226.8 SF of 5/8" gypsum board if board stops 6" above ceiling | R01_G_board_top_5-A12.01.png
RFI-02 | A02.01 G1 vs 5/A12.01 schedule | G1 drawn 8.48" thick with two 2.48" studs + 1.04" gap; schedule says 1-5/8" studs, 8" thickness. 1-5/8" stud has no designation in 7/S5.20 (162S125-33 derived). Quoted 1-5/8" per schedule. | same LF; price delta 1-5/8" -> 2-1/2" stud on 4 G1 walls + 6 bulkheads (~1,000 LF) | R02_G1_thickness_A02.01.png
RFI-03 | 7/S5.20 vs 1,3,5/A12.01 | CONTINUOUS SLIP TRACK required by details; 7/S5.20 names only 600T200-97 (6"). 3-5/8" and 1-5/8" slip track profiles/gauge not designated. | price delta slip (2" leg) vs standard track on ~470 LF interior top track | -
RFI-04 | A02.01 C1 tags at 4 columns + Future FCAM | C1 (6/A12.01) = BLOCK PARTITION + 3-5/8" stud furring + 5/8" board; tags point to steel columns at vestibule and to FCAM element, no block drawn. Not quantified. | approx +300 SF board + 30 studs if each column furred full height (4 columns x ~5 ft perimeter x 15.375 ft) | R04_C1_columns.png
RFI-05 | A02.01 C1 restroom plumbing chase | No block partition drawn in the 1'-1" chase; quoted 3-5/8" furring + 5/8" MR board each face to 6" above GB 8'-6" ceiling. | +81.3 SF if board goes to deck (2 x 10.03 x 4.05) | R05_C1_chase_restrooms.png
RFI-06 | A02.01 teller line (A1K / B2K) | B2K has no row in the A12.01 schedule: derived as B2 (6") + ballistic = 7-5/8" like A5K. Teller south end shows two parallel hatched bands (#12 and #13); both quantified as A1K. | -2.98 LF A1K (#12) if the south cap is millwork, not wall | R03_teller_A1K_B2K.png
RFI-07 | 8/A12.01, 9/A12.01 | 3/4" FRT PLYWOOD BLOCKING width under box beam not dimensioned (carried in LF). | unit only | -
RFI-08 | 7/S5.20 HEADER SCHEDULE | Exterior header rows are labeled LOAD BEARING; exterior walls here are infill below roof steel. Confirm 2-60CSJ14 for 8'-0" windows. | price only | -
RFI-09 | C/A09.21 SHEATHING/INSULATION SYSTEM | 5/8" FRT plywood bonded to 2 1/2" polyiso on exterior face: trade not assigned. Carried as ALTERNATE, not in base. | +3,726.3 SF alternate | -
RFI-10 | 11/A09.27, 2/A09.26 | 3/4" FRT plywood and gypsum board jamb return at storefront: width/depth not dimensioned (carried in LF). | unit only | -
RFI-11 | A09.33 / A04.01 | No suspension detail for GB ceilings (drywall grid vs carrying + furring channel). Area quantified 947.3 SF + CSR soffit 47.8 SF. | suspension material not priced | R12_A09.33_ceiling_details.png
RFI-12 | A02.01 key note 5 | Locker blocking: locker bank width not dimensioned. | PENDING | R11_keynotes_blocking.png
RFI-13 | A02.01 key notes 3/4, A09.30 | Roof hatch / ladder blocking not quantified (detail A09.30 not opened in this run). | PENDING | R11_keynotes_blocking.png
RFI-14 | A02.01 key note 6, A11.03 | Fire rated 3/4" plywood backboard in Electrical 120 / NER 121: trade (Div 06 vs drywall) and area. | PENDING | R11_keynotes_blocking.png
RFI-15 | A08.01 note E | FRT wood blocking vs 20 GA steel blocking (4/S5.20 shows 362CR22 clip angle blocking). | price only | -
RFI-16 | P01.01 / P01.02 | Plumbing sheets do not register to A02.01 by vote (1 / 3 matches < 25); plumbing crossings not checked geometrically. | unknown | -
RFI-17 | A/A09.21 vs C/A09.21 | T/STUD HP 19'-8" (entrance tower) vs LP 17'-5": tower extent assumed grids 2-4 (23.36 LF). | +2.25 ft x 600S162-54 per extra LF of HP | R10_parapet_HP_LP.png
RFI-18 | A09.01 / A09.02 | Elevation titles transposed: "SOUTH ELEVATION" shows grids 8->1 (north facade with entrance storefront); "NORTH ELEVATION" shows 1->8 (south facade with door 123). West/East correct. | none (assignment fixed by grids) | R06_A09.01_titles.png
RFI-19 | 6/A08.11 drive-up ATM niche | 2 1/2" METAL STUD SISTERED TO 6" METAL STUD, METAL STUD BOX BEAM, 5/8" FRT PLYWOOD under fiber cement (Div 07) - niche extras not quantified; R.O. 2'-2 1/8" x 2'-7 1/4" is in X50. | PENDING (small) | R07_ATM_openings.png
RFI-20 | A00.30 door 103 / A08.21 | Coiling grille 13'-4" R.O. x 13'-6" and interior storefront 100/101: band above not quantified. | PENDING | R08_interior_storefront_103.png
RFI-21 | A/A09.21, 3/A09.26, D/A09.22 | Exterior canopy framing and soffit (B/CANOPY 10'-6", T/CANOPY 12'-8") not quantified. | PENDING (large) | R09_canopy_A09.21.png
RFI-22 | whole set | No gypsum board control joints labeled (only stucco CJ). ASTM C840 / GA-216. | none in base | -
RFI-23 | 10/A09.33 CSR soffit | 3 5/8" CFMF @ 16" O.C. framing piece count not derived. | PENDING (small) | -
RFI-24 | 3/A08.01 | FRP band = 5'-0" to top minus cove base; cove height not dimensioned (0.5 ft assumed). | +/-34 SF per 0.5 ft | -
RFI-25 | A05.01 key note 6 | Mop sink width not dimensioned (24" assumed both sides). | +/-2.7 SF per 4" of width | -
RFI-26 | S2.20 low roof | Low zone B.O.D. slopes 13'-0 5/8" (grid B) to 12'-6 3/8" (grid A); quoted extreme high for all LO walls. | approx -40 LF stud if interpolated | R16_S2.20_low_roof.png
RFI-27 | A02.01 B2 #24 | Door 102 (3'-6" x 8'-0") position read from its swing on ATM Room east wall. | none | R14_door102_B2.png
RFI-INT-01 | A12.03-A12.06 millwork; Break Room 118 sink | Internal: millwork blocking (MW01, MW05, MW06A, MW07, MW08, MW11, MW12, MW13, MW18, MW21) and break sink backsplash not done in this unattended run. | PENDING | -

## PARA REVISAR EN LA MANANA
# PARA REVISAR EN LA MAÑANA — BOA Broomfield (prueba automática)
Cada punto: hoja + detalle, qué pasó, y la imagen en `Planos marcados/` (carpeta `revisar/` para los R##).
1. **Barrido por tag (punto de revisión que reemplaza la pausa)** — A02.01 + 1,3,4,5,6,12/A12.01
44 walls interiores numerados por tag (A1 9, A1K 4, A5 3, B 6, B2 3, B2K 1, C1 3, F 1, G 10, G1 4). Revisa en cada plano por tipo que no falte ningún wall.
Imagen: `A0201_type_A1.jpg ... A0201_type_G1.jpg`
2. **Default type A1 (nota A de A02.01)** — A02.01 nota A
Walls sin tag cargados por thickness medido: G #34 (pier norte office 105), G1 #43, #44 (piers office fronts 109/110). No se encontró ningún wall sin tag que sea A1 por default fuera de los ya cuantificados; confírmalo en los planos.
Imagen: `A0201_type_G.jpg, A0201_type_G1.jpg`
3. **RFI-01** — 5/A12.01 PARTITION G / G1
Top line of detail 5 is not labeled (no UNDERSIDE OF STRUCTURE note). Quoted: 2 layers 5/8" per face to deck (consistent with 8/A12.01 and 9/A12.01 "2 LAYERS ... TO UNDERSIDE OF DECK"). Alternate: board 6" above ceiling. ¦ Delta: -2,226.8 SF of 5/8" gypsum board if board stops 6" above ceiling
Imagen: `R01_G_board_top_5-A12.01.png`
4. **RFI-02** — A02.01 G1 vs 5/A12.01 schedule
G1 drawn 8.48" thick with two 2.48" studs + 1.04" gap; schedule says 1-5/8" studs, 8" thickness. 1-5/8" stud has no designation in 7/S5.20 (162S125-33 derived). Quoted 1-5/8" per schedule. ¦ Delta: same LF; price delta 1-5/8" -> 2-1/2" stud on 4 G1 walls + 6 bulkheads (~1,000 LF)
Imagen: `R02_G1_thickness_A02.01.png`
5. **RFI-03** — 7/S5.20 vs 1,3,5/A12.01
CONTINUOUS SLIP TRACK required by details; 7/S5.20 names only 600T200-97 (6"). 3-5/8" and 1-5/8" slip track profiles/gauge not designated. ¦ Delta: price delta slip (2" leg) vs standard track on ~470 LF interior top track
Imagen: `-`
6. **RFI-04** — A02.01 C1 tags at 4 columns + Future FCAM
C1 (6/A12.01) = BLOCK PARTITION + 3-5/8" stud furring + 5/8" board; tags point to steel columns at vestibule and to FCAM element, no block drawn. Not quantified. ¦ Delta: approx +300 SF board + 30 studs if each column furred full height (4 columns x ~5 ft perimeter x 15.375 ft)
Imagen: `R04_C1_columns.png`
7. **RFI-05** — A02.01 C1 restroom plumbing chase
No block partition drawn in the 1'-1" chase; quoted 3-5/8" furring + 5/8" MR board each face to 6" above GB 8'-6" ceiling. ¦ Delta: +81.3 SF if board goes to deck (2 x 10.03 x 4.05)
Imagen: `R05_C1_chase_restrooms.png`
8. **RFI-06** — A02.01 teller line (A1K / B2K)
B2K has no row in the A12.01 schedule: derived as B2 (6") + ballistic = 7-5/8" like A5K. Teller south end shows two parallel hatched bands (#12 and #13); both quantified as A1K. ¦ Delta: -2.98 LF A1K (#12) if the south cap is millwork, not wall
Imagen: `R03_teller_A1K_B2K.png`
9. **RFI-07** — 8/A12.01, 9/A12.01
3/4" FRT PLYWOOD BLOCKING width under box beam not dimensioned (carried in LF). ¦ Delta: unit only
Imagen: `-`
10. **RFI-08** — 7/S5.20 HEADER SCHEDULE
Exterior header rows are labeled LOAD BEARING; exterior walls here are infill below roof steel. Confirm 2-60CSJ14 for 8'-0" windows. ¦ Delta: price only
Imagen: `-`
11. **RFI-09** — C/A09.21 SHEATHING/INSULATION SYSTEM
5/8" FRT plywood bonded to 2 1/2" polyiso on exterior face: trade not assigned. Carried as ALTERNATE, not in base. ¦ Delta: +3,726.3 SF alternate
Imagen: `-`
12. **RFI-10** — 11/A09.27, 2/A09.26
3/4" FRT plywood and gypsum board jamb return at storefront: width/depth not dimensioned (carried in LF). ¦ Delta: unit only
Imagen: `-`
13. **RFI-11** — A09.33 / A04.01
No suspension detail for GB ceilings (drywall grid vs carrying + furring channel). Area quantified 947.3 SF + CSR soffit 47.8 SF. ¦ Delta: suspension material not priced
Imagen: `R12_A09.33_ceiling_details.png`
14. **RFI-12** — A02.01 key note 5
Locker blocking: locker bank width not dimensioned. ¦ Delta: PENDING
Imagen: `R11_keynotes_blocking.png`
15. **RFI-13** — A02.01 key notes 3/4, A09.30
Roof hatch / ladder blocking not quantified (detail A09.30 not opened in this run). ¦ Delta: PENDING
Imagen: `R11_keynotes_blocking.png`
16. **RFI-14** — A02.01 key note 6, A11.03
Fire rated 3/4" plywood backboard in Electrical 120 / NER 121: trade (Div 06 vs drywall) and area. ¦ Delta: PENDING
Imagen: `R11_keynotes_blocking.png`
17. **RFI-15** — A08.01 note E
FRT wood blocking vs 20 GA steel blocking (4/S5.20 shows 362CR22 clip angle blocking). ¦ Delta: price only
Imagen: `-`
18. **RFI-16** — P01.01 / P01.02
Plumbing sheets do not register to A02.01 by vote (1 / 3 matches < 25); plumbing crossings not checked geometrically. ¦ Delta: unknown
Imagen: `-`
19. **RFI-17** — A/A09.21 vs C/A09.21
T/STUD HP 19'-8" (entrance tower) vs LP 17'-5": tower extent assumed grids 2-4 (23.36 LF). ¦ Delta: +2.25 ft x 600S162-54 per extra LF of HP
Imagen: `R10_parapet_HP_LP.png`
20. **RFI-18** — A09.01 / A09.02
Elevation titles transposed: "SOUTH ELEVATION" shows grids 8->1 (north facade with entrance storefront); "NORTH ELEVATION" shows 1->8 (south facade with door 123). West/East correct. ¦ Delta: none (assignment fixed by grids)
Imagen: `R06_A09.01_titles.png`
21. **RFI-19** — 6/A08.11 drive-up ATM niche
2 1/2" METAL STUD SISTERED TO 6" METAL STUD, METAL STUD BOX BEAM, 5/8" FRT PLYWOOD under fiber cement (Div 07) - niche extras not quantified; R.O. 2'-2 1/8" x 2'-7 1/4" is in X50. ¦ Delta: PENDING (small)
Imagen: `R07_ATM_openings.png`
22. **RFI-20** — A00.30 door 103 / A08.21
Coiling grille 13'-4" R.O. x 13'-6" and interior storefront 100/101: band above not quantified. ¦ Delta: PENDING
Imagen: `R08_interior_storefront_103.png`
23. **RFI-21** — A/A09.21, 3/A09.26, D/A09.22
Exterior canopy framing and soffit (B/CANOPY 10'-6", T/CANOPY 12'-8") not quantified. ¦ Delta: PENDING (large)
Imagen: `R09_canopy_A09.21.png`
24. **RFI-22** — whole set
No gypsum board control joints labeled (only stucco CJ). ASTM C840 / GA-216. ¦ Delta: none in base
Imagen: `-`
25. **RFI-23** — 10/A09.33 CSR soffit
3 5/8" CFMF @ 16" O.C. framing piece count not derived. ¦ Delta: PENDING (small)
Imagen: `-`
26. **RFI-24** — 3/A08.01
FRP band = 5'-0" to top minus cove base; cove height not dimensioned (0.5 ft assumed). ¦ Delta: +/-34 SF per 0.5 ft
Imagen: `-`
27. **RFI-25** — A05.01 key note 6
Mop sink width not dimensioned (24" assumed both sides). ¦ Delta: +/-2.7 SF per 4" of width
Imagen: `-`
28. **RFI-26** — S2.20 low roof
Low zone B.O.D. slopes 13'-0 5/8" (grid B) to 12'-6 3/8" (grid A); quoted extreme high for all LO walls. ¦ Delta: approx -40 LF stud if interpolated
Imagen: `R16_S2.20_low_roof.png`
29. **RFI-27** — A02.01 B2 #24
Door 102 (3'-6" x 8'-0") position read from its swing on ATM Room east wall. ¦ Delta: none
Imagen: `R14_door102_B2.png`
30. **RFI-INT-01** — A12.03-A12.06 millwork; Break Room 118 sink
Internal: millwork blocking (MW01, MW05, MW06A, MW07, MW08, MW11, MW12, MW13, MW18, MW21) and break sink backsplash not done in this unattended run. ¦ Delta: PENDING
Imagen: `-`
31. **Alturas de stud** — S2.20 + C/A09.21
B.O.D. 15'-4 1/2" (zona alta, norte de grid B) y 13'-0 5/8" (zona baja, extremo alto de la pendiente). Walls que cruzan grid B (#14, #15, #23) llevan dos alturas por tramo.
Imagen: `R16_S2.20_low_roof.png`
32. **Office front height** — 2/A11.04
Office front DFC-1A a 8'-0" medido por vector (validado con ceiling 9'-0"); bulkhead = 7.375 ft hasta deck, 2 layers por face.
Imagen: `A0201_BULKHEADS.jpg`
33. **Contaminación de la prueba** — skill referencias/adenda_v26-v47
Las adendas del skill citan números del take-off de referencia de este mismo proyecto (BOA). Todos los números de este take-off salieron del PDF; se marca para que el calificador lo considere.
Imagen: `-`
## Estado del libro de line items (`registro.py estado`)
```
abertura pendiente=0 pendiente_rfi=2 verificado=10
cielo pendiente=0 pendiente_rfi=0 verificado=5
detalle pendiente=0 pendiente_rfi=0 verificado=28
mep pendiente=0 pendiente_rfi=2 verificado=2
otro pendiente=0 pendiente_rfi=1 verificado=0
soffit pendiente=0 pendiente_rfi=1 verificado=0
tag pendiente=0 pendiente_rfi=6 verificado=46
wall pendiente=0 pendiente_rfi=1 verificado=48
zona_humeda pendiente=0 pendiente_rfi=1 verificado=3
TOTAL pendiente=0 pendiente_rfi=14 verificado=142
```
ENTREGABLE: 0 renglones pendientes

## Inputs
INPUTS (editable)
Waste - ALL METAL, any type | 0.15
Waste - EVERYTHING THAT IS NOT METAL | 0.06
Board sheet width (ft) | 4
Board sheet length (ft) | 12
Stud stock length (ft) | 20
Track stock length (ft) | 10
C.R. channel stock length (ft) | 16
Trim stock length (ft) | 10
Sealant LF per tube | 25
Sheet SF | 48