## Inputs
Bank of America - Broomfield, CO (CO1-111) ¦ METAL FRAMING & DRYWALL TAKEOFF
Bid set: boa_SIN_MARKUPS.pdf (Drive 11IXNHfdM94K8kwL1RHo8clIoTQbezVBp) · 2026-10-17 · Edit ONLY the yellow cells.
PARAMETER | VALUE | NOTE / SOURCE
Waste - ALL METAL, any type | 0.15 | Estimator standing rule: 15% on everything that is metal.
Waste - EVERYTHING THAT IS NOT METAL | 0.06 | Estimator standing rule: same figure as board.
Board sheet width (ft) | 4 | Sheet size is a parameter; buy the size that wastes least.
Board sheet length (ft) | 12 | Change it and every sheet count re-rounds.
SF per board sheet | 48 | Width x length.
Stud stock length (ft) | 20 | Stud, header, framed opening and stud blocking: sticks.
Track stock length (ft) | 10 | Track, sill track and purlin: runs.
Floor plan scale (pt/ft) | n/a | Project value (canon constants).
B.O. Deck (ft) | n/a | Project value (canon constants).
T.O. Parapet (ft) | n/a | Project value (canon constants).
Sealant coverage (LF per tube) | 25 | Sealant yield per tube - set your supplier's figure.
C.R. channel stock length (ft) | 16 | 1-1/2" cold-rolled channel (bracing, carrying channel).
Hat / furring channel stock (ft) | 12 | 7/8" hat furring channel.
Trim stick length (ft) | 10 | Corner bead, casing bead, shadow molding, PVC trim.
Hanger wire purchase | continuous coil (LF) | Bought by LF from a continuous coil; the hanger count goes on its own PCS row.
Drywall screws per SF of board | 1.2 | YIELD (GA-216 field / perimeter spacing).
Framing screws per stud piece | 4 | YIELD: 2 per stud-to-track connection, each end.
Power-driven pin spacing (ft) | 1 | YIELD: bottom track on slab, interior walls.
Joint compound (lb per SF) | 0.072 | YIELD: 72 lb per 1,000 SF, level 4 (estimator criterion).
Joint tape (LF per SF) | 0.37 | YIELD: 370 LF per 1,000 SF.
Expansion anchor spacing (ft) | 0.6667 | YIELD: exterior bottom track on slab.

## Partition Takeoff
ORGANIZED PARTITION TAKEOFF - Bank of America - Broomfield, CO (CO1-111)
Grouped by partition type. Every row cites its DETAIL/SHEET and its status.
Partition / Scope | Wall # | Length (LF) | Height (FT) | Layers | Stud Size | Stud O.C. (in) | Board (SF) | Location | Source (DETAIL/SHEET) | Status
TYPE G1
G1 #G1-01 - 105 / 106 | G1-01 | 11.771 | 15.375 | 4 | 1-5/8" | 16 | 723.92 | 105 / 106 | 5/A12.01 | [CONFIRMED]
G1 #G1-S1 - 109 / 103 | G1-S1 | 1.173 | 15.375 | 4 | 1-5/8" | 16 | 72.14 | 109 / 103 | 5/A12.01 | [DERIVED]
G1 #G1-S2 - 109 / 110 / 103 | G1-S2 | 3.84 | 15.375 | 6 | 1-5/8" | 16 | 220.57 | 109 / 110 / 103 | 5/A12.01 | [DERIVED]
G1 #G1-S3 - 110 / 103 | G1-S3 | 3.727 | 15.375 | 4 | 1-5/8" | 16 | 201.73 | 110 / 103 | 5/A12.01 | [DERIVED]
TYPE G
G #G-01 - 106 / 107 | G-01 | 11.771 | 15.375 | 4 | 1-5/8" | 16 | 723.92 | 106 / 107 | 5/A12.01 | [CONFIRMED]
G #G-02 - 107 / 108 | G-02 | 11.771 | 15.375 | 4 | 1-5/8" | 16 | 723.92 | 107 / 108 | 5/A12.01 | [CONFIRMED]
G #G-03+G-S5 - 108 / 116 + 103 / 108 (incl. jog G-S5 0.973 LF) | G-03+G-S5 | 11.046 | 15.375 | 4 | 1-5/8" | 16 | 679.32 | 108 / 116 + 103 / 108 (incl. jog G-S5 0.973 LF) | 5/A12.01 | [DERIVED]
G #G-S1 - 103 / 105 | G-S1 | 2.42 | 14.383 | 4 | 1-5/8" | 16 | 148.82 | 103 / 105 | 5/A12.01 | [DERIVED]
G #G-S2 - 103 / 106 | G-S2 | 3.467 | 14.383 | 4 | 1-5/8" | 16 | 213.22 | 103 / 106 | 5/A12.01 | [DERIVED]
G #G-S3 - 103 / 107 | G-S3 | 3.253 | 15.375 | 4 | 1-5/8" | 16 | 200.06 | 103 / 107 | 5/A12.01 | [DERIVED]
G #G-S4 - 103 / 108 | G-S4 | 3.253 | 14.225 | 4 | 1-5/8" | 16 | 200.06 | 103 / 108 | 5/A12.01 | [DERIVED]
G #G-04 - 102 / 109 | G-04 | 15.646 | 15.375 | 4 | 1-5/8" | 16 | 838.64 | 102 / 109 | 5/A12.01 | [CONFIRMED]
G #G-06 - 109 / 110 | G-06 | 11.625 | 15.375 | 4 | 1-5/8" | 16 | 714.94 | 109 / 110 | 5/A12.01 | [CONFIRMED]
G #G-05 - 110 / 114 | G-05 | 11.625 | 15.375 | 4 | 1-5/8" | 16 | 714.94 | 110 / 114 | 5/A12.01 | [CONFIRMED]
TYPE B2K
B2K #B2K-01 - 108 / 103 | B2K-01 | 1.693 | 15.375 | 2 | 6" | 24 | 52.06 | 108 / 103 | 4/A12.01 | [DERIVED]
TYPE A1K
A1K #A1K-01 - 116 / 103 | A1K-01 | 3.413 | 15.375 | 2 | 3-5/8" | 24 | 104.94 | 116 / 103 | 4/A12.01 | [DERIVED]
A1K #A1K-02 - 116 / 103 | A1K-02 | 3.413 | 12.939 | 2 | 3-5/8" | 24 | 88.32 | 116 / 103 | 4/A12.01 | [DERIVED]
A1K #A1K-03 - 118 / 103 | A1K-03 | 2.24 | 12.927 | 2 | 3-5/8" | 24 | 57.92 | 118 / 103 | 4/A12.01 | [DERIVED]
TYPE B2
B2 #B2-01 - 102 / 103 | B2-01 | 5.487 | 15.375 | 2 | 6" | 16 | 168.72 | 102 / 103 | 1/A12.01 | [DERIVED]
B2 #B2-02 - 114 / 111 | B2-02 | 5.153 | 15.375 | 2 | 6" | 16 | 158.46 | 114 / 111 | 1/A12.01 | [DERIVED]
B2 #B2-03 - 113 / 117 / 115 / 111 | B2-03 | 15.787 | 12.865 | 4 | 6" | 16 | 395.7 | 113 / 117 / 115 / 111 | 1/A12.01 | [DERIVED]
B2 #B2-04 - 118 / 116 / 119 | B2-04 | 15.073 | 11.709 | 3 | 6" | 16 | 382.18 | 118 / 116 / 119 | 1/A12.01 | [DERIVED]
TYPE F
F #F-01 - 101 / 102 | F-01 | 18.067 | 15.375 | 2 | 3-5/8" | 16 | 343.27 | 101 / 102 | 12/A12.01 | [DERIVED]
TYPE C1
C1 #C1-01 - 114 | C1-01 | 10.08 | 12.926 | 1 | 3-5/8" | 16 | 130.29 | 114 | 6/A12.01 | [DERIVED]
C1 #C1-02 - 113 | C1-02 | 10.08 | 12.896 | 1 | 3-5/8" | 16 | 129.99 | 113 | 6/A12.01 | [DERIVED]
C1 #C1-03 - 103 | C1-03 | 9.293 | 15.375 | 1 | 3-5/8" | 16 | 142.88 | 103 | 6/A12.01 | [DERIVED]
C1 #C1-04 - 116 | C1-04 | 2.98 | 12.93 | 1 | 3-5/8" | 16 | 38.53 | 116 | 6/A12.01 | [DERIVED]
C1 #PIER-NW - 100 | PIER-NW | 2.54 | 15.375 | 1 | 6" | 16 | 30.75 | 100 | 1/A09.25 | [DERIVED]
C1 #PIER-NE - 100 | PIER-NE | 2.587 | 15.375 | 1 | 6" | 16 | 36.84 | 100 | 2/A09.25 | [DERIVED]
C1 #GBOX-N - 101 | GBOX-N | 4 | 15.375 | 1 | 3-5/8" | 16 | 61.5 | 101 | 3/A08.21 | [CONFIRMED]
C1 #GBOX-S - 101 | GBOX-S | 4 | 15.375 | 1 | 3-5/8" | 16 | 61.5 | 101 | 3/A08.21 | [CONFIRMED]
TYPE A1
A1 #A1-01 - 114 / 113 / 111 | A1-01 | 4.887 | 11.816 | 3 | 3-5/8" | 16 | 71.7 | 114 / 113 / 111 | 3/A12.01 | [DERIVED]
A1 #A1-02 - 114 / 111 | A1-02 | 1.3 | 12.958 | 2 | 3-5/8" | 16 | 23.4 | 114 / 111 | 3/A12.01 | [DERIVED]
A1 #A1-03 - 111 / 113 | A1-03 | 1.3 | 12.865 | 2 | 3-5/8" | 16 | 23.4 | 111 / 113 | 3/A12.01 | [DERIVED]
A1 #A1-04 - 111 / 122 / 118 / 120 / 121 | A1-04 | 24.427 | 11.901 | 5 | 3-5/8" | 16 | 482.85 | 111 / 122 / 118 / 120 / 121 | 3/A12.01 | [DERIVED]
A1 #A1-05 - 103 / 122 | A1-05 | 16.42 | 15.375 | 2 | 3-5/8" | 16 | 344.82 | 103 / 122 | 3/A12.01 | [DERIVED]
A1 #A1-06 - 103 / 122 | A1-06 | 3.127 | 15.375 | 2 | 3-5/8" | 16 | 65.66 | 103 / 122 | 3/A12.01 | [DERIVED]
A1 #A1-07 - 103 / 122 | A1-07 | 2.02 | 15.375 | 2 | 3-5/8" | 16 | 42.42 | 103 / 122 | 3/A12.01 | [DERIVED]
A1 #A1-08 - 122 / 118 | A1-08 | 15.427 | 12.971 | 2 | 3-5/8" | 16 | 277.68 | 122 / 118 | 3/A12.01 | [DERIVED]
A1 #A1-09 - 118 / 103 | A1-09 | 2.14 | 11.821 | 2 | 3-5/8" | 16 | 44.94 | 118 / 103 | 3/A12.01 | [DERIVED]
A1 #A1-12 - 103 / 111 | A1-12 | 5 | 15.375 | 2 | 3-5/8" | 16 | 105 | 103 / 111 | 3/A12.01 | [DERIVED]
A1 #A1-10 - 103 / 118 | A1-10 | 1.3 | 12.927 | 2 | 3-5/8" | 16 | 27.3 | 103 / 118 | 3/A12.01 | [DERIVED]
A1 #A1-11 - 116 / 119 | A1-11 | 11.667 | 12.775 | 2 | 3-5/8" | 16 | 215.84 | 116 / 119 | 3/A12.01 | [CONFIRMED]
TYPE B
B #B-01 - 113 / 112 / 117 | B-01 | 11.667 | 12.752 | 3 | 3-5/8" | 16 | 293.22 | 113 / 112 / 117 | 1/A12.01 | [CONFIRMED]
B #B-02 - 112 / 117 | B-02 | 3.5 | 12.743 | 2 | 3-5/8" | 16 | 89.2 | 112 / 117 | 1/A12.01 | [DERIVED]
B #B-03 - 112 / 117 / 115 | B-03 | 11.733 | 12.671 | 3 | 3-5/8" | 16 | 292.2 | 112 / 117 / 115 | 1/A12.01 | [DERIVED]
B #B-04 - 118 / 120 | B-04 | 9.987 | 12.831 | 2 | 3-5/8" | 16 | 256.28 | 118 / 120 | 1/A12.01 | [DERIVED]
B #B-05 - 120 / 121 | B-05 | 9.583 | 12.703 | 2 | 3-5/8" | 16 | 243.46 | 120 / 121 | 1/A12.01 | [CONFIRMED]
B #B-06 - 120 / 121 / 118 | B-06 | 13.74 | 12.823 | 3 | 3-5/8" | 16 | 347.16 | 120 / 121 / 118 | 1/A12.01 | [DERIVED]
TYPE A5
A5 #A5-01 - 103 / 122 | A5-01 | 11.967 | 15.375 | 2 | 6" | 16 | 251.3 | 103 / 122 | 3/A12.01 | [DERIVED]
A5 #A5-02 - 122 / 103 | A5-02 | 19 | 14.225 | 2 | 6" | 16 | 399 | 122 / 103 | 3/A12.01 | [CONFIRMED]
A5 #A5-03 - 118 / 116 | A5-03 | 3.287 | 11.776 | 2 | 6" | 16 | 60.81 | 118 / 116 | 3/A12.01 | [DERIVED]
TYPE EXT-6CFMF
EXT-6CFMF #EXT-8N+EXT-8S - 105-108,116 + 116,119 | EXT-8N+EXT-8S | 75.334 | 13.551 | 1 | 6" | 16 | 1100.54 | 105-108,116 + 116,119 | C/A09.21 | [DERIVED]
EXT-6CFMF #EXT-A - 115,111,121,118,119 | EXT-A | 51.733 | 11.065 | 1 | 6" | 16 | 648.73 | 115,111,121,118,119 | C/A09.21 | [DERIVED]
EXT-6CFMF #EXT-3N+EXT-3S - 109,110 + 114,113,112,115 | EXT-3N+EXT-3S | 47.414 | 12.937 | 1 | 6" | 16 | 671.27 | 109,110 + 114,113,112,115 | C/A09.21 | [DERIVED]
EXT-6CFMF #EXT-2 - 101,102 | EXT-2 | 20.907 | 14.067 | 1 | 6" | 16 | 321.45 | 101,102 | C/A09.21 | [DERIVED]
EXT-6CFMF #EXT-D - EXT-D | EXT-D | 3.351 | 14.067 | 0 | 6" | 16 | 0 | EXT-D | C/A09.21 | [DERIVED]
EXT-6CFMF #EXT-FN - 105 | EXT-FN | 12.64 | 14.358 | 1 | 6" | 16 | 194.34 | 105 | C/A09.21 | [DERIVED]
TYPE CANOPY-COL
CANOPY-COL #CCOL-G - CCOL-G | CCOL-G | 5.667 | 10.5 | 0 | 3-5/8" | 16 | 0 | CCOL-G | 5/A09.25 | [CONFIRMED]
CANOPY-COL #CCOL-E4 - CCOL-E4 | CCOL-E4 | 5.667 | 10.5 | 0 | 3-5/8" | 16 | 0 | CCOL-E4 | 5/A09.25 | [CONFIRMED]
CANOPY-COL #CCOL-C5 - CCOL-C5 | CCOL-C5 | 5.667 | 10.5 | 0 | 3-5/8" | 16 | 0 | CCOL-C5 | 5/A09.25 | [CONFIRMED]
CANOPY-COL #CCOL-B2 - CCOL-B2 | CCOL-B2 | 5.667 | 10.5 | 0 | 3-5/8" | 16 | 0 | CCOL-B2 | 5/A09.25 | [CONFIRMED]
TYPE EXT-PARAPET
EXT-PARAPET #PAR-2T+PAR-2 - PAR-2T + PAR-2 | PAR-2T+PAR-2 | 30.21 | 2.174 | 0 | 6" parapet | 16 | 0 | PAR-2T + PAR-2 | 11/S5.10 | [DERIVED]
EXT-PARAPET #PAR-D - PAR-D | PAR-D | 3.9 | 2.042 | 0 | 6" parapet | 16 | 0 | PAR-D | 11/S5.10 | [DERIVED]
EXT-PARAPET #PAR-3N+PAR-3S - PAR-3N + PAR-3S | PAR-3N+PAR-3S | 47.372 | 3.411 | 0 | 6" parapet | 16 | 0 | PAR-3N + PAR-3S | 11/S5.10 | [DERIVED]
EXT-PARAPET #PAR-A - PAR-A | PAR-A | 52.278 | 4.883 | 0 | 6" parapet | 16 | 0 | PAR-A | 11/S5.10 | [DERIVED]
EXT-PARAPET #PAR-8S+PAR-8N - PAR-8S + PAR-8N | PAR-8S+PAR-8N | 76.355 | 2.892 | 0 | 6" parapet | 16 | 0 | PAR-8S + PAR-8N | 11/S5.10 | [DERIVED]
EXT-PARAPET #PAR-F - PAR-F | PAR-F | 39.828 | 2.042 | 0 | 6" parapet | 16 | 0 | PAR-F | 11/S5.10 | [DERIVED]
EXT-PARAPET #PAR-GT - PAR-GT | PAR-GT | 16.35 | 4.292 | 0 | 6" parapet | 16 | 0 | PAR-GT | 11/S5.10 | [DERIVED]
EXT-PARAPET #PAR-4T - PAR-4T | PAR-4T | 1.444 | 4.292 | 0 | 6" parapet | 16 | 0 | PAR-4T | 11/S5.10 | [DERIVED]
TYPE BULKHEAD-G
BULKHEAD-G #BH-105+BH-106+BH-107+BH-108 - 105 / 103 + 106 / 103 + 107 / 103 + 108 / 103 | BH-105+BH-106+BH-107+BH-108 | 30 | 6.262 | 4 | 1-5/8" | 16 | 880 | 105 / 103 + 106 / 103 + 107 / 103 + 108 / 103 | 9/A12.01 | [DERIVED]
BULKHEAD-G #BH-109+BH-110 - 109 / 103 + 110 / 103 | BH-109+BH-110 | 14.5 | 7.333 | 4 | 1-5/8" | 16 | 425.32 | 109 / 103 + 110 / 103 | 9/A12.01 | [DERIVED]
| TOTAL - PARTITIONS | 952.037 |  |  |  |  | 16959.34
TYPE OTHER FRAMING (NOT A PARTITION)
storefront_cripples #SF-G1 - 100 | SF-G1 | 12.563 | 4.692 | 1 | 6" | 16 | 86.37 | 100 | C/A09.21 | [CONFIRMED]
storefront_cripples #SF-G2 - 103 | SF-G2 | 26.25 | 4.983 | 1 | 6" | 16 | 180.47 | 103 | C/A09.21 | [CONFIRMED]
storefront_cripples #SF-W1 - 101 | SF-W1 | 6.5 | 4.692 | 1 | 6" | 16 | 44.69 | 101 | C/A09.21 | [DERIVED]
vestibule_head #VH-1 - 100 / 101 | VH-1 | 15.638 | 5.375 | 2 | 3-5/8" | 16 | 168.1 | 100 / 101 | 4/A12.10 | [DERIVED]
vestibule_head #VH-2 - 100 / 103 | VH-2 | 6.364 | 5.375 | 2 | 3-5/8" | 16 | 68.42 | 100 / 103 | 4/A12.10 | [DERIVED]
grille_head #GRILLE-HEAD - 101 / 103 | GRILLE-HEAD | 13.333 | 1.5 | 2 | 2-1/2" | 16 | 40 | 101 / 103 | 4/A08.21 | [CONFIRMED]
roof_step #RS-1 - RS-1 | RS-1 | 52.278 | 2.323 | 0 | 3-5/8" | 16 | 0 | RS-1 | 4/A02.02 | [DERIVED]
roof_step #RS-2 - rooms south of B | RS-2 | 52.278 | 4.052 | 1 | 3-5/8" | 16 | 211.83 | rooms south of B | 4/A02.02 | [DERIVED]
roof_step #RS-3 - rooms north of B | RS-3 | 52.278 | 6.375 | 1 | 3-5/8" | 16 | 333.27 | rooms north of B | 4/A02.02 | [DERIVED]
soffit_side #CSR-W - 103 | CSR-W | 12.013 | 7.375 | 1 | 3-5/8" | 16 | 48.05 | 103 | 10/A09.33 | [DERIVED]
soffit_side #CSR-E - 116 | CSR-E | 12.013 | 7.375 | 1 | 3-5/8" | 16 | 18.02 | 116 | 10/A09.33 | [DERIVED]
fascia_box #FASCIA-G - FASCIA-G | FASCIA-G | 78.161 | 1.864 | 0 | 3-5/8" canopy | 16 | 0 | FASCIA-G | A04.01 canopy fascia vector; 3/A09.26 SECTION DETAIL @ ENTRANCE CANOPY; A04.01 | [DERIVED]
fascia_box #FASCIA-1 - FASCIA-1 | FASCIA-1 | 78.44 | 1.864 | 0 | 3-5/8" canopy | 16 | 0 | FASCIA-1 | A04.01 canopy fascia vector; 15/A09.27, 16/A09.27 DRIVE UP CANOPY; A04.01 | [DERIVED]
fascia_box #FASCIA-8 - FASCIA-8 | FASCIA-8 | 55.578 | 1.864 | 0 | 3-5/8" canopy | 16 | 0 | FASCIA-8 | A04.01 canopy fascia vector; 7/A09.26 SECTION DETAIL @ SIDE CANOPY; A04.01 | [DERIVED]
fascia_box #FASCIA-A - FASCIA-A | FASCIA-A | 29 | 1.864 | 0 | 3-5/8" canopy | 16 | 0 | FASCIA-A | A04.01 canopy fascia vector; 7/A09.26 SIM (canopy door 123); A04.01 | [DERIVED]

## Material Summary
MATERIAL SUMMARY - NET / WASTE / PURCHASE
Waste lives HERE, in its own column, applied ONCE: Pieces = ROUNDUP(Net x (1 + waste) / stock). Every stock length, coverage and yield is an Inputs cell.
Material | Unit | Net | Waste % | Waste | Purchase | Selling unit | Pieces to buy | Where it comes from | Yield check (live formula)
6" metal stud 600S162-54 / 600S137-33 (exterior CFMF) | LF | 4144.73 | 0.15 | 621.7095 | 4766.4395 | stick 20 ft | 239 | familias_out.json '6" stud (all gauges)'; S1.11 note 5; 7/S5.20; J/A09.23
3-5/8" metal stud 362S137-33 (A1K / B2K: 14 ga per 4/A12.01) | LF | 6953.16 | 0.15 | 1042.974 | 7996.134 | stick 20 ft | 400 | familias_out.json '3-5/8" stud (all gauges)'; 3/A12.01; 1/A12.01; 12/A12.01; 7/S5.20
1-5/8" metal stud (double row, type G / G1) | LF | 4031.14 | 0.15 | 604.671 | 4635.811 | stick 20 ft | 232 | familias_out.json '1-5/8" stud'; 5/A12.01
6" parapet stud 600S162-54 @16" | LF | 930.82 | 0.15 | 139.623 | 1070.443 | stick 20 ft | 54 | familias_out.json '6" parapet stud'; 11/S5.10; 4/A09.26
Bottom track (all sizes) | LF | 1343.74 | 0.15 | 201.561 | 1545.301 | run 10 ft | 155 | familias_out.json 'bottom track (all)'; 1/A12.01; 3/A12.01; 7/S5.20
Top / deflection track (all sizes, slip track) | LF | 1343.74 | 0.15 | 201.561 | 1545.301 | run 10 ft | 155 | familias_out.json 'top / deflection track (all)'; 1/A12.01; 3/A12.01; 10/S5.10
Track at ceilings / soffits | LF | 1379.1 | 0.15 | 206.865 | 1585.965 | run 10 ft | 159 | familias_out.json 'ceiling / soffit track'; 7/A09.33; 10/A09.33; 7/A09.26
Bracing C.R. channel 1-1/2" @ 48" | LF | 2471.64 | 0.15 | 370.746 | 2842.386 | C.R. channel 16 ft | 178 | familias_out.json 'bracing C.R. channel'; F/S5.20
Purlin (track to deck) | LF | 348.81 | 0.15 | 52.3215 | 401.1315 | run 10 ft | 41 | familias_out.json 'purlin (track to deck)'; 10/S5.10; 1/A12.01
Header / box beam (track and stud pieces) | LF | 741.2 | 0.15 | 111.18 | 852.38 | stick 20 ft | 43 | familias_out.json 'header / box beam'; 7/S5.20; 6/A08.11; 8/A12.01
Sill track | LF | 119.09 | 0.15 | 17.8635 | 136.9535 | run 10 ft | 14 | familias_out.json 'sill track'; 2/S5.20
Furring channel 7/8" @ 16" (GB ceilings) | LF | 776.22 | 0.15 | 116.433 | 892.653 | hat channel 12 ft | 75 | familias_out.json 'furring channel'; A04.01; 10/A09.33
Carrying channel 1-1/2" C.R. @ 48" (GB ceilings) | LF | 307.79 | 0.15 | 46.1685 | 353.9585 | C.R. channel 16 ft | 23 | familias_out.json 'carrying channel'; A04.01; 3/A09.33
Hanger wire 12 ga | LF | 504.79 | 0.15 | 75.7185 | 580.5085 | continuous coil (LF) | 581 | familias_out.json 'hanger wire'; 3/A09.33
5/8" gypsum board, regular (walls + ceilings) | SF | 18881.67 | 0.06 | 1132.9002 | 20014.5702 | 4x12 ft sheet | 417 | familias_out.json '5/8" gyp board regular (walls + ceilings)'; 1/A12.01; 3/A12.01; 5/A12.01; A04.01
5/8" gypsum board, moisture resistant | SF | 260.29 | 0.06 | 15.6174 | 275.9074 | 4x12 ft sheet | 6 | familias_out.json '5/8" gyp MOISTURE RESISTANT'; A-D/A08.01
Ballistic panel UL 752 (fiberglass) 3/8" | SF | 86.07 | 0.06 | 5.1642 | 91.2342 | 4x8 ft sheet | 3 | familias_out.json 'ballistic panel'; 4/A12.01
3/8" gyp board (teller line customer side) | SF | 65.55 | 0.06 | 3.933 | 69.483 | 4x8 ft sheet | 3 | familias_out.json '3/8" gyp board'; 4/A12.01
5/8" glass mat sheathing (band / soffit) | SF | 477.09 | 0.06 | 28.6254 | 505.7154 | 4x8 ft sheet | 16 | familias_out.json '5/8" glass mat sheathing'; A09.01; 7/A09.26
5/8" exterior gyp sheathing (parapet roof side) | SF | 869.01 | 0.06 | 52.1406 | 921.1506 | 4x8 ft sheet | 29 | familias_out.json '5/8" EXTERIOR gyp sheathing'; 4/A09.26; A/A09.21
FRT blocking (2x wood) | LF | 687.99 | 0.06 | 41.2794 | 729.2694 | LF | 730 | familias_out.json 'FRT blocking'; 8/A12.01; A02.01
Metal stud blocking 362CR / stud blocking | LF | 776.06 | 0.15 | 116.409 | 892.469 | stick 20 ft | 45 | familias_out.json 'metal stud blocking (362CR / STUD BLOCKING)'; 4/S5.20
Metal trim (corner bead, casing bead, shadow molding) | LF | 1184.44 | 0.15 | 177.666 | 1362.106 | trim stick 10 ft | 137 | familias_out.json 'metal trim (corner bead, casing, shadow molding)'; 10/A09.33; 4/A12.01
Cement board 1/2" (tile backer) | SF | 31.8 | 0.06 | 1.908 | 33.708 | 3x5 ft sheet | 3 | familias_out.json 'cement board'; A-D/A08.01
FRP panel | SF | 334.02 | 0.06 | 20.0412 | 354.0612 | 4x8 ft sheet | 12 | familias_out.json 'FRP'; A-D/A08.01; 5/A08.01
Acoustical sealant | LF | 1008.03 | 0.06 | 60.4818 | 1068.5118 | tube (25 LF per tube) | 43 | familias_out.json 'acoustical sealant'; 1/A12.01; 3/A12.01; 5/A12.01
Framed openings MEP (track / stud framing at fixtures and slot diffusers) | LF | 940.79 | 0.15 | 141.1185 | 1081.9085 | stick 20 ft | 55 | fo_out.json framed_openings.py 'framed openings MEP'; E00.01; E02.01; M03.01; M01.01
5/8" exterior grade FRT plywood (canopy soffits, fascia, column wraps) | SF | 2278.85 | 0.06 | 136.731 | 2415.581 | 4x12 ft sheet (Inputs) | 51 | familias_out.json FRT plywood by material; C/A09.21; 7/A09.26; 12/A12.01
5/8" FRT plywood bonded to 2-1/2" polyiso (exterior sheathing / nailbase) | SF | 3782.24 | 0.06 | 226.9344 | 4009.1744 | 4x12 ft sheet (Inputs) | 84 | familias_out.json FRT plywood by material; C/A09.21; 7/A09.26; 12/A12.01
3/4" FRT plywood | SF | 683.21 | 0.06 | 40.9926 | 724.2026 | 4x12 ft sheet (Inputs) | 16 | familias_out.json FRT plywood by material; C/A09.21; 7/A09.26; 12/A12.01
5/8" FRT plywood | SF | 4.78 | 0.06 | 0.2868 | 5.0668 | 4x12 ft sheet (Inputs) | 1 | familias_out.json FRT plywood by material; C/A09.21; 7/A09.26; 12/A12.01
Sealant at base of gypsum (exterior, not acoustical) | LF | 219.94 | 0.06 | 13.1964 | 233.1364 | tube (25 LF per tube) | 10 | familias_out.json acoustical sealant rows 'base of gypsum (exterior)'
Hanger wire 12 ga - hanger count (one per hanger, height per room) | PCS | 108 | 0 | 0 | 108 |  | 108 | familias_out.json hanger_pcs.total_pcs; wire bought on the LF row
Additional head track at openings over 4'-0" wide | LF | 56 | 0.15 | 8.4 | 64.4 | run 10 ft | 7 | accesorios.py [CRITERION]: HEAD TRACK @ NON LOAD BRG: ADD FULL LENGTH ADDL HEAD TRACK @ OPNG > 4'-0"; Estimator user decision #1: R.O. + 1'-4" (8" bearing each side)
Stud reinforcement at MEP penetrations | PCS | 29 | 0 | 0 | 29 | each | 29 | accesorios.py [CRITERION]: 6/S5.20; M01.01 registered sweep (offset dx -572.0 dy 22.0) crossing #0; 6/S5.20; 6/S5.20; M01.01 registered sweep (offset dx -572.0 dy 22.0) crossing #1; 6/S5.20; 6/S5.20; M01.01 registered sweep (offset dx -572.0 dy 22.0) crossing #2; 6/S
Extra framing - sistered stud and furring at the ATM recess | LF | 12.17 | 0.15 | 1.8255 | 13.9955 | stick 20 ft | 1 | accesorios.py [CRITERION]: 6/A08.11 2 1/2" METAL STUD SISTERED TO 6" METAL STUD
2-1/2" CFMF @ 16" O.C. at coiling grille head (4/A08.21) | LF | 4.93 | 0.15 | 0.7395 | 5.6695 | stick 20 ft | 1 | accesorios.py [DERIVED]: 4/A08.21 1'-6" chain
Gypsum board jamb return at openings | SF | 83.41 | 0.06 | 5.0046 | 88.4146 | 4x12 ft sheet (Inputs) | 2 | accesorios.py [CRITERION]: Estimator criterion (return width = 6" stud depth, not dimensioned; RFI with delta at 0.20 ft)
PVC trim - edge trim molding and inside corner molding at the FRP | LF | 213.21 | 0.06 | 12.7926 | 226.0026 | trim stick 10 ft | 23 | accesorios.py [DERIVED]: A-D/A08.01 5'-0" TO TOP OF FRP; A08.01 rectangular room; A05.01 key note 6 FRP 4'-0" AFF WIDTH OF MOP SINK BOTH SIDES; 5/A08.01 (sink width not dimensioned: 2'-0" RFI-16)
Power-driven fasteners and duct sleeves | PCS | 294 | 0 | 0 | 294 | each | 294 | accesorios.py [DERIVED]: Parapet infill: PAFs SPACED AT 12" O.C. MAX to the steel beam; M01.01 registered sweep (offset dx -572.0 dy 22.0) crossing #0; 6/S5.20; M01.01 registered sweep (offset dx -572.0 dy 22.0) crossing #10; 6/S5.20; M01.01 registered sweep (offse
Access panel | PCS | 1 | 0 | 0 | 1 | each | 1 | accesorios.py [CONFIRMED]: A04.01 key note 4
Drywall screws 1-1/4" bugle head | PCS | 23049.01 | 0 | 0 | 23049.01 | each | 23050 | accesorios.py [DERIVED]: Inputs!B20 (Drywall screws per SF of board = 1.2) x 19207.5 SF of board | 23049
Framing screws, pan head self-drilling | PCS | 6908 | 0 | 0 | 6908 | each | 6908 | accesorios.py [DERIVED]: Inputs!B21 (Framing screws per stud piece = 4) x 1727 stud pieces | 6908
Power-driven fasteners, slab pins for the bottom track | PCS | 534.81 | 0 | 0 | 534.81 | each | 535 | accesorios.py [DERIVED]: 534.81 LF of interior bottom track on slab / Inputs!B22 (Power-driven pin spacing (ft) = 1) | 534.81
Expansion anchors Hilti 1/4" Kwik Bolt II, exterior bottom track @ 8" O.C. | PCS | 317.07 | 0 | 0 | 317.07 | each | 318 | accesorios.py [DERIVED]: 211.38 LF of exterior bottom track on slab / Inputs!B25 (Expansion anchor spacing (ft) = 0.6667) | 317.0541
Joint compound, all purpose | LB | 1382.94 | 0 | 0 | 1382.94 | lb | 1383 | accesorios.py [DERIVED]: Inputs!B23 (Joint compound (lb per SF) = 0.072) x 19207.5 SF of board | 1382.94
Joint tape, paper | LF | 7106.78 | 0 | 0 | 7106.78 | LF | 7107 | accesorios.py [DERIVED]: Inputs!B24 (Joint tape (LF per SF) = 0.37) x 19207.5 SF of board | 7106.775
Level 5 finish | SF | 963.22 | 0.06 | 57.7932 | 1021.0132 | SF | 1022 | accesorios.py [DERIVED]: A05.01 WC-18 office 105; A00.40 WC-18 WALL SURFACE TO BE LEVEL 5; A05.01 WC-18 office 106; A00.40 WC-18 WALL SURFACE TO BE LEVEL 5; A05.01 WC-18 office 107; A00.40 WC-18 WALL SURFACE TO BE LEVEL 5; A05.01 WC-18 office 108; A00.40 WC-18 WALL

## Pending Items
RFI | Question / condition | Delta of each alternative
RFI-ACC-additional-head-track | additional head track: openings with their own box (openings_extra) > 4'-0": do they also take the additional head track of 2/S5.20? | 83.15 lf
RFI-ACC-extra-framing-atm | extra framing ATM: DU ATM: ATM recess not fully dimensioned (width CONFIRMED, sistered height DERIVED, furring rows DERIVED) | 4.78 lf
RFI-ACC-gypsum-board-jamb-return | gypsum board jamb return: jamb return width not dimensioned | -50.04 sf
RFI-ACC-slab-pins | slab pins: pin spacing: 12" (interior anchorage) vs 16" (fastener schedule) vs 24" (type K box) | 16in: -133.7 pcs; 24in: -267.4 pcs
RFI-01 | Elevation titles on A09.01 / A09.02 (NORTH / SOUTH) are transposed against the plan (S2.20 note: BUILDING FOOTPRINT MIRRORED NORTH-SOUTH). Take-off follows the grid lines (G = storefront side, A = egress side). Confirm. | 0 LF: identification only, quantities follow the grids
RFI-02 | S1.11 note 5: exterior studs 600S162-54 @ 16" O.C., @ 12" within 6 ft of building corners, vs S5.20 600S137-33. Carried 600S162-54 @ 16" without the @ 12" corner zones. Confirm gauge and corner spacing. | +115 LF to +246 LF 6" stud if @ 12" within 6 ft of building corners (4 to 8+ corners; whole studs x 15.4 ft) [DERIVED]
RFI-03 | GB ceiling suspension is not detailed (A04.01 / A09.33): carried 7/8" furring channel @ 16", 1-1/2" C.R. @ 48", 12 ga hanger wire @ 48". Confirm system. | -226.16 LF furring channel if @ 24" (canon formula per room); carrying direction N-S instead of E-W: +16.1 to +18.6 LF carrying channel
RFI-04 | Bracing C.R. channel carried continuous across openings (literal). Confirm if it stops at openings. | -103.42 LF bracing C.R. channel
RFI-05 | Bottom track: door R.O. not deducted (estimator criterion). Confirm. | -43.83 LF bottom track if door R.O. deducted (canon.py); -50.50 LF if openings 111 and 118A (openings_extra) are also deducted
RFI-06 | Storefront heads (lobby G, vestibule G, vestibule west): S2.20 HSS9x5x5/8 (LLV) lintels = steel by others; no metal-stud header carried. Confirm. | 0 LF: steel by others, no metal-frame quantity
RFI-07 | R-11C / R-11CE linear gyp slot (room 104): E00.01 description 12' vs catalog code WH-20'-0". Carried 12' (= drawn on A04.01). | +64.0 LF framed openings MEP if 20'
RFI-08 | UU1-UU6 linear recessed fixtures in canopy soffits: catalog LSR-WET-2.5 vs drawn width 5" to 6" (E02.01). Carried drawn width. UU5 50' is longer than the east canopy soffit (48.05 ft). | -9.13 LF framed openings MEP at 2-1/2" width; >= -3.9 LF if UU5 is limited to the soffit length
RFI-09 | UU1-UU6 canopy soffit fixtures carried as framed openings in the canopy soffit framing (PT-4 on 5/8" FRT plywood on studs, 7/A09.26). Confirm the opening framing is by the framing contractor. | -703.88 LF framed openings MEP if by others
RFI-10 | 6/A08.11 DU ATM: furring under the fiber cement panel carried in 'extra framing ATM' (accesorios.py rule) although it is cladding substrate (60.4). Confirm who furnishes it. | -4.35 LF extra framing ATM (2 rows x 2.177 ft)
RFI-11 | Cladding substrate (7/8" hat channel at EPS-5 metal panel A09.25 / A09.27, self-furring metal lath at PT-3 stucco A09.31, PT-4 stucco at canopy soffits with control joints and SA-4 vents A04.01 / 16/A09.27) EXCLUDED from metal frame / drywall scope (alcance_filtro.py). Confirm. | n/a: excluded scope, not measured (quantity to be taken only if the RFI answer includes it)
RFI-12 | E26 partial beams: G1-01, G-S3, G-04, G-06, B-01, B-03 are only partly under a beam (28-55 %); studs carried to deck full length. Confirm. | -29.9 LF stud if studs stop under the beam where covered (recomputed per beam)
RFI-13 | MEP penetrations: 3/4" domestic water (P01.02) carried with no plate (<= 1" centered in web, 6/S5.20); MEP-20 duct crosses above door 119 header; MEP-30 (4" OD at EXT-8N) and MEP-31 (2" ST at G-01) added where the CAD line is cut at a fitting. Confirm. | -2 PCS without MEP-30/31; +3 PCS if water lines take plates; -4 PCS if the 4 storm lines to exterior CO run below grade (check A09.02); +11 PCS if double-row G/G1 walls take one plate per row; -20 PCS if ducts pass between studs without cutting one (criterion carried: 1 stud cut per duct)
RFI-14 | Fire-rated 3/4" FRT plywood backboards ELEC 120 / NER 121: carried full wall width per 1, 2, 3, 5/A11.03 (32.39 LF x 8'-0"); E02.02 note 29 calls 8'x7'-6" in NER. Confirm height. | -16.2 SF 3/4" FRT plywood if 7'-6" high
RFI-15 | Exterior opening perimeter 3/4" FRT plywood width not dimensioned (11/A09.27, 10/A09.27, 2/A09.26): carried 6". | +115.56 SF FRT plywood per +6" of width (231.11 LF)
RFI-16 | Mop sink FRP (A05.01 key note 6): sink width not dimensioned, carried 2'-0" both sides x 4'-0" AFF. | +4 SF FRP per +6" of sink width
RFI-18 | Roof step RS-2 / RS-3 (9/S5.10): second and third framing rows and their heights not dimensioned; carried 3 rows. | -41 LF stud per row removed; +/-41 LF per foot of row height
RFI-19 | FEC-1 recessed fire extinguisher cabinet framing: cabinet size not dimensioned; FEC-2 is a bracket (no framing). | +6.67 LF framing if FEC-1 needs a 24" framed opening
RFI-20 | Office front bulkheads BH-109 / BH-110: base taken from the 7'-6" HOLD clear opening dims (A02.01) and 8'-0 1/2" HOLD (A11.01). Confirm. | +/-2 LF 1-5/8" stud per inch of base height change (approx.)
RFI-21 | PAFs and duct sleeves: 20 duct sleeves carried in the metal frame scope (accesorios.py). Confirm they are not by the mechanical contractor. | -20 PCS duct sleeves if by mechanical
RFI-22 | SOUNDGUARD ISOLATOR by Marinoware between the two stud rows of types G / G1 and office bulkheads (5, 8, 9, 10/A12.01): not carried as a material row (no tool family). Confirm count per stud pair. | +312 EA (2 per stud pair, as drawn); +156 EA minimum (1 per pair)
RFI-23 | A02.01 note C 'PROVIDE BLOCKING FOR ALL EQUIPMENT AND ACCESSORIES MOUNTED ON WALLS': lockers, cork boards, wellness and work room equipment (A11.02, A03.01 key note 24 TV), roof ladder 3/A09.30 not located on elevations. | +39 LF metal stud blocking; +8 LF 2x FRT blocking; +15 SF 3/4" FRT plywood
RFI-24 | Board behind C1 furring (A1-05 behind C1-03, A1K-02 behind C1-04) and G-04 room 109 face over EXT-D: carried boarded (wall finished before furring). Confirm. | -273.7 SF 5/8" gyp board regular if not boarded
RFI-25 | Canopy fascia box (7/A09.26, 3/A09.26, 15/16/A09.27): 5/8" exterior FRT plywood carried on the front face only; the air barrier wraps top and back. | +120.6 SF (top only) to +570 SF (top + back) 5/8" exterior FRT plywood
RFI-26 | ATM plinths 'GC BUILT' (3, 4, 6/A08.11): carpentry not carried (Div 06 / ATM vendor). | +12.8 LF 2x4 FRT; +5.3 LF 4x4 FRT; +30 SF 3/4" FRT plywood if in scope
RFI-27 | Opening perimeter 3/4" FRT plywood: HM door 123 (4/A09.25, 14/A09.27) not in the list; DU ATM perimeter appears in two plywood rows (6/A08.11). | +8.8 SF (door 123); -4.78 SF (DU ATM double)
RFI-28 | Free ends of C1 furring (C1-03, C1-04, 6/A12.01): return board and corner bead not carried. | +37.7 SF 5/8" gyp board; +82 LF corner bead
RFI-29 | Canopy soffit track (corridas CSOF-x) plus the 2 fascia box tracks (7/A09.26): possible double where the joist rim acts as bottom track of the box. | -241.2 LF track at ceilings / soffits if double
RFI-30 | EXT-A grid 6 to 8: S2.20 shows W14x22 over 17.67 LF (W18x35 elsewhere); canon stops all EXT-A studs under W18x35. | +4.7 LF 6" stud (0.333 ft x 14 studs)
RFI-31 | SD / SDR TBDI-10 slot diffusers (M03.01 SIZE SEE DRAWING): framed at slot length 12'-0" / 2'-0"; drawn housing 12.87 / 2.29 ft on M01.01. Confirm with submittal. | +9.3 LF framed openings MEP if framed to the housing
RFI-32 | 7/S5.20 exterior headers: 2-600CSJ18 up to 4'-0" and 2-600CSJ14 up to 8'-0" (GL-2 windows); purchase gauge not split in the header row. | 0 LF: gauge split only
RFI-17 | Office front continuous box beam west (109-110): run carried 18.34 ft from plan vs printed 7'-6" HOLD openings; east 39.973 ft. Confirm extents (8/A12.01). | -8.03 LF header (west) and -23.90 LF header (east) if framed opening by opening instead of continuous runs

## Review Items
# | Item | Sheet + detail | Image
1 | Elevation titles transposed vs plan; quantities follow grids | A09.01; A09.02; S2.20 | A02.01_type_EXT.jpg
2 | Exterior stud gauge / corner spacing S1.11 vs S5.20 (RFI-02) | S1.11; 7/S5.20 | A02.01_type_EXT.jpg
3 | GB ceiling suspension criterion (RFI-03) | A04.01; 3/A09.33 | A04.01_GB_ceilings.jpg
4 | Framed openings MEP: R-11C/CE length, UU width and canopy scope (RFI-07/08/09) | E00.01; E02.01; M03.01 | E02.01_framed_openings_fixtures.jpg
5 | MEP penetrations registered sweep, 31 crossings (RFI-13) | M01.01; P01.01; P01.02; 6/S5.20 | A02.01_MEP_penetrations.jpg
6 | Door bulkheads BH-105..108 under beams (E26) shortened by beam depth | 9/A12.01; S2.20 | A02.01_type_G.jpg
7 | Partial beams over 6 walls carried to deck (RFI-12) | S2.20; 10/S5.10 | A02.01_type_G.jpg
8 | Backboards height 8' (E02.02 note 29) and ELEC 120 extent (RFI-14) | E02.02; A02.01 key note 6 | A02.01_type_A1.jpg

## Scope Checklist
Scope ID | Scope | Status | Note (quantity, NOT APPLICABLE + sheet, or RFI)
ALC-01 | Interior partition framing (studs + tracks) | QUANTIFIED | familias_out.json (canon.py)
ALC-02 | Exterior wall framing (CFMF) | QUANTIFIED | familias_out.json (canon.py)
ALC-03 | Parapet framing | QUANTIFIED | familias_out.json (canon.py)
ALC-04 | Top / deflection and bottom track | QUANTIFIED | familias_out.json (canon.py)
ALC-05 | Headers, sills and jambs at openings | QUANTIFIED | familias_out.json (canon.py)
ALC-06 | Bracing / bridging | QUANTIFIED | familias_out.json (canon.py)
ALC-07 | Gypsum board on walls (layers per type) | QUANTIFIED | familias_out.json (canon.py)
ALC-08 | Moisture / abuse / special board at wet zones | QUANTIFIED | familias_out.json (canon.py)
ALC-09 | Exterior gypsum / glass mat sheathing | QUANTIFIED | familias_out.json (canon.py)
ALC-10 | FRT plywood sheathing / substrate | QUANTIFIED | familias_out.json (canon.py)
ALC-11 | Gypsum board ceilings | QUANTIFIED | familias_out.json (canon.py)
ALC-12 | Ceiling suspension (furring / carrying channel / hanger wire / ceiling track) | QUANTIFIED | familias_out.json (canon.py)
ALC-13 | Soffits and bulkheads (framing + board) | QUANTIFIED | familias_out.json (canon.py)
ALC-14 | Canopy / marquee framing and sheathing | QUANTIFIED | familias_out.json (canon.py)
ALC-15 | Column furring / wraps | QUANTIFIED | Canopy column wraps CCOL-G/E4/C5/B2 and glass boxes GBOX-N/S (5/A09.25)
ALC-16 | Blocking (FRT wood / metal) for millwork and accessories | QUANTIFIED | familias_out.json (canon.py)
ALC-17 | Framed openings (MEP, access panels, diffusers) | QUANTIFIED | framed_openings.py (E02.01 fixtures, M01.01 slot diffusers) + access panel; RFI-07/08/09
ALC-18 | Trim: corner bead, casing bead, control joints, reveals | QUANTIFIED | familias_out.json (canon.py)
ALC-19 | Acoustical sealant / sound attenuation | QUANTIFIED | familias_out.json (canon.py)
ALC-20 | FRP / cement board / tile backer | QUANTIFIED | familias_out.json (canon.py)
ALC-21 | Shaft walls / area separation walls | NOT APPLICABLE | A02.01: no shaft wall or area separation wall shown
ALC-22 | Rated assemblies (UL designs) and their board type | QUANTIFIED | No rated partition assembly on A02.01; fire-rated 3/4" plywood backboards per A02.01 key note 6 and E02.02 note 29 carried in FRT plywood
ALC-23 | Special panels (ballistic, lead-lined, abuse) | QUANTIFIED | Ballistic panel UL 752 per 4/A12.01 (types A1K/B2K)
ALC-24 | Finish level (Level 4 / Level 5) | QUANTIFIED | Level 5 finish per A05.01 / A00.40 (accesorios.py)
ALC-X1 | Cladding substrate (hat channel / metal lath) | RFI | EXCLUDED by alcance_filtro.py; RFI-11
ALC-X26 | batt insulation | NOT APPLICABLE | EXCLUDED (estimator criterion: no insulation)