## Inputs
Bank of America - Broomfield, CO (CO1-111) ¦ METAL FRAMING & DRYWALL TAKEOFF
Bid set: 2025.08.26_CO1-111_Broomfield_PERMIT SET_BID SET.pdf · 2026-10-18 · Edit ONLY the yellow cells.
PARAMETER | VALUE | NOTE / SOURCE
Waste - ALL METAL, any type | 0.15 | Estimator standing rule: 15% on everything that is metal.
Waste - EVERYTHING THAT IS NOT METAL | 0.06 | Estimator standing rule: same figure as board.
Board sheet width (ft) | 4 | Sheet size is a parameter; buy the size that wastes least.
Board sheet length (ft) | 12 | Change it and every sheet count re-rounds.
SF per board sheet | 48 | Width x length.
Stud stock length (ft) | 20 | Stud, header, framed opening and stud blocking: sticks.
Track stock length (ft) | 10 | Track, sill track and purlin: runs.
Floor plan scale (pt/ft) | 18 | Project value (canon constants).
B.O. Deck (ft) | 15.375 | Project value (canon constants).
T.O. Parapet (ft) | n/a | Project value (canon constants).
Sealant coverage (LF per tube) | 25 | Sealant yield per tube - set your supplier's figure.
C.R. channel stock length (ft) | 16 | 1-1/2" cold-rolled channel (bracing, carrying channel).
Hat / furring channel stock (ft) | 12 | 7/8" hat furring channel.
Trim stick length (ft) | 10 | Corner bead, casing bead, shadow molding, PVC trim.
Hanger wire purchase | continuous coil (LF) | Bought by LF from a continuous coil; the hanger count goes on its own PCS row.
Drywall screws per SF of board | 1.875 | YIELD (GA-216 field / perimeter spacing).
Framing screws per stud piece | 4 | YIELD: 2 per stud-to-track connection, each end.
Power-driven pin spacing (ft) | 1 | YIELD: bottom track on slab, interior walls.
Joint compound (lb per SF) | 0.072 | YIELD: 72 lb per 1,000 SF, level 4 (estimator criterion).
Joint tape (LF per SF) | 0.37 | YIELD: 370 LF per 1,000 SF.
Expansion anchor spacing (ft) | 0.6667 | YIELD: exterior bottom track on slab.

## Partition Takeoff
ORGANIZED PARTITION TAKEOFF - Bank of America - Broomfield, CO (CO1-111)
Grouped by partition type. Every row cites its DETAIL/SHEET and its status.
Partition / Scope | Wall # | Length (LF) | Height (FT) | Layers | Stud Size | Stud O.C. (in) | Board (SF) | Location | Source (DETAIL/SHEET) | Status
TYPE EXT-6CFMF
EXT-6CFMF #EX-2 - West wall grid 2: Vestibule 100 / 24 HR Vestibule 101 / ATM Room 102, pier 2 to grid D | EX-2 | 27.411 | 14.358 | 3 | 6" | 16 | 352.94 | West wall grid 2: Vestibule 100 / 24 HR Vestibule 101 / ATM Room 102, pier 2 to grid D | J/A09.23 | [DERIVED]
EXT-6CFMF #EX-3 - Jog on grid D between grids 2 and 3 (ATM Room 102 side; exterior face toward the drive-up canopy) | EX-3 | 3.86 | 14.358 | 1 | 6" | 16 | 59.35 | Jog on grid D between grids 2 and 3 (ATM Room 102 side; exterior face toward the drive-up canopy) | J/A09.23 | [DERIVED]
EXT-6CFMF #EX-4+EX-5 - South wall line F grids 4-7 (Central Zone 103), storefront 26'-3" + South wall line F grids 7-8 (Office 1 ME 105) | EX-4+EX-5 | 38.888 | 14.041 | 1 | 6" | 16 | 374.78 | South wall line F grids 4-7 (Central Zone 103), storefront 26'-3" + South wall line F grids 7-8 (Office 1 ME 105) | C/A09.21 | [DERIVED]
EXT-6CFMF #EX-6+EX-7 - East wall grid 8, F to B (offices 105-108, Cash Window 116) + East wall grid 8, B to A (Cash Window 116, Work Room 119) - low roof | EX-6+EX-7 | 75.334 | 13.551 | 5 | 6" | 16 | 1030.04 | East wall grid 8, F to B (offices 105-108, Cash Window 116) + East wall grid 8, B to A (Cash Window 116, Work Room 119) - low roof | D/A09.22; E/A09.22 | [DERIVED]
EXT-6CFMF #EX-8+EX-9 - North wall grid A, grids 3-6 (Wellness 115, exit corridor door 123, NER 121, Break 118) - low roof + North wall grid A, grids 6-8 (Break 118, Work Room 119) - low roof | EX-8+EX-9 | 51.732 | 11.17 | 4 | 6" | 16 | 621.03 | North wall grid A, grids 3-6 (Wellness 115, exit corridor door 123, NER 121, Break 118) - low roof + North wall grid A, grids 6-8 (Break 118, Work Room 119) - low roof | F/A09.22 | [DERIVED]
EXT-6CFMF #EX-10+EX-11 - West wall grid 3, D to B (offices 109, 110, Women's 114) + West wall grid 3, B to A (restrooms 114/113, Janitor 112, Wellness 115) - low roof | EX-10+EX-11 | 47.417 | 13.075 | 3 | 6" | 16 | 632.81 | West wall grid 3, D to B (offices 109, 110, Women's 114) + West wall grid 3, B to A (restrooms 114/113, Janitor 112, Wellness 115) - low roof | H/A09.23 | [DERIVED]
TYPE C1
C1 #EX-12 - Storefront pier at grid 2 / F-G (NW corner of Vestibule 100): 6" CFMF exterior L + 3-5/8" C1 interior L | EX-12 | 7.25 | 14.358 | 2 | mixed | 16 | 50.23 | Storefront pier at grid 2 / F-G (NW corner of Vestibule 100): 6" CFMF exterior L + 3-5/8" C1 interior L | 1/A09.25 | [DERIVED]
C1 #EX-13 - Storefront pier at grid 4 / F-G (NE corner of Vestibule 100, door 100A): 6" CFMF exterior L + 3-5/8" C1 interior L | EX-13 | 7.208 | 14.358 | 2 | mixed | 16 | 45.62 | Storefront pier at grid 4 / F-G (NE corner of Vestibule 100, door 100A): 6" CFMF exterior L + 3-5/8" C1 interior L | 2/A09.25 | [DERIVED]
C1 #W2-12 - Restroom wet chase, north face (Women's Restroom 114) | W2-12 | 9.973 | 12.923 | 1 | 3-5/8" | 16 | 128.88 | Restroom wet chase, north face (Women's Restroom 114) | 6/A12.01 | [DERIVED]
C1 #W2-13 - Restroom wet chase, south face (Men's Restroom 113) | W2-13 | 9.973 | 12.892 | 1 | 3-5/8" | 16 | 128.57 | Restroom wet chase, south face (Men's Restroom 113) | 6/A12.01 | [DERIVED]
C1 #W2-14 - C1 furring (8" deep) on north face of Calling Cubes 122 A1 wall, facing Waiting 104 (key note 7, 85" display monitor); incl. two 8" end returns (PT3) | W2-14 | 11.333 | 15.375 | 1 | 3-5/8" | 16 | 174.24 | C1 furring (8" deep) on north face of Calling Cubes 122 A1 wall, facing Waiting 104 (key note 7, 85" display monitor); incl. two 8" end returns (PT3) | 6/A12.01 | [CONFIRMED]
C1 #W2-15 - C1 furring box at Future FCAM, south of Cash Window 116 A1K wall (Break Room 118 side) | W2-15 | 2.98 | 12.924 | 1 | 3-5/8" | 16 | 38.51 | C1 furring box at Future FCAM, south of Cash Window 116 A1K wall (Break Room 118 side) | 6/A12.01 | [DERIVED]
C1 #W2-18 - Column enclosure on grid 4 between Vestibule 100 and 24 HR Vestibule 101 | W2-18 | 4 | 15.375 | 1 | 3-5/8" | 16 | 61.5 | Column enclosure on grid 4 between Vestibule 100 and 24 HR Vestibule 101 | 6/A12.01 | [DERIVED]
C1 #W2-19 - Column enclosure at grid 4 / line E (end of F wall and B2 W2-7) | W2-19 | 2.94 | 15.375 | 1 | 3-5/8" | 16 | 45.2 | Column enclosure at grid 4 / line E (end of F wall and B2 W2-7) | 6/A12.01 | [DERIVED]
TYPE CANOPY-COL
CANOPY-COL #EX-14 - Drive-up canopy column wrap, grid 1 / F/G | EX-14 | 5.667 | 10.604 | 0 | 3-5/8" | 16 | 0 | Drive-up canopy column wrap, grid 1 / F/G | 5/A09.25 | [DERIVED]
CANOPY-COL #EX-15 - Drive-up canopy column wrap, grid 1 / E.4 | EX-15 | 5.667 | 10.604 | 0 | 3-5/8" | 16 | 0 | Drive-up canopy column wrap, grid 1 / E.4 | 5/A09.25 | [DERIVED]
CANOPY-COL #EX-16 - Drive-up canopy column wrap, grid 1 / C.5 | EX-16 | 5.667 | 10.604 | 0 | 3-5/8" | 16 | 0 | Drive-up canopy column wrap, grid 1 / C.5 | 5/A09.25 | [DERIVED]
CANOPY-COL #EX-17 - Drive-up canopy column wrap, grid 1 / B.2 | EX-17 | 5.667 | 10.604 | 0 | 3-5/8" | 16 | 0 | Drive-up canopy column wrap, grid 1 / B.2 | 5/A09.25 | [DERIVED]
TYPE EXT-PARAPET
EXT-PARAPET #EX-18 - HP parapet (T.O. PARAPET 2 20'-0") over vestibule front, grid 2 to grid 4 return | EX-18 | 16.354 | 4.292 | 0 | 6" parapet | 16 | 0 | HP parapet (T.O. PARAPET 2 20'-0") over vestibule front, grid 2 to grid 4 return | 4/A09.26 | [DERIVED]
EXT-PARAPET #EX-19 - HP parapet return on grid 4 (stud CL 1 3/4" east of grid 4, 2/A09.25) from grid G line into the roof past line F (A02.02 key note 10 ACM coping) | EX-19 | 3.927 | 4.292 | 0 | 6" parapet | 16 | 0 | HP parapet return on grid 4 (stud CL 1 3/4" east of grid 4, 2/A09.25) from grid G line into the roof past line F (A02.02 key note 10 ACM coping) | 4/A09.26 | [DERIVED]
EXT-PARAPET #EX-20 - HP parapet grid 2, G to D (J/A09.23 T.O. PARAPET 2) | EX-20 | 29 | 4.292 | 0 | 6" parapet | 16 | 0 | HP parapet grid 2, G to D (J/A09.23 T.O. PARAPET 2) | 4/A09.26 | [DERIVED]
EXT-PARAPET #EX-21 - HP parapet on D, grid 2 to grid 3 (2/A09.02 EPS-3 at T.O. PARAPET 2) | EX-21 | 3.875 | 4.292 | 0 | 6" parapet | 16 | 0 | HP parapet on D, grid 2 to grid 3 (2/A09.02 EPS-3 at T.O. PARAPET 2) | 4/A09.26 | [DERIVED]
EXT-PARAPET #EX-22 - LP parapet line F, grid 4 to grid 8 (C/A09.21) | EX-22 | 39.604 | 2.042 | 0 | 6" parapet | 16 | 0 | LP parapet line F, grid 4 to grid 8 (C/A09.21) | 4/A09.26 | [DERIVED]
EXT-PARAPET #EX-23+EX-24 - LP parapet grid 8, F to B (high roof, D/A09.22) + LP parapet grid 8, B to A (low roof, E/A09.22 PARAPET HEIGHT @ LOWER ROOF 4'-2 1/4") | EX-23+EX-24 | 75.938 | 2.988 | 0 | 6" parapet | 16 | 0 | LP parapet grid 8, F to B (high roof, D/A09.22) + LP parapet grid 8, B to A (low roof, E/A09.22 PARAPET HEIGHT @ LOWER ROOF 4'-2 1/4") | 4/A09.26 | [DERIVED]
EXT-PARAPET #EX-25 - LP parapet grid A, grid 3 to grid 8 (low roof, F/A09.22 4'-6 3/4" @ lower roof) | EX-25 | 52.333 | 4.886 | 0 | 6" parapet | 16 | 0 | LP parapet grid A, grid 3 to grid 8 (low roof, F/A09.22 4'-6 3/4" @ lower roof) | 4/A09.26 | [DERIVED]
EXT-PARAPET #EX-26+EX-27 - LP parapet grid 3, D to B (high roof, H/A09.23 T.O. PARAPET 1 17'-9") + LP parapet grid 3, B to A (low roof) | EX-26+EX-27 | 47.927 | 3.54 | 0 | 6" parapet | 16 | 0 | LP parapet grid 3, D to B (high roof, H/A09.23 T.O. PARAPET 1 17'-9") + LP parapet grid 3, B to A (low roof) | 4/A09.26 | [DERIVED]
TYPE A1
A1 #W1-1 - Calling Cubes 122 north wall (to Waiting 104) | W1-1 | 17.021 | 15.375 | 3 | 3-5/8" | 16 | 343.52 | Calling Cubes 122 north wall (to Waiting 104) | 3/A12.01 | [DERIVED]
A1 #W1-2 - MW01 printer niche east wall (in 122) | W1-2 | 3.531 | 15.375 | 2 | 3-5/8" | 16 | 63.56 | MW01 printer niche east wall (in 122) | 3/A12.01 | [DERIVED]
A1 #W1-3 - MW01 niche south wall / MW07 (in 122) | W1-3 | 2.022 | 15.375 | 2 | 3-5/8" | 16 | 36.4 | MW01 niche south wall / MW07 (in 122) | 3/A12.01 | [DERIVED]
A1 #W1-4 - Corridor 111 north end, incl. door 111 (between B2 restroom wall and A5 stub) | W1-4 | 5.587 | 15.375 | 3 | 3-5/8" | 16 | 110.28 | Corridor 111 north end, incl. door 111 (between B2 restroom wall and A5 stub) | 3/A12.01 | [DERIVED]
A1 #W1-5 - Calling Cubes 122 / Break Room 118 wall | W1-5 | 15.233 | 12.971 | 2 | 3-5/8" | 16 | 274.2 | Calling Cubes 122 / Break Room 118 wall | 3/A12.01 | [DERIVED]
A1 #W1-6 - Break Room 118 north wall, incl. door 118A (grid 6 to the A1K corner at grid 7) | W1-6 | 5.094 | 12.927 | 2 | 3-5/8" | 16 | 94.24 | Break Room 118 north wall, incl. door 118A (grid 6 to the A1K corner at grid 7) | 3/A12.01 | [DERIVED]
A1 #W1-7 - East end of MW21 / Break Room 118 (grid 6) | W1-7 | 2.139 | 11.821 | 2 | 3-5/8" | 16 | 39.57 | East end of MW21 / Break Room 118 (grid 6) | 3/A12.01 | [DERIVED]
A1 #W1-8 - Corridor 111 east wall (grid 5), Break Room 118 / Electrical 120 / NER 121 | W1-8 | 20.521 | 11.821 | 5 | 3-5/8" | 16 | 353.01 | Corridor 111 east wall (grid 5), Break Room 118 / Electrical 120 / NER 121 | 3/A12.01 | [DERIVED]
A1 #W1-9 - Work Room 119 north wall, incl. door 119 (B2 grid 7 to exterior wall grid 8) | W1-9 | 11.667 | 12.775 | 2 | 3-5/8" | 16 | 215.84 | Work Room 119 north wall, incl. door 119 (B2 grid 7 to exterior wall grid 8) | 3/A12.01 | [DERIVED]
A1 #RW1-2 - Corridor 111 drinking fountain alcove, back wall (restroom side) | RW1-2 | 4.073 | 11.807 | 4 | 3-5/8" | 16 | 63.6 | Corridor 111 drinking fountain alcove, back wall (restroom side) | 3/A12.01 | [DERIVED]
A1 #RW1-3 - Corridor 111 drinking fountain alcove, north return | RW1-3 | 1.698 | 12.958 | 3 | 3-5/8" | 16 | 26.98 | Corridor 111 drinking fountain alcove, north return | 3/A12.01 | [DERIVED]
A1 #RW1-4 - Corridor 111 drinking fountain alcove, south return | RW1-4 | 1.698 | 12.865 | 3 | 3-5/8" | 16 | 26.98 | Corridor 111 drinking fountain alcove, south return | 3/A12.01 | [DERIVED]
TYPE A5
A5 #W1-10 - Calling Cubes 122 west wall (MW07 / FEC-1), grid 5 north of corridor 111 | W1-10 | 11 | 15.375 | 3 | 6" | 16 | 227.34 | Calling Cubes 122 west wall (MW07 / FEC-1), grid 5 north of corridor 111 | 3/A12.01 | [DERIVED]
A5 #W1-11a+W1-11b - Calling Cubes 122 east wall (grid 6), north of grid B + Calling Cubes 122 east wall (grid 6), south of grid B | W1-11a+W1-11b | 19.408 | 13.709 | 3 | 6" | 16 | 378.53 | Calling Cubes 122 east wall (grid 6), north of grid B + Calling Cubes 122 east wall (grid 6), south of grid B | 3/A12.01 | [DERIVED]
A5 #W1-12 - Break Room 118 / Cash Window 116 (grid 7), north of door 116 | W1-12 | 3.28 | 11.776 | 2 | 6" | 16 | 60.68 | Break Room 118 / Cash Window 116 (grid 7), north of door 116 | 3/A12.01 | [DERIVED]
A5 #RW1-1a+RW1-1b - Calling Cubes 122 west wall, offset A5 run at door 122 (north of grid B) + Calling Cubes 122 west wall at door 122 (south of grid B) | RW1-1a+RW1-1b | 5.28 | 12.535 | 3 | 6" | 16 | 87.72 | Calling Cubes 122 west wall, offset A5 run at door 122 (north of grid B) + Calling Cubes 122 west wall at door 122 (south of grid B) | 3/A12.01 | [DERIVED]
TYPE A1K
A1K #W1-13 - Cash Window 116 CSR line north end (kevlar wall, east part; west part tagged B2K = other task) | W1-13 | 3.417 | 15.375 | 2 | 3-5/8" | 24 | 105.08 | Cash Window 116 CSR line north end (kevlar wall, east part; west part tagged B2K = other task) | 4/A12.01 | [DERIVED]
A1K #W1-14 - Cash Window 116 CSR line south end, east part (over Future FCAM C1 box) | W1-14 | 3.417 | 12.939 | 2 | 3-5/8" | 24 | 88.42 | Cash Window 116 CSR line south end, east part (over Future FCAM C1 box) | 4/A12.01 | [DERIVED]
A1K #W1-15 - Cash Window 116 CSR line south end, west part | W1-15 | 2.347 | 12.927 | 2 | 3-5/8" | 24 | 60.68 | Cash Window 116 CSR line south end, west part | 4/A12.01 | [DERIVED]
TYPE B
B #W2-1 - Electrical 120 north wall (Break Room 118 side) | W2-1 | 9.99 | 12.827 | 2 | 3-5/8" | 16 | 256.28 | Electrical 120 north wall (Break Room 118 side) | 1/A12.01 | [DERIVED]
B #W2-2 - Janitor 112 / Storage 117 north wall (Men's Restroom 113 side) | W2-2 | 11.719 | 12.748 | 3 | 3-5/8" | 16 | 250.99 | Janitor 112 / Storage 117 north wall (Men's Restroom 113 side) | 1/A12.01 | [DERIVED]
B #W2-3 - Janitor 112 / Storage 117 south wall (Wellness 115 side) | W2-3 | 11.719 | 12.667 | 3 | 3-5/8" | 16 | 296.87 | Janitor 112 / Storage 117 south wall (Wellness 115 side) | 1/A12.01 | [DERIVED]
B #W2-4 - Wall between Electrical 120 and NER 121 | W2-4 | 9.583 | 12.698 | 2 | 3-5/8" | 16 | 243.36 | Wall between Electrical 120 and NER 121 | 1/A12.01 | [CONFIRMED]
B #W2-5 - East wall of Electrical 120 / NER 121 (Break Room 118 side) | W2-5 | 13.74 | 12.823 | 3 | 3-5/8" | 16 | 252.91 | East wall of Electrical 120 / NER 121 (Break Room 118 side) | 1/A12.01 | [DERIVED]
B #W2-6 - Wall between Janitor 112 (MW06A) and Storage 117 (MW05) | W2-6 | 3.5 | 12.743 | 2 | 3-5/8" | 16 | 88.94 | Wall between Janitor 112 (MW06A) and Storage 117 (MW05) | 1/A12.01 | [CONFIRMED]
TYPE B2
B2 #W2-7 - ATM Room 102 east wall on grid 4 (Central Zone 103 side), incl. door 102 | W2-7 | 5.667 | 15.375 | 2 | 6" | 16 | 111.66 | ATM Room 102 east wall on grid 4 (Central Zone 103 side), incl. door 102 | 1/A12.01 | [CONFIRMED]
B2 #W2-8 - Women's Restroom 114 east wall (Corridor 111 side), incl. door 114, from G wall face to drinking-fountain alcove | W2-8 | 5.542 | 13.052 | 2 | 6" | 16 | 96.32 | Women's Restroom 114 east wall (Corridor 111 side), incl. door 114, from G wall face to drinking-fountain alcove | 1/A12.01 | [CONFIRMED]
B2 #W2-9 - East wall on grid 4 from drinking-fountain alcove to exterior wall: Men's 113 / Storage 117 / Wellness 115 (Corridor 111 side), incl. doors 113, 117, 115 | W2-9 | 15.787 | 12.865 | 4 | 6" | 16 | 257.71 | East wall on grid 4 from drinking-fountain alcove to exterior wall: Men's 113 / Storage 117 / Wellness 115 (Corridor 111 side), incl. doors 113, 117, 115 | 1/A12.01 | [DERIVED]
B2 #W2-10 - Wall between Break Room 118 and Work Room 119 (grid 7) | W2-10 | 11.74 | 11.64 | 3 | 6" | 16 | 270.47 | Wall between Break Room 118 and Work Room 119 (grid 7) | 1/A12.01 | [DERIVED]
TYPE B2K
B2K #W2-11 - Kevlar (hatched) wall between Office 4 (108) and the customer alcove west of Cash Window 116 | W2-11 | 2.207 | 15.375 | 2 | 6" | 16 | 67.86 | Kevlar (hatched) wall between Office 4 (108) and the customer alcove west of Cash Window 116 | 1/A12.01+4/A12.01 | [DERIVED]
TYPE F
F #W2-20 - Diagonal F wall between 24 HR Vestibule 101 (ATM lobby) and ATM Room 102, west wall to column W2-19 | W2-20 | 17.762 | 15.375 | 2 | 3-5/8" | 16 | 325.38 | Diagonal F wall between 24 HR Vestibule 101 (ATM lobby) and ATM Room 102, west wall to column W2-19 | 12/A12.01 | [DERIVED]
TYPE G
G #W3-1 - Office front E (grid 7), north end stub of Office 105 between north exterior wall and vendor frame | W3-1 | 2.42 | 14.383 | 4 | 1-5/8" | 16 | 139.24 | Office front E (grid 7), north end stub of Office 105 between north exterior wall and vendor frame | 5/A12.01 | [DERIVED]
G #W3-2 - Office front E (grid 7), stub between Office 105 door and Office 106 glass (incl. 4" return at door 105, G1 demising abuts) | W3-2 | 3.467 | 14.383 | 6 | 1-5/8" | 16 | 199.45 | Office front E (grid 7), stub between Office 105 door and Office 106 glass (incl. 4" return at door 105, G1 demising abuts) | 5/A12.01 | [DERIVED]
G #W3-3 - Office front E (grid 7), stub between Office 106 door and Office 107 glass (wraps column E/7; G demising abuts) | W3-3 | 3.253 | 14.383 | 6 | 1-5/8" | 16 | 187.18 | Office front E (grid 7), stub between Office 106 door and Office 107 glass (wraps column E/7; G demising abuts) | 5/A12.01 | [DERIVED]
G #W3-4 - Office front E (grid 7), stub between Office 107 door and Office 108 glass (G demising abuts) | W3-4 | 3.253 | 14.225 | 6 | 1-5/8" | 16 | 185.11 | Office front E (grid 7), stub between Office 107 door and Office 108 glass (G demising abuts) | 5/A12.01 | [DERIVED]
G #W3-11 - Demising wall Office 106 / Office 107 | W3-11 | 11.771 | 15.375 | 4 | 1-5/8" | 16 | 723.9 | Demising wall Office 106 / Office 107 | 5/A12.01 | [DERIVED]
G #W3-12 - Demising wall Office 107 / Office 108 | W3-12 | 11.771 | 15.375 | 4 | 1-5/8" | 16 | 723.9 | Demising wall Office 107 / Office 108 | 5/A12.01 | [DERIVED]
G #W3-13+W3-5 - South wall of Office 108 (Office 108 / Cash Window 116), from B2K end to east exterior wall + Office front E (grid 7), 4" return at Office 108 door, south end against B2K (incl. jog W3-5 0.333 LF) | W3-13+W3-5 | 10.407 | 15.338 | 4 | 1-5/8" | 16 | 638.46 | South wall of Office 108 (Office 108 / Cash Window 116), from B2K end to east exterior wall + Office front E (grid 7), 4" return at Office 108 door, south end against B2K (incl. jog W3-5 0.333 LF) | 5/A12.01 | [DERIVED]
G #W3-14 - North wall of Office 109 (ATM Room 102 / Office 109), west exterior face to lobby face of office front W | W3-14 | 12.333 | 15.375 | 4 | 1-5/8" | 16 | 758.5 | North wall of Office 109 (ATM Room 102 / Office 109), west exterior face to lobby face of office front W | 5/A12.01 | [DERIVED]
G #W3-18 - Demising wall Office 109 / Office 110 | W3-18 | 11.625 | 15.375 | 4 | 1-5/8" | 16 | 714.94 | Demising wall Office 109 / Office 110 | 5/A12.01 | [DERIVED]
G #W3-19 - South wall of Office 110 (Office 110 / Women's Restroom 114) | W3-19 | 11.625 | 15.375 | 4 | 1-5/8" | 16 | 714.94 | South wall of Office 110 (Office 110 / Women's Restroom 114) | 5/A12.01 | [DERIVED]
TYPE BULKHEAD-G
BULKHEAD-G #W3-6+W3-7+W3-8+W3-9 - Office front E (grid 7), bulkhead over vendor office front of Office 105 (glass panel DFC-1A + door 105) + Office front E (grid 7), bulkhead over vendor office front of Office 106 (glass panel DFC-1A + door 106) + Office front E (grid 7), bulkhead over vendor office front of Office 107 (glass panel DFC-1A + door 107) + Office front E (grid 7), bulkhead over vendor office front of Office 108 (glass panel DFC-1A + door 108) | W3-6+W3-7+W3-8+W3-9 | 30 | 6.262 | 5 | 1-5/8" | 16 | 766.8 | Office front E (grid 7), bulkhead over vendor office front of Office 105 (glass panel DFC-1A + door 105) + Office front E (grid 7), bulkhead over vendor office front of Office 106 (glass panel DFC-1A + door 106) + Office front E (grid 7), bulkhead over vendor office front of Office 107 (glass panel DFC-1A + door 107) + Office front E (grid 7), bulkhead over vendor office front of Office 108 (glass panel DFC-1A + door 108) | 9/A12.01 | [DERIVED]
BULKHEAD-G #W3-20+W3-21 - Office front W (grid 4), bulkhead over vendor office front of Office 109 (glass panel DFC-1A + door 109) + Office front W (grid 4), bulkhead over vendor office front of Office 110 (glass panel DFC-1A + door 110) | W3-20+W3-21 | 15 | 7.375 | 5 | 1-5/8" | 16 | 452.48 | Office front W (grid 4), bulkhead over vendor office front of Office 109 (glass panel DFC-1A + door 109) + Office front W (grid 4), bulkhead over vendor office front of Office 110 (glass panel DFC-1A + door 110) | 9/A12.01 | [DERIVED]
TYPE G1
G1 #W3-10 - Demising wall Office 105 / Office 106 (front stub W3-2 to east exterior wall) | W3-10 | 11.771 | 15.375 | 4 | 1-5/8" | 16 | 723.9 | Demising wall Office 105 / Office 106 (front stub W3-2 to east exterior wall) | 5/A12.01 | [DERIVED]
G1 #W3-16+W3-15 - Office front W (grid 4), stub between Office 109 glass and Office 110 door (incl. 4" return at door 110, G demising abuts) + Office front W (grid 4), 4" return at Office 109 door under north wall of Office 109 (incl. jog W3-15 0.333 LF) | W3-16+W3-15 | 3.84 | 15.375 | 6 | 1-5/8" | 16 | 236.16 | Office front W (grid 4), stub between Office 109 glass and Office 110 door (incl. 4" return at door 110, G demising abuts) + Office front W (grid 4), 4" return at Office 109 door under north wall of Office 109 (incl. jog W3-15 0.333 LF) | 5/A12.01 | [DERIVED]
G1 #W3-17 - Office front W (grid 4), south end stub of Office 110 down to south face of W3-19 (L corner) | W3-17 | 3.18 | 15.375 | 4 | 1-5/8" | 16 | 195.58 | Office front W (grid 4), south end stub of Office 110 down to south face of W3-19 (L corner) | 5/A12.01 | [DERIVED]
| TOTAL - PARTITIONS | 995.03 |  |  |  |  | 16279.62
TYPE OTHER FRAMING (NOT A PARTITION)
ceiling_transition #CE-1 - Waiting 104 north edge vs Central Zone 103 ACT-4 11'-6" | CE-1 | 17.027 | 4.375 | 3 | 3-5/8" | 16 | 30.68 | Waiting 104 north edge vs Central Zone 103 ACT-4 11'-6" | 7/A09.33 | [DERIVED]
ceiling_transition #CE-2 - Waiting 104 west edge vs Central Zone 103 ACT-4 11'-6" | CE-2 | 30 | 4.375 | 3 | 3-5/8" | 16 | 54.06 | Waiting 104 west edge vs Central Zone 103 ACT-4 11'-6" | 7/A09.33 | [DERIVED]
ceiling_transition #CE-3 - Waiting 104 east edge vs Central Zone 103 ACT-4 11'-6" | CE-3 | 30 | 4.375 | 3 | 3-5/8" | 16 | 54.06 | Waiting 104 east edge vs Central Zone 103 ACT-4 11'-6" | 7/A09.33 | [DERIVED]
ceiling_transition #CE-4 - Central Zone 103: ACT-4 11'-6" (north) to ACT-4 9'-0" pocket west of CSR | CE-4 | 5.093 | 6.375 | 3 | 3-5/8" | 16 | 19.37 | Central Zone 103: ACT-4 11'-6" (north) to ACT-4 9'-0" pocket west of CSR | 7/A09.33 | [DERIVED]
soffit_side #CE-5 - CSR soffit W drop line facing 103 ACT-4 9'-0", north of grid B | CE-5 | 6.529 | 7.375 | 1 | 3-5/8" | 16 | 9.79 | CSR soffit W drop line facing 103 ACT-4 9'-0", north of grid B | 10/A09.33 | [DERIVED]
soffit_side #CE-6 - CSR soffit W drop line facing 103 ACT-4 9'-0", south of grid B | CE-6 | 5.492 | 5.052 | 1 | 3-5/8" | 16 | 8.24 | CSR soffit W drop line facing 103 ACT-4 9'-0", south of grid B | 10/A09.33 | [DERIVED]
soffit_side #CE-7 - CSR soffit E drop line facing 116 ACT-4 9'-0", north of grid B | CE-7 | 6.529 | 7.375 | 1 | 3-5/8" | 16 | 9.79 | CSR soffit E drop line facing 116 ACT-4 9'-0", north of grid B | 10/A09.33 | [DERIVED]
soffit_side #CE-8 - CSR soffit E drop line facing 116 ACT-4 9'-0", south of grid B | CE-8 | 5.492 | 5.052 | 1 | 3-5/8" | 16 | 8.24 | CSR soffit E drop line facing 116 ACT-4 9'-0", south of grid B | 10/A09.33 | [DERIVED]
storefront_cripples #EX-1 - Vestibule 100 front (entrance), line G between piers at grids 2 and 4 | EX-1 | 12.562 | 4.983 | 1 | 6" | 16 | 86.36 | Vestibule 100 front (entrance), line G between piers at grids 2 and 4 | A/A09.21 | [CONFIRMED]
roof_step #EX-28 - Roof step at grid B, grids 3-8, row 1 of 3 (4/A02.02) | EX-28 | 51.787 | 3.323 | 0 | 3-5/8" | 16 | 0 | Roof step at grid B, grids 3-8, row 1 of 3 (4/A02.02) | 4/A02.02 | [DERIVED]
roof_step #EX-29 - Roof step at grid B, grids 3-8, row 2 of 3 (4/A02.02) | EX-29 | 51.787 | 3.465 | 2 | 3-5/8" | 16 | 246.3 | Roof step at grid B, grids 3-8, row 2 of 3 (4/A02.02) | 4/A02.02 | [DERIVED]
roof_step #EX-30 - Roof step at grid B, grids 3-8, row 3 of 3 (4/A02.02) | EX-30 | 51.787 | 1.142 | 1 | 3-5/8" | 16 | 59.14 | Roof step at grid B, grids 3-8, row 3 of 3 (4/A02.02) | 4/A02.02 | [DERIVED]
fascia_box #EX-31 - South canopy fascia (G/F side), full length | EX-31 | 78.167 | 1.865 | 0 | 3-5/8" | 16 | 0 | South canopy fascia (G/F side), full length | 7/A09.26 | [DERIVED]
fascia_box #EX-32 - East canopy fascia (grid 8 side) | EX-32 | 52.583 | 1.865 | 0 | 3-5/8" | 16 | 0 | East canopy fascia (grid 8 side) | 7/A09.26 | [DERIVED]
fascia_box #EX-33 - East canopy end return at B.2 | EX-33 | 3.667 | 1.865 | 0 | 3-5/8" | 16 | 0 | East canopy end return at B.2 | 7/A09.26 | [DERIVED]
fascia_box #EX-34 - Drive-up canopy west fascia (west of grid 1) | EX-34 | 55.896 | 1.865 | 0 | 3-5/8" | 16 | 0 | Drive-up canopy west fascia (west of grid 1) | 7/A09.26 | [DERIVED]
fascia_box #EX-35 - Drive-up canopy north edge at grid B (fascia to grid-3 wall) | EX-35 | 21.5 | 1.865 | 0 | 3-5/8" | 16 | 0 | Drive-up canopy north edge at grid B (fascia to grid-3 wall) | 7/A09.26 | [DERIVED]
fascia_box #EX-36 - North canopy fascia (grid A side) | EX-36 | 23 | 1.865 | 0 | 3-5/8" | 16 | 0 | North canopy fascia (grid A side) | 7/A09.26 | [DERIVED]
fascia_box #EX-37 - North canopy west end return | EX-37 | 3.688 | 1.865 | 0 | 3-5/8" | 16 | 0 | North canopy west end return | 7/A09.26 | [DERIVED]
fascia_box #EX-38 - North canopy east end return | EX-38 | 3.688 | 1.865 | 0 | 3-5/8" | 16 | 0 | North canopy east end return | 7/A09.26 | [DERIVED]
vestibule_head #EX-39 - Vestibule 100 / 24 HR Vestibule 101 storefront head (doors 101) | EX-39 | 15.646 | 6.708 | 0 | 3-5/8" | 16 | 0 | Vestibule 100 / 24 HR Vestibule 101 storefront head (doors 101) | 4/A12.10 | [CONFIRMED]
vestibule_head #EX-40 - Vestibule 100 east storefront head (door 100A + sidelite), grid 4 | EX-40 | 6.417 | 6.708 | 0 | 3-5/8" | 16 | 0 | Vestibule 100 east storefront head (door 100A + sidelite), grid 4 | 4/A12.10 | [CONFIRMED]
grille_head #EX-41 - Coiling grille head, grid 4 between 24 HR Vestibule 101 and Central Zone 103 | EX-41 | 13.333 | 1.5 | 2 | 2-1/2" | 16 | 40 | Coiling grille head, grid 4 between 24 HR Vestibule 101 and Central Zone 103 | 4/A08.21 | [CONFIRMED]

## Material Summary
MATERIAL SUMMARY - NET / WASTE / PURCHASE
Waste lives HERE, in its own column, applied ONCE: Pieces = ROUNDUP(Net x (1 + waste) / stock). Every stock length, coverage and yield is an Inputs cell.
Material | Unit | Net | Waste % | Waste | Purchase | Selling unit | Pieces to buy | Where it comes from | Yield check (live formula)
6" metal stud - exterior CFMF 600S162-54 (S1.11 note 5, rule 56.2, RFI-ADV-6) and 6" interior 600S137-33 | LF | 4730.2 | 0.15 | 709.53 | 5439.73 | stick 20 ft | 272 | familias_out.json '6" stud (all gauges)'; 7/S5.20; S1.11; A09.21-A09.23
3-5/8" metal stud 362S137-33 | LF | 7403.24 | 0.15 | 1110.486 | 8513.726 | stick 20 ft | 426 | familias_out.json '3-5/8" stud (all gauges)'; 1/A12.01; 3/A12.01; 7/S5.20
1-5/8" metal stud (G / G1 double row) | LF | 4014.39 | 0.15 | 602.1585 | 4616.5485 | stick 20 ft | 231 | familias_out.json '1-5/8" stud'; 5/A12.01; 7/S5.20
6" parapet stud 600S162-54 (parapet infill) | LF | 1015.37 | 0.15 | 152.3055 | 1167.6755 | stick 20 ft | 59 | familias_out.json '6" parapet stud'; 11/S5.10; 6/S5.10
Bottom track (all sizes) | LF | 1347.39 | 0.15 | 202.1085 | 1549.4985 | run 10 ft | 155 | familias_out.json 'bottom track (all)'; 7/S5.20; 3/A12.01
Top / deflection track (all sizes) | LF | 1347.39 | 0.15 | 202.1085 | 1549.4985 | run 10 ft | 155 | familias_out.json 'top / deflection track (all)'; 10/S5.10; 3/A12.01
Ceiling / soffit track | LF | 1336.49 | 0.15 | 200.4735 | 1536.9635 | run 10 ft | 154 | familias_out.json 'ceiling / soffit track'; 6/A09.33; 7/A09.33; 7/A09.26
1-1/2" C.R. channel bracing | LF | 2557.63 | 0.15 | 383.6445 | 2941.2745 | C.R. channel 16 ft | 184 | familias_out.json 'bracing C.R. channel'; F/1/S5.20
Purlin 1x1x1 16 ga (track to deck) | LF | 239.4 | 0.15 | 35.91 | 275.31 | run 10 ft | 28 | familias_out.json 'purlin (track to deck)'; 4/A12.01; 10/A09.33
Header / box beam (by pieces) | LF | 792.25 | 0.15 | 118.8375 | 911.0875 | stick 20 ft | 46 | familias_out.json 'header / box beam'; 7/S5.20; 11/A09.27; 8/A12.01
Sill track | LF | 115.58 | 0.15 | 17.337 | 132.917 | run 10 ft | 14 | familias_out.json 'sill track'; 2/S5.20
7/8" furring channel (GWB ceilings) | LF | 364.05 | 0.15 | 54.6075 | 418.6575 | hat channel 12 ft | 35 | familias_out.json 'furring channel'; 6/A09.33; A04.01
1-1/2" carrying channel (GWB ceilings) | LF | 324.78 | 0.15 | 48.717 | 373.497 | C.R. channel 16 ft | 24 | familias_out.json 'carrying channel'; 6/A09.33; A04.01
Hanger wire 12 ga | LF | 533.62 | 0.15 | 80.043 | 613.663 | continuous coil (LF) | 614 | familias_out.json 'hanger wire'; 6/A09.33; S2.20
5/8" gypsum board regular (walls + ceilings) | SF | 17628.06 | 0.06 | 1057.6836 | 18685.7436 | 4x12 sheet | 390 | familias_out.json '5/8" gyp board regular (walls + ceilings)'; 1/A12.01; 3/A12.01; A04.01
5/8" moisture resistant gypsum board | SF | 257.45 | 0.06 | 15.447 | 272.897 | 4x12 sheet | 6 | familias_out.json '5/8" gyp MOISTURE RESISTANT'; F/A08.01; 6/A12.01
Ballistic panel 3/8" UL752 level 2 fiberglass | SF | 91.1 | 0.06 | 5.466 | 96.566 | 4x8 sheet | 4 | familias_out.json 'ballistic panel'; 4/A12.01
3/8" gypsum board (over ballistic panel) | SF | 69.92 | 0.06 | 4.1952 | 74.1152 | 4x8 sheet | 3 | familias_out.json '3/8" gyp board'; 4/A12.01
5/8" glass mat sheathing | SF | 474.13 | 0.06 | 28.4478 | 502.5778 | 4x8 sheet | 16 | familias_out.json '5/8" glass mat sheathing'; 5/A09.26; 9/A09.27; 7/A09.26
5/8" exterior gypsum sheathing | SF | 964.94 | 0.06 | 57.8964 | 1022.8364 | 4x8 sheet | 32 | familias_out.json '5/8" EXTERIOR gyp sheathing'; 4/A09.26
FRT wood blocking | LF | 764.18 | 0.06 | 45.8508 | 810.0308 | LF | 811 | familias_out.json 'FRT blocking'; 4/A09.26; A02.01 note C
Metal stud blocking 362CR / stud blocking | LF | 685.52 | 0.15 | 102.828 | 788.348 | stick 20 ft | 40 | familias_out.json 'metal stud blocking (362CR / STUD BLOCKING)'; 4/S5.20; A02.01 note C
Metal trim (corner bead, casing bead, shadow molding) | LF | 1012.91 | 0.15 | 151.9365 | 1164.8465 | trim stick 10 ft | 117 | familias_out.json 'metal trim (corner bead, casing, shadow molding)'; 7/A09.33; 8/A12.01; 53.1
Cement board (tile cove base) | SF | 33.38 | 0.06 | 2.0028 | 35.3828 | 3x5 sheet | 3 | familias_out.json 'cement board'; 3/A08.01
FRP panel | SF | 349.75 | 0.06 | 20.985 | 370.735 | 4x10 sheet | 10 | familias_out.json 'FRP'; A/A08.01; 3/A08.01
Acoustical sealant | LF | 1186.44 | 0.06 | 71.1864 | 1257.6264 | tube (25 LF per tube) | 51 | familias_out.json 'acoustical sealant'; 1/A12.01; 3/A12.01; 5/A09.26
Framed openings for recessed fixtures / air devices (MEP) | LF | 951.26 | 0.15 | 142.689 | 1093.949 | stick 20 ft | 55 | framed_openings_out.json totales_lf 'framed openings MEP'; E00.01; E02.01; M01.01
5/8" exterior grade FRT plywood (canopy soffits, fascia, column wraps) | SF | 2313.44 | 0.06 | 138.8064 | 2452.2464 | 4x12 ft sheet (Inputs) | 52 | familias_out.json FRT plywood by material; canon rows
5/8" FRT plywood bonded to 2-1/2" polyiso (exterior sheathing / nailbase) | SF | 3993.55 | 0.06 | 239.613 | 4233.163 | 4x12 ft sheet (Inputs) | 89 | familias_out.json FRT plywood by material; canon rows
3/4" FRT plywood | SF | 708.13 | 0.06 | 42.4878 | 750.6178 | 4x12 ft sheet (Inputs) | 16 | familias_out.json FRT plywood by material; canon rows
5/8" FRT plywood | SF | 27 | 0.06 | 1.62 | 28.62 | 4x12 ft sheet (Inputs) | 1 | familias_out.json FRT plywood by material; canon rows
Sealant at base of gypsum (exterior, not acoustical) | LF | 208.56 | 0.06 | 12.5136 | 221.0736 | tube (25 LF per tube) | 9 | familias_out.json acoustical sealant rows 'base of gypsum (exterior)'
Hanger wire 12 ga - hanger count (one per hanger, height per room) | PCS | 113 | 0 | 0 | 113 |  | 113 | familias_out.json hanger_pcs.total_pcs; wire bought on the LF row
Additional head track at openings over 4'-0" wide | LF | 56 | 0.15 | 8.4 | 64.4 | run 10 ft | 7 | accesorios.py [CRITERION]: 2/S5.20 HEAD TRACK @ NON LOAD BRG: 'ADD FULL LENGTH ADDL HEAD TRACK @ OPNG >4'-0"'; 9/S5.20 'HEAD TRACK (DOUBLE TRACK @ OPNG > 4'-0")'; Estimator user decision #1: R.O. + 1'-4" (8" bearing each side)
Stud reinforcement at MEP penetrations | PCS | 28 | 0 | 0 | 28 | each | 28 | accesorios.py [CRITERION]: 6/S5.20; M01.01 registered sweep (cruce.py group 0); 6/S5.20; M01.01 registered sweep (cruce.py group 1); 6/S5.20; M01.01 registered sweep (cruce.py group 2); 6/S5.20; M01.01 registered sweep (cruce.py group 3); 6/S5.20; M01.01 registered s
Extra framing - sistered stud and furring at the ATM recess | LF | 40.35 | 0.15 | 6.0525 | 46.4025 | stick 20 ft | 3 | accesorios.py [CRITERION]: 6/A08.11 2 1/2" METAL STUD SISTERED TO 6" METAL STUD; 7/A08.11; 5/A08.11; A08.11 ATM equipment PO form
2-1/2" CFMF @ 16" O.C. at coiling grille head (4/A08.21) | LF | 4.93 | 0.15 | 0.7395 | 5.6695 | stick 20 ft | 1 | accesorios.py [DERIVED]: 4/A08.21: 2 1/2" CFMF @ 16" O.C. between two 6" CFMF box beam headers in the 1'-6" zone; the 2'-4 1/2" zone above holds the vendor 3x3 tube / angle (RFI-EX-10)
Gypsum board jamb return at openings | SF | 92.78 | 0.06 | 5.5668 | 98.3468 | 4x12 ft sheet (Inputs) | 3 | accesorios.py [CRITERION]: Estimator criterion (return width = 6" stud depth, not dimensioned; RFI with delta at 0.20 ft)
PVC trim - edge trim molding and inside corner molding at the FRP | LF | 219.5 | 0.06 | 13.17 | 232.67 | trim stick 10 ft | 24 | accesorios.py [DERIVED]: 3/A08.01 '5'-0" TO TOP OF FRP' (elevations A-D/A08.01); WC-3 FRP A00.40; 1/A08.01 room polygon: 4 room corners + notch at TA-14 / lavatory alcove wall (1 inside + 1 outside); 5 - 1 = 4; A05.01 finish plan key note 6 'FRP FROM FLOOR TO 4'-0"
Power-driven fasteners and duct sleeves | PCS | 293 | 0 | 0 | 293 | each | 293 | accesorios.py [DERIVED]: 11/S5.10 PARAPET INFILL FRAMING: 'PAFs SPACED AT 12" O.C. MAX.' (600T125-54 bottom track to steel beam); M01.01 label 'FD' at sidewall register (wall-mounted, ends in the wall; not a straight crossing); M00.03 schedule; M01.01 registered sw
Access panel 2'x2' | PCS | 1 | 0 | 0 | 1 | each | 1 | accesorios.py [CONFIRMED]: A04.01 key note 4 '2' X 2' LOCKING ACCESS PANEL. KEYED TO MATCH MAIN ENTRY' (marker in vestibule 100, GB ceiling 10'-0")
Drywall screws 1-1/4" bugle head | PCS | 33666.43 | 0 | 0 | 33666.43 | each | 33667 | accesorios.py [DERIVED]: Inputs!B20 (Drywall screws per SF of board = 1.875) x 17955.4 SF of board | 33666.375
Framing screws, pan head self-drilling | PCS | 7144 | 0 | 0 | 7144 | each | 7144 | accesorios.py [DERIVED]: Inputs!B21 (Framing screws per stud piece = 4) x 1786 stud pieces | 7144
Power-driven fasteners, slab pins for the bottom track | PCS | 537.15 | 0 | 0 | 537.15 | each | 538 | accesorios.py [DERIVED]: 537.15 LF of interior bottom track on slab / Inputs!B22 (Power-driven pin spacing (ft) = 1) | 537.15
Expansion anchors Hilti 1/4" Kwik Bolt II, exterior bottom track @ 8" O.C. | PCS | 366.94 | 0 | 0 | 366.94 | each | 367 | accesorios.py [DERIVED]: 244.64 LF of exterior bottom track on slab / Inputs!B25 (Expansion anchor spacing (ft) = 0.6667) | 366.9417
Joint compound, all purpose | LB | 1292.79 | 0 | 0 | 1292.79 | lb | 1293 | accesorios.py [DERIVED]: Inputs!B23 (Joint compound (lb per SF) = 0.072) x 17955.4 SF of board | 1292.7888
Joint tape, paper | LF | 6643.51 | 0 | 0 | 6643.51 | LF | 6644 | accesorios.py [DERIVED]: Inputs!B24 (Joint tape (LF per SF) = 0.37) x 17955.4 SF of board | 6643.498
Level 5 finish | SF | 868.71 | 0.06 | 52.1226 | 920.8326 | SF | 921 | accesorios.py [DERIVED]: 1/A11.04 11'-9 1/4" V.I.F.; height = office ceiling ACT-4 9'-0" A04.01; A05.01 WC-18 tag; 6/A11.01 11'-9 1/4" V.I.F.; height = office ceiling ACT-4 9'-0" A04.01; A05.01 WC-18 tag; 5/A11.04 11'-9 1/4" V.I.F.; height = office ceiling ACT-4 9'

## Pending Items
RFI | Question / condition | Delta of each alternative
RFI-ACC-additional-head-track | additional head track: openings with their own box (openings_extra) > 4'-0": do they also take the additional head track of 2/S5.20? | 100.54 lf
RFI-ACC-extra-framing-atm | extra framing ATM: ATM-DU drive-up ATM (NHA 9D): ATM recess not fully dimensioned (width DERIVED, sistered height DERIVED, furring rows DERIVED) | 11.18 lf
RFI-ACC-gypsum-board-jamb-return | gypsum board jamb return: jamb return width not dimensioned | -55.67 sf
RFI-ACC-slab-pins | slab pins: pin spacing: 12" (interior anchorage) vs 16" (fastener schedule) vs 24" (type K box) | 16in: -134.29 pcs; 24in: -268.57 pcs
RFI-ACC-level-5-finish | Level 5 finish: WC-20 (A05.01 key note 9, 24 HR vestibule) is not in the A00.40 legend and has no tag; extent taken as the vestibule face of the diagonal ATM wall (2 x 7.604 ft x 10.0 ft). | 0 SF if WC-20 is not used / +34.8 SF if the ATM opening strip is also covered
RFI-ACC-stud-reinforcement-mep | stud reinforcement MEP: Curved flex / round duct runs and wall registers cannot be detected as straight crossings; the list adds the labelled FD and S-2 sidewall registers by hand from M01.01. Other flex-duct crossings of deck-high partitions may exist. | +1 plate per additional duct crossing
RFI-CE-1 | GWB ceiling suspension spacing is not printed (no GWB suspended ceiling detail or spec in the set; A09.33 notes cover ACT only). Carried furring channel @ 16" O.C., carrying channel @ 48" O.C., hangers @ 48" O.C. (ASTM C754 typical). Confirm. | Furring @ 24" O.C.: -109.07 LF furring channel and -130.25 LF 3-5/8" ceiling joists (104 stud_joist). Carrying and hangers @ 36": +61.29 LF carrying, +48 hanger PCS (+230.06 LF hanger wire).
RFI-CE-2 | Carrying channel direction not printed. Carried E-W (perpendicular to the N-S roof beams on S2.20, deck flute E-W); furring / ceiling joists N-S. Confirm. | Carrying N-S instead: -5.25 LF carrying channel, +36.77 LF furring channel, -11.35 LF 3-5/8" ceiling joists (104), hanger PCS unchanged (113).
RFI-CE-3 | Waiting 104 GB ceiling: no RCP callout; its R-11C/R-11CE trimless linear gyp slots follow 6/A09.33, which draws 3-5/8" METAL STUD FRAMING @ 16" O.C. Carried as stud_joist (3-5/8" ceiling joists + carrying + hangers). Confirm vs standard furring channel. | As furring instead: -420.0 LF 3-5/8" stud (ceiling joists) and +420.0 LF furring channel; carrying / hangers / board unchanged.
RFI-CE-4 | RCP has no callout to 7/A09.33 (ceiling transition) or 8/A09.33 (bulkhead). Typical details applied at: Waiting 104 GB 11'-0" vs 103 ACT-4 11'-6" (N, W, E edges, 77.03 LF) and 103 ACT-4 11'-6" to ACT-4 9'-0" step drawn as a 5" band west of the CSR (5.09 LF). Both details give the same framing (vertical studs @ 16" to structure + 3-5/8" kicker/bracing @ 48"). Confirm the 103 ACT-to-ACT step is a framed GWB band. | If the 103 ACT-to-ACT step (CE-4) is not framed: -31.88 LF vertical studs, -27.05 LF kickers, -10.19 LF ceiling track, -10.19 LF trim, -3.82 LF purlin.
RFI-CE-5 | CSR soffit (116, GB 8'-0"): typical 10/A09.33 draws one drop side and a scheduled partition on the other; 4/A12.08 and A04.01 show ACT-4 9'-0" on BOTH long sides (116 and 103) and 9/A12.08 draws two framed sides. Carried 2 drop lines to deck. Confirm. | With 1 drop line: -12.02 LF of soffit side = approx -69.5 LF 3-5/8" studs (6 x 7.375 + 5 x 5.052) and -24.04 LF ceiling/soffit track.
RFI-CE-6 | S2.20 tags B.O.D. 15'-4 1/2" (NO SLOPE) only between grids E-F; the B-E zone has no B.O.D. tag (only '@ LOW ROOF' text near the grid E beam) while A02.02 shows the only roof step at grid B (key note 13) and S2.20 marks the grid B beams W14x22 (HI)/(LOW). Carried 15'-4 1/2" for F-B (Vestibules 100/101, Waiting 104, transitions CE-1..CE-4, CSR north drop sides). Confirm B.O.D. between E and B. | Per 1 ft lower deck south of grid E: about -23 LF hanger wire (104, ~23 of 54 PCS south of E), -38 LF vertical/drop studs (CE-2/CE-3 south parts ~21 studs, CE-4 5, CSR north sides 12) and -16 LF kickers; vestibules unchanged.
RFI-CE-7 | Linear slot diffusers SD (TITUS TBDI-10, M00.03 size SEE DRAWING) in GB ceilings 100/101/113/114: framed opening carried at the drawn plenum width (7.7 in) and drawn section length (4.29 ft / 2.29 ft) per M01.01. Confirm opening size (slot face is 2 x 1 in). | At 2 in slot face width: -15.2 LF framed openings MEP.
RFI-CE-8 | Low roof A-B slopes from B.O.D. 13'-0 5/8" (grid B) to 12'-6 3/8" (grid A). Restrooms 113/114 hangers and CSR south drop sides carried at the high end 13'-0 5/8". Confirm. | Interpolated at room centers (about -0.16 ft): -3.8 LF hanger wire (24 PCS) and about -1 LF drop studs.
RFI-EX-1 | S2.20 prints the canopy deck as 'B.O.D. EL. 111'-9" TYP. @ CANOPY' while every other elevation is relative to 0'-0" (canopy T.O.S. 11'-9" to 12'-2 3/4"; J/A09.23 and H/A09.23 T/STEEL 11'-9"). Read as 11'-9". | No change to exterior wall heights (set by the roof perimeter beams); canopy deck constant only.
RFI-EX-2 | Canopy beams sit in the 6" CFMF stud plane (A/A09.21, J/A09.23, H/A09.23, 7/A09.26, 15/A09.27). Studs carried continuous to the roof perimeter beam (canopy_beam_split false). Confirm whether the studs are split at the canopy beam (piece below + piece above). | If split: +155.78 LF bottom track and +155.78 LF top track (EX-1, 2, 3, 4, 5, 6, 10), approx. -147 LF 6" stud (studs x canopy beam depth); inventario.py _rfi_split gives the exact value.
RFI-EX-3 | Drive-up ATM R.O. width: 7/A08.11 plan 2'-2 1/2" vs 5/A08.11 elevation 2'-2 1/8" (26.4"). Carried 2'-2 1/2" (more material). | -0.031 ft x 4 header pieces = -0.13 LF header; negligible.
RFI-EX-4 | Door 123 rough opening not printed: carried 3'-4" (3'-0" leaf A00.30 + 2" HM frame faces; vector 3.39 ft) with head 8'-2" (14/A09.27). | +/-0.167 ft per inch of frame face x 4 box pieces = +/-0.67 LF header.
RFI-EX-5 | S2.20 does not label the perimeter beam on grid A between grids 3 and 3.4; carried W18x35 (same run as 3.4-6). | If W14x22: EX-8 studs within ~4.1 ft gain 0.333 ft each (about +1.3 LF 6" stud).
RFI-EX-6 | Low roof (B-A) B.O.D. slopes 13'-0 5/8" at B to 12'-6 3/8" at A along grids 8 and 3: EX-7 and EX-11 studs carried at the high side (53.2) H = 11.910 ft. | Average height 11.650 ft: -0.26 ft x about 20 studs per wall = about -10.4 LF 6" stud total.
RFI-EX-7 | Sloped low-roof parapets on grids 8 and 3 (B-A) carried at the high side T/STUD 17'-5" - 12'-6 3/8" = 4.886 ft; sheathing uses the average 4.625 ft. | Parapet studs at average height: -0.26 ft x studs of EX-24 + EX-27 (about 2 x 26) = about -13.5 LF 6" parapet stud.
RFI-EX-8 | HP parapet return on grid 4 (A02.02 key note 10, ACM coping): stud CL 1 3/4" east of grid 4 (2/A09.25 4 3/4" FOS); length from grid G stud CL to the end of the roof-plan outline = 3.927 ft (vector, end of studs not dimensioned; outline end carried = more material). | -0.5 ft of return (stud end inside the end finish) = 0 studs (1 bay, 4 studs either way), -0.5 LF top + bottom track; reading B (1'-0" jog G-F added to grid G, no return) = -4 studs x 4.292 = -17.17 LF 6" parapet stud and -3.93 LF track.
RFI-EX-9 | Vestibule heads 4-7/A12.10 'METAL STUD FRAMING & BOX HEADER AS NEEDED': stud size, height and box size not printed. Carried 3 5/8" @ 16" from storefront top 8'-8" (8'-4" door + 4" top rail) to B.O.D. 15'-4 1/2" (6.708 ft) and a 4-piece box (E11, E20). Board faces on the heads not quantified (ceiling height from RCP). | If heads stop at the ceiling: about -4 ft x (13 + 6) studs = -76 LF 3 5/8" stud; box size unknown (header LF counted at 4 pieces).
RFI-EX-10 | Coiling grille head 4/A08.21: 2 1/2" CFMF @ 16" drawn only between the two 6" CFMF box beam headers (1'-6" zone); the 2'-4 1/2" zone above holds the vendor 3x3 tube/angle. Carried head_chain [18 in]. | If the 2 1/2" studs run the full printed chain 2'-4 1/2" + 1'-6": +2.375 ft x 12 studs = +28.5 LF 2 1/2" stud.
RFI-EX-11 | Grille jamb boxes 3/A08.21 (3 5/8" framing around vendor 3x3 tubes) height not printed: carried to deck 15'-4 1/2". FRT wood blocking at the grille jambs (3/A08.21 'FRT WOOD BLOCKING (TYP)') not quantified: grille opening height not printed. [INTEG: applies to the C1 grille jamb boxes W2-18 / W2-19 (EX-42 / EX-43 deleted by OTH); same height question as RFI-W2-1.] | If boxes stop at the ceiling (~9 ft): -6.4 ft x 8 studs = -51 LF 3 5/8" stud; FRT blocking pending (2 jambs x opening height).
RFI-EX-12 | Drive-up canopy soffit joist direction: E13 tracks carried at the west fascia (55.9 ft) and the wall line (56.3 ft) assuming E-W joists; 16/A09.27 (E-W cut) shows the soffit framing in cross-section, i.e. N-S joists hung from the E-W canopy beams. | If N-S: track lines become south fascia west of grid 2 (17.6) + north edge at B (21.5) = 39.1 LF instead of 112.2 LF (-73.1 LF ceiling track); joist LF changes with span.
RFI-EX-13 | Cladding and its supports EXCLUDED (60.4): 7/8" hat channel under EPS-5 (7/A09.26, 9/A09.27), ACM subframing / Z-girts, lath and Portland cement plaster PT-3/PT-4 (stucco on walls, soffits and column wraps), fiber cement panel and furring at the ATM (6/A08.11). Confirm by cladding trade. | Not quantified (excluded).
RFI-EX-14 | Storefront piers 1/A09.25 and 2/A09.25 draw two framing systems (exterior L 6" CFMF, interior L 3 5/8") as zones, not individual studs. Studs per part derived from FOS faces ROUNDUP(face/16")+1 minus one shared corner (5+5 at grid 2, 4+4 at grid 4). [INTEG: piers now 5 + 5 studs at grid 2 (EX-12) and 5 + 5 at grid 4 (EX-13).] | +/-1 stud per part per pier = +/-14.4 LF (6" or 3 5/8").
RFI-EX-15 | Canopy column wraps 5/A09.25: height not printed; carried slab to canopy soffit framing B/STUD 10'-7 1/4" (16/A09.27). | If wraps run to the canopy steel (11'-9"): +1.146 ft x 8 studs x 4 wraps = +36.7 LF 3 5/8" stud.
RFI-EX-16 | CLOSED by the drawings (E23): S2.20 prints HSS9x5x5/8 (LLV) T.O.S. EL. 9'-4 1/2" (lines G and F) and B.O.S. EL. 8'-7 1/2" on grid 2 (+ 9" LLV = 9'-4 1/2"); 2/A09.26 draws the 6" studs on the STEEL HEADER FRAMING. Cripples of SF-F (EX-4) and SF-W (EX-2) now start at 9'-4 1/2"; SF-100 (EX-1) already did. CLOSED by the drawings (E23): S2.20 prints HSS9x5x5/8 (LLV) T.O.S. EL. 9'-4 1/2" (lines G and F) and B.O.S. EL. 8'-7 1/2" on grid 2 (+ 9" LLV = 9'-4 1/2"); 2/A09.26 draws the 6" studs on the STEEL HEADER FRAMING. Cripples of SF-F (EX-4) and SF-W (EX-2) now start at 9'-4 1/2"; SF-100 (EX-1) already did. Storefronts with HSS lintels (SF-F, SF-100, SF-W; S2.20 HSS9x5x5/8 T.O.S. 9'-4 1/2"): cripples are computed by the tool from the opening head 8'-6"; actual cripples start on top of the HSS (9'-4 1/2"). | n/a: closed, 0 (applied in the canon: EX-4 -16.63 LF, EX-2 -3.50 LF 6" stud)
RFI-EX-17 | Exterior stud: S1.11 LGS note 5 requires 600S162-54 @ 12" within 6 ft of building corners and 600S162-54 @ 16" elsewhere; 7/S5.20 schedule lists exterior walls 600S137-33 @ 16". Gauge conflict (54 vs 33 mil). Corner zones applied at convex building corners only (not at the re-entrant corner grid 3 / D). | Gauge: no LF change. If the re-entrant corner also takes @12": +1 to +2 studs on EX-3 / EX-10 (about +28 LF).
RFI-EX-18 | CLOSED by the drawings (E23): 7/S5.20 METAL STUD PROPERTIES prints 362S137-33 @ 16" O.C. for the canopy fascia framing. Canopy fascia box framing 7/A09.26 '3 5/8" METAL STUD FRAMING' spacing not printed; carried 16" O.C. | n/a: closed, 0
RFI-EX-19 | S2.20 'HSS9x5x5/8 (LLV) B.O.S. EL. 8'-7 1/2"' along grid 2: extent not dimensioned. Carried over the vestibule west storefront only; the drive-up ATM head is the metal stud box beam of 6/A08.11. | If the HSS also spans the ATM: -(2.208 + 1.333) x 4 = -14.2 LF header.
RFI-EX-20 | Canopy fascia end returns (east canopy at B.2, 3'-8"; north canopy ends, 3'-8 1/4") taken from the A02.02 outline; no section through the ends. | If the returns are not boxed: -11.0 LF fascia track x 2 and about -10 studs x 1.865 ft.
RFI-EX-21 | Exterior wall lengths are interior face to interior face (chains on A02.01); the 6" x 6" outside-corner blocks are not in any wall length (corner studs come from L nodes). | If measured to the outer stud face at the 5 convex corners: +0.55 ft each = +2.8 LF bottom and top track.
RFI-EX-22 | Roof step 4/A02.02 outer upper row: top of 2x FRT blocking 'to align with highest point of tapered insulation' not dimensioned; carried high B.O.D. + 1'-0" (row height 3.323 ft). | +/-0.5 ft x about 40 studs = +/-20 LF 3 5/8" stud.
RFI-EX-23 | Interior pier faces (5/8" gypsum board on the 3 5/8" L, 1/A09.25, 2/A09.25) and the grille head soffit return (corner bead, 4/A08.21) are not entered as board faces. | Pier boards about 2 x 3.4 ft x 15.4 ft = +105 SF 5/8" regular; grille soffit about 13.3 x 0.83 = +11 SF.
RFI-W1-1 | Zone between grids E and B (A02.01 y=734-1246 pt): S2.20 prints B.O.D. EL. 15'-4 1/2" NO SLOPE only in the F-E band; 4/A02.02 shows the roof step at grid B (high T/STEEL 15'-4 1/2", low 13'-0 5/8"). Assumed 15'-4 1/2" for W1-1, W1-2, W1-3, W1-4, W1-10, W1-11a, W1-13. Confirm deck elevation E-B. | If 13'-0 5/8": stud height -2.323 ft on those walls (A1 ~23.4 LF, A5 ~27.9 LF of wall, A1K 3.42 LF); A1K board both faces -2.323 ft x 3.42 ft each.
RFI-W1-2 | A5 (6" interior, 3/A12.01) stud gauge not scheduled: 7/S5.20 lists 6" only as 600S137-33 EXTERIOR @ 16" O.C. Assumed 600S137-33 @ 16" O.C. (53.3). | No LF change; gauge/material cost only if a heavier/lighter 6" member is required.
RFI-W1-3 | A1K: 4/A12.01 '14 GA. METAL STUDS @ 24" O.C. MAX' vs 7/S5.20 interior 362S137-33 @ 16" O.C. Detail governs (53.8): 14 ga @ 24". | At 16" O.C.: +1 stud per wall on W1-13/W1-14 (3.42 ft) and +0 on W1-15; gauge 14 ga vs 33 mil.
RFI-W1-4 | A1K end walls of the CSR line (W1-13 north, W1-14/W1-15 south): plan hatch fills the full wall thickness, so the customer (fiberglass panel) face is not determinable; assumed the face away from the teller station. | Ballistic SF unchanged (L x 8'-0" either face); only the room/face carrying ballistic + 3/8" changes.
RFI-W1-5 | W1-10 (A5, grid 5 west of 122): W14x30 on grid 5 has its axis ~9.6 pt (~6") east of the wall axis; flange edge within ~1" of the stud. Taken to deck (15'-4 1/2"), not stops_under_beam. | If it stops under W14x30: -1.150 ft x studs on 11.0 ft of wall (~10 studs = -11.5 LF of 6" stud).
RFI-W1-6 | Electrical 120 and NER 121 show no ceiling tag in A04.01; W1-8 east faces there taken to underside of structure/beam (53.3). | If an 8'-6" ceiling is intended: -(11.821-9.0) x 13.333 ft = -37.6 SF of 5/8" board.
RFI-W1-7 | Door R.O. not printed: doors 111, 116, 118A, 118B, 119, 122 (A00.30 3'-0" type A, HM frame 2" per 11/A12.02) taken as R.O. 3'-4" (also 60 pt between wall ends on A02.01). R.O. equals the 3'-4" limit of the SINGLE TRACK row in 7/S5.20. | If R.O. > 3'-4": DOUBLE TRACK 18 ga (2 pieces): +4.667 LF of header track per door (6 doors = +28.0 LF).
RFI-W1-8 | W1-11a east face: ceiling changes from ACT-4 11'-6" (Central Zone) to ACT-4 9'-0" (CSR queue) at a band near y=1111-1118 pt on A04.01 (no printed dimension); split taken at 1115 pt. | +/-0.2 ft of face length moves 2.5 ft of board height: about +/-0.5 SF.
RFI-W2-1 | Partition type C1 (6/A12.01) does not label its top condition (studs reach a top line, board shows a break mark). Taken to underside of structure (deck) for all C1 chase faces, furrings and column/pier enclosures. Confirm whether C1 stops at ceiling + 6". | If C1 stops at ceiling + 6": 3 5/8" stud -237.9 LF (studs @ 16") and 5/8" board -190.0 SF (of which MR -78.3 SF at the restroom chase), track and bracing unchanged; per element: W2-12 9.973 ft x 3.923 ft; W2-13 9.973 ft x 3.892 ft; W2-14 10.0 ft x 3.875 ft; W2-15 2.98 ft x 3.924 ft; W2-16 3.267 ft x 4.875 ft; W2-17 2.967 ft x 4.875 ft; W2-18 4.0 ft x 4.875 ft; W2-19 2.407 ft x 4.875 ft [INTEG: the pier interior parts are the 3-5/8" parts of EX-12 / EX-13 (W2-16 / W2-17 deleted, PRIORIDAD_parches).]
RFI-W2-2 | Tag B2K (A02.01, Office 108 / cash window customer alcove, 1.77 ft hatched) is not in the A12.01 partition schedule. Composition derived as B2 (1/A12.01: 6" stud, 5/8" each face, 7 1/4") + K panel (4/A12.01: 3/8" UL752 level-2 fiberglass to 8'-0", 3/8" gyp above) = 7 5/8", which closes with A5K (7 5/8") and with the plan (11.52 pt = 7.68"). Stud gauge taken from 4/A12.01 (14 ga, @ 24" O.C. max) at 16" O.C.; customer (ballistic) side assumed = alcove side. Confirm type, spacing and customer side. | Spacing @ 24" instead of 16": -1 stud x 15.375 ft = -15.375 LF 6" 14 ga; customer side swapped: no quantity change (same wall length); if B2K were plain B2: ballistic -14.187 SF, 3/8" gyp -13.078 SF, studs 20 ga instead of 14 ga [INTEG: length decided 2.207 ft by image (vector to G wall W3-13 start), resolucion_W2 item 22.]
RFI-W2-3 | Interior 6" studs (type B2) gauge not printed: 7/S5.20 lists 600S137-33 @ 16" O.C. under 'EXTERIOR WALLS' while S1.11 calls exterior studs 600S162-54. Assumed 600S137-33 (33 mil) for interior B2. Confirm gauge. | Gauge change only (no LF change): B2 walls W2-7..W2-10 6" stud LF priced 33 mil vs 43/54 mil
RFI-W2-4 | C1 tags at the two storefront piers (A02.01 grid 2/F and 4/F) point to piers detailed in 1/A09.25 and 2/A09.25 (3 5/8" metal framing + 5/8" gyp inside, 6" CFMF + 5/8" FRT nailbase + composite metal panel outside). This fragment carries only the interior C1 part (3 5/8" + 5/8" gyp faces); the 6" CFMF and exterior layers belong to the exterior/pier scope. Confirm that the C1 tag refers to the interior furring only. [INTEG: interior C1 part counted once as parts[1] of EX-12 / EX-13 (tag C1); W2-16 / W2-17 deleted (PRIORIDAD_parches, OTH wins).] | If the whole pier is counted under C1: add the 6" CFMF studs drawn in 1/A09.25 and 2/A09.25 x 15.375 ft to this type (no change to the project total if the exterior scope already carries them; double count otherwise)
RFI-W2-5 | C1 furring return of W2-15 (PT0036): one east return of about 7" that abuts a wall of another type; PT3 adds jogs only when they touch a wall of the same type. Not added. (W2-14 returns closed: added per PT3, resolucion_W2 item 23.) | Add W2-15 return: +0.58 ft (+7.496 SF board, +1 stud x 12.924 ft)
RFI-W2-6 | S2.20 shows an unlabelled steel member on grid 4 just south of line E (about 2.5 ft long, lw 1.56) and a STL SUPPORT ref. 3/S5.11 line over B2 wall W2-7 (ATM Room 102 east). Size not printed: wall carried to B.O.D. 15'-4 1/2". Confirm whether W2-7 stops under that member and its depth. | If W2-7 stops under a member of depth d over 2.5 ft: studs -ROUNDUP(2.5/1.333)+1 = 3 studs x d; board -2 faces x 2.5 ft x d
RFI-W2-7 | F wall (W2-20) runs 30 deg off the E-W deck flutes (S2.20). Purlin (track to deck) not carried because the wall is not parallel to the flutes; confirm top-track attachment detail across flutes. | If purlin is required: +0.75 x 17.762 = 13.321 LF purlin
RFI-W2-9 | vigas_sobre_walls.py (S2.20 over A02.01) finds a W8x10 along B wall W2-2 and a W14x22 along B wall W2-3 over their west 5.29 ft only (45 %), and a W14x22 joist on grid 7 over B2 wall W2-10 (99 %). W2-10 stops under the W14x22 (E26); W2-2 / W2-3 are kept to B.O.D. as one run. Confirm whether the west parts of W2-2 / W2-3 stop under those members. | If they stop under: W2-2 studs ROUNDUP(5.29/1.333)+1 = 5 x -0.657 ft = -3.3 LF and board -2 x 5.29 x 0.657 = -6.9 SF; W2-3 5 studs x -1.142 = -5.7 LF and board -2 x 5.29 x 1.142 = -12.1 SF
RFI-W2-8 | Low roof (grids A-B) B.O.D. taken as a linear slope from 13'-0 5/8" at grid B to 12'-6 3/8" at grid A (S2.20 labels and SLOPE arrow); heights of B/B2/C1 walls in that zone are interpolated by position. Confirm B.O.D. elevations at the restroom / electrical / work room walls. | Each 1" of B.O.D. error = 0.083 ft x studs of each wall (W2-1..W2-6, W2-8..W2-10, W2-12, W2-13, W2-15) and 0.083 ft x L x faces of board
RFI-W3-1 | CONT. BOX BEAM (8/A12.01, 9/A12.01) over the office fronts has no printed run length. Carried one continuous run per front (E22) from the first to the last vendor jamb: E (grid 7, Offices 105-108) 39.97 ft, W (grid 4, Offices 109-110) 18.51 ft, x 4 pieces, + 1'-4" bearing (E1). Confirm run extent. | Full front length instead (E 42.73 ft / W 22.02 ft): +11.02 LF (E) and +14.05 LF (W) of box pieces. One box per opening instead (7'-6" each): -23.9 LF (E) and -8.7 LF (W). FRT plywood at the box bottom follows the same run.
RFI-W3-2 | Vendor frame head height: 7/A11.01 (east front) prints 8'-0 1/2" HOLD TYP. FROM SLAB; 8/A11.01 (west front) prints 8'-0" CLEAR FINISHED OPENING with no HOLD label. Carried 8'-0" for the west bulkheads (printed on their own elevation) and 8'-0 1/2" for the east bulkheads. | West at 8'-0 1/2": bulkhead height -0.042 ft -> about -2.5 SF of 5/8" board and -1.2 LF of 1-5/8" studs; jamb sealant, plywood and corner bead -0.17 LF each.
RFI-W3-3 | The east office front (grid 7) sits under S2.20 steel joists: W12x14 on grid 7 (F-E) and W14x30 (E-B), the W14x30 drawn 3.9 in east of grid 7 so its flange covers only the office-side stud row. Carried stops_under_beam (E26) for all east front stubs and bulkheads: 14.38 ft under the W12x14 and 14.23 ft under the W14x30, with bulkheads = these heights - 8.04 ft HOLD. Confirm the top of the bulkhead/stub framing at these joists. | E-B part to B.O.D. instead (W3-4, W3-5, W3-8, W3-9): +1.15 ft x 43 studs = +49.5 LF of 1-5/8" and +85.5 SF of board. F-E part to B.O.D. as well (W3-1, W3-2, W3-3, W3-6, W3-7): +0.99 ft x 55 studs = +54.5 LF and +95.8 SF.
RFI-W3-4 | Members partly over G/G1 walls (E26): W3-10 (demising 105/106) has a W8x10 over its east 3.36 ft of 11.77 ft. W3-14 (north wall of 109) has a W12x19 (HI) over 3.02 ft and a W8x10 over 3.82 ft of 12.33 ft. W3-18 is touched only by a W10x12 flange edge (about 0.35 in). Carried full B.O.D. 15'-4 1/2" for the whole length (more material). | Stopping under the members: W3-10 -3.9 LF of studs and -8.8 SF of board. W3-14: -6.1 LF and -12.2 SF (W12x19), plus -3.9 LF and -10.0 SF (W8x10).
RFI-W3-5 | B.O.D. in the S2.20 bay E-B (grids 3.4-8) is not tagged. S2.20 tags 15'-4 1/2" NO SLOPE only in bay F-E and carries a '@ LOW ROOF' label in bay E-B, but S1.14 and A02.02 show F-B as one HIGH ROOF, and H/A09.23 shows T/STEEL 15'-4 1/2". Carried 15'-4 1/2" for bay E-B. | Per 1 ft of B.O.D. difference in bay E-B: about +/-199 LF of 1-5/8" studs (199 stud pieces) and +/-392 SF of 5/8" board on W3-4, 5, 8, 9, 12-21.
RFI-W3-6 | Four office-front stubs have no tag: W3-1 (north end of 105, 2.42 ft), W3-5 (4" at 108), W3-15 (4" at 109) and W3-17 (south end of 110, 3.18 ft). A02.01 note A makes untagged partitions type A1, but the drawn thickness and graphic match the tagged front stubs (G east 6-1/8", G1 west 8") and 10/A12.01. Carried as G / G1. Alternative (merged RFI-b3-1): stubs W3-1 / W3-17 are vendor office front (Div 08), not framed. | As A1 (single row 3-5/8", 1 layer per face, 6.27 ft total): about -417 LF of 1-5/8" studs, +209 LF of 3-5/8" studs and -187 SF of 5/8" board. Vendor alternative: -2.42 LF G and -3.18 LF G1.
RFI-b3-2 | Office front stubs: the east front (grid 7) is tagged G and the west front (grid 4) G1 although both are drawn as the same office-front stub condition (10/A12.01). Types carried as tagged. | 0 LF (type attribution only; G and G1 rows of the Partition Takeoff swap if unified)
RFI-b3-3 | Office front stubs between the 7'-6" openings are not dimensioned; lengths taken from the A02.01 vector (W3-2 3.4667, W3-3 3.2533, W3-4 3.2533, W3-16 3.5067 ft). | +/-1" per stub = +/-0.083 LF x 2 rows each (1-5/8" stud row LF unchanged unless a stud is added)
RFI-RW1-1 | Drinking fountain alcove back wall (A1 default, A02.01 x 1092-1100 pt): S2.20 W14x22 on grid 3 has its axis ~4" west of the wall axis; vigas_sobre_walls.py flags it. Taken as stops_under_beam (E26). Confirm. | To deck instead: +4.57 LF 3-5/8" stud.
RFI-RW1-2 | Door 116 (A02.01 grid 7, between A5 PT0017 north and B2 PT0027 south): which partition type frames the opening/head? Plan does not say. | 3.333 LF A5 vs B2 in the Partition Takeoff; no framing change.
RFI-FO-UU | Canopy soffit linear recessed fixtures UU1-UU6 (Coronet LSR-WET-2.5, E00.01): framed opening width taken as the 2.5 in catalog body; the end/trim width is not printed. Confirm cutsheet. | +/- 2 ends x qty per 1 in of width: +/- 3.5 LF total (21 fixtures x 2 x 1/12 ft)
RFI-ADV-1 | Ceiling transitions 7/A09.33 (CE-1..CE-4) and CSR soffit drop sides 10/A09.33 (CE-5..CE-8): face heights are not dimensioned (only the 6" laps). Carried every board face drawn in 7/A09.33 (upper-room face to upper ceiling + 6", 6" lap above the lower ceiling and the 3 5/8" bottom return) per 53.3. Confirm whether the inner 6" lap and the bottom return are boarded. | Outer faces only (upper-room face of CE-1..CE-4 + drop face of CE-5..CE-8): -65.85 SF 5/8" regular (194.22 -> 128.37 SF), plus screws / mud / tape by yield.
RFI-ADV-2 | CSR soffit blocking conflict: 10/A09.33 'PROVIDE FRTW BLOCKING FOR FUTURE' draws two FRTW pieces (3 1/2" and 5 1/2" x 1 1/2") on the soffit; 9/A12.08 CSR LINE SECTION labels '5/8" FIRE TREATED PLYWOOD BLOCKING' (carried, 12.021 LF). Which governs, or both? | If 10/A09.33 governs: +12.02 LF FRT blocking (2 pieces x 12.021 instead of 1); if both: +24.04 LF.
RFI-ADV-3 | A1 wall W1-1 north face (104 Waiting) is boarded full length at 11.5 ft, but the C1 display box W2-14 (A02.01 printed 10'-0" x 8", key note 7) stands against it and is boarded on its own face to deck: the A1 face inside the box is hidden (possible double board). Same item as back-check suspicion 3. Confirm whether the A1 face behind the C1 furring is boarded. | If not boarded: -107.3 SF 5/8" regular (9.33 ft inner length by vector x 11.5) up to -115.0 SF (printed 10'-0" x 11.5); back-check estimate about -130 SF.
RFI-ADV-4 | Office-front CONT. BOX BEAM (8/A12.01, 9/A12.01): member size not printed; carried as 1-5/8" box (C + track), headers OF-E 39.97 ft and OF-W 18.51 ft x 4 pieces (E11). | 0 LF; member size / price only (e.g. 3 5/8" or 6" box instead of 1-5/8").
RFI-ADV-5 | GL-2 window sills (10/A09.27): BRAKE METAL SILL over 3/4" FRT PLYWOOD, the interior 5/8" gypsum stops under the sill (no gypsum return at the sill; JAMB RETURN BEYOND refers to the jambs; 11/A09.27 draws the return at the head). CONFIRMED on the drawing but NOT applied: the canon schema adds the sill edge to the jamb return whenever with_sill is true, and with_sill also drives the double sill track (E18, 2/S5.20). Tool change needed (sill edge flag). Also: A1/A3 moved head_ft (storefront wall jambs to 9'-4 1/2") and sill_ft (windows to 6'-4 1/2"), which the tool reuses for the return edges. | Gypsum board jamb return: -24.0 SF (6 windows x 8.0 LF sill edge x 0.5) and -0.875 SF (SF-F/SF-W wall jambs measured to the HSS top instead of T/OPENING 8'-6") and -0.75 SF (window jambs from T/STUD instead of B/OPENING) = -25.63 SF; metal trim (corner + casing) -102.5 LF.
RFI-ADV-6 | Exterior 6" CFMF gauge conflict (56.2): S1.11 LIGHT GAUGE STEEL FRAMING note 5 '600S162-54 @ 12" O.C. within 6 ft of building corners / all other exterior studs 600S162-54 @ 16" O.C.' vs 7/S5.20 METAL STUD PROPERTIES 'EXTERIOR WALLS 600S137-33'. The take-off carries the heavier 600S162-54 for the exterior 6" studs [DERIVED] (the canon already applies S1.11 for the 12" zones; same note). 6" interior studs (A5, B2, B2K) stay 600S137-33. Confirm gauge. | 0 LF. Weight: exterior 6" studs 3153.56 LF (studs_out.json, EX-1..EX-11; gauge_6in.json) x (1.929 - 1.101) = 0.828 lb/LF = -2,611 lb if 600S137-33 governs (+ pier exterior L EX-12/EX-13 2 x 5 x 14.358 = 143.6 LF x 0.828 = -119 lb). Weights: A = t x (6 + 2 flange + 2 lip - 4t) x 3.40 lb/ft/in2, t 0.0566 / 0.0346 in (SSMA design thickness), approximate; Material Summary line must read 600S162-54 for exterior CFMF.
RFI-ADV-7 | S2.20 grid 2: one member line (between the column boxes, F to E) carries 'HSS9x5x5/8 (LLV) B.O.S. EL. 8'-7 1/2"', 'W16x26 (CANOPY)' and 'W12x19 (HI)'. The HSS extent is not dimensioned: it may span the whole F-E bay (under the solid part of EX-2 north of SF-W, about 15.0 ft), not only SF-W. The E-D bay (DU ATM) is labelled W12x19 only. Confirm HSS extent. | If the HSS spans F-E: about 11-13 EX-2 studs split at the HSS: about -10 LF 6" stud and +30 LF track (bottom + top at the HSS, 2 x 15.0).
RFI-ADV-8 | GL-2 window heads 11/A09.27 'METAL STUD BOX BEAM OR STEEL FRAMING AS REQUIRED': box depth and shim not dimensioned (1 1/2" shim + 3/4" FRT plywood + about 6" box drawn). Cripples are carried from T/OPENING 8'-6"; real start about 9'-2 1/4" on top of the box. | 6 windows x 6 cripples x -0.6875 = -24.8 LF 6" stud (door 123 and DU ATM similar, about -2 LF).
RFI-ADV-9 | S1.11 LGS note 5 '6 FT OF BUILDING CORNERS' @ 12": basis of the corner zones is inconsistent between walls. RFI-EX-17 says convex corners only, but EX-4 carries 12" from the re-entrant corner F/4 (only justified by distance to the convex corner G/4, about 1.67 ft away); on the same distance logic EX-10 (4.51 ft from convex corner D/2) would carry 12" over about 3.95 ft. The RFI-EX-17 delta also counts EX-3, already all @12". | Distance criterion: EX-10 +1 stud (+14.4 LF 6" stud); strict convex criterion: EX-4 -1 stud (-13.9 LF).
RFI-ADV-10 | Canopy fascia box 7/A09.26: the 5/8" EXT. GRADE FRT PLYWOOD hatch is drawn on the outer face, the bottom (about 0.36 ft) and the inner face above and below the C channel (about 0.55 ft); the canon carries the outer face only (L x 1.865). Widths not dimensioned. | +0.9 ft x 241.5 LF of fascia (EX-31..EX-38) = about +217 SF 5/8" ext. grade FRT plywood.
RFI-ADV-11 | Pier 4 exterior east face at the G-F step (about 1'-0", the same step the canopy soffit EX-44 counts): not in any facade (S-HP covers the G front only; S-LP starts at the pier face on line F). Not dimensioned. | +17.2 SF nailbase (1.0 x (19.167 - 1.979)) and +2.5 SF glass mat (1.0 x (0.5 + 1.979)).
RFI-ADV-12 | VH-2 (EX-40) on grid 4: S2.20 draws a member on grid 4 (W12x19 (HI)); registered to A02.01 the flange and the EX-40 head band touch by about 0.6 pt. EX-40 carries no stops_under_beam. Confirm whether the vestibule head stops under the W12x19. | If under the beam: EX-40 height 6.708 -> 5.691: 6 x -1.017 = -6.1 LF 3-5/8" stud (W2-18 on the same grid, other scope, similar).
RFI-ADV-13 | Canopy soffit sheathing material: 7/A09.26 SECTION DETAIL @ SIDE CANOPY labels the soffit '5/8" PORTLAND CEMENT PLASTER SYSTEM (PT-4) ON (2) LAYERS GRADE 'D' BUILDING PAPER ON 5/8" EXT. GRADE FRT PLYWOOD SHEATHING ON 3 5/8" METAL STUD FRAMING' (3/A09.26 entrance canopy same product); the canon carries it as frt_5_8_ext (canopy soffits S 276.6 + E 161.6 + N 84.8 + drive-up 1098.4 = 1621.4 SF). 4/A09.33 and 5/A09.33 (canopy linear light) label '5/8" EXTERIOR SHEATHING ON 3 5/8" CFMF @ 16" O.C. / 5/8" CEMENT PLASTER SYSTEM'. Which product at the canopy soffits? | If exterior gypsum sheathing: -1621.4 SF 5/8" ext. grade FRT plywood / +1621.4 SF 5/8" EXTERIOR gyp sheathing (no total SF change).
RFI-ADV-14 | Back-check suspicion: east canopy soffit joists 37 vs 41 if the run were the full east fascia 52.583 ft. Re-checked on A02.02: the east fascia chain is 5'-2 1/2" (SE corner, inside the south canopy soffit, whose area already includes the SE corner 3.41 x 4.95) + 47'-4 1/2" (east soffit run). The east soffit run is 47.375 ft -> ROUNDUP(47.375/1.333)+1 = 37. Answered by the drawing; listed for traceability only. | 0 (adding the 5'-2 1/2" corner to the east run would count the SE corner joists twice: +13.6 LF 3-5/8" not justified).
RFI-ADV-15 | Roof step 4/A02.02 gypsum faces and nailbase (added after the adversarial check): row heights are not dimensioned (row 1 top RFI-EX-22; rows 2/3 from S2.20 T/STEEL and AISC depth) and the bottom soffit width 1.291 ft is measured on the vector (1 1/2" = 1'-0"). | Per +/-0.25 ft of row 1 height: +/-12.9 SF nailbase; per +/-0.1 ft of soffit width: +/-5.2 SF 5/8" regular.
RFI-CANON-1 | Bracing: 178.95 LF of C.R. channel crosses openings with no studs (53.4 literal). Delta if not run across openings: -178.95 LF | -178.95 LF
RFI-CANON-2 | Bottom track: 47.16 LF of door R.O. not deducted (E10). Delta if deducted: -47.16 LF | -47.16 LF

## Review Items
# | Item | Sheet + detail | Image
1 | Stage 3 estimator item (W1 #17): A = door 116 R.O. 3.333 ft in openings_extra (jamb_wall W1-12, A5) and again (jamb_wall W2-10, B2) ¦ B = RFI-b1-1: opening counted in neither type ¦ delta: Duplicate removed (one door). Partition Takeoff LF of the opening: +3.333 LF A5 or +3.333 LF B2 (both 6" studs, 7 1/4"; framing identical, header SINGLE TRACK 7/S5.20). Taken in neither type's LF; tracks carried by openings_extra. | see work/etapas/3_revision/resolucion.md | /home/user/boa18a/work/agentes/R_W1/img/it8_17_18_breakroom.png
2 | Stage 3 estimator item (W1 #57): A = RW1-2 stops under W14x22 grid 3 (tool flag): stud 11.807 ft ¦ B = - ¦ delta: If taken to deck: +1.142 ft x 4 studs (4.073 ft @16" + 1) = +4.57 LF of 3-5/8" stud (RFI-RW1-1: beam axis 1089.53 pt is 6.5 pt (4.3") west of the wall axis; flange overlaps the stud ~0.5"). | see work/etapas/3_revision/resolucion.md | /home/user/boa18a/work/agentes/R_W1/img/it57_59_fountain.png
3 | Stage 3 estimator item (W2 #alert 5 / alert 10 (B2K)): A = W2-11 B2K, composition derived B2 (1/A12.01) + K panel (4/A12.01), 7 5/8" ¦ B = b2-9 B2K read as B2 + Kevlar per A1K/A5K pattern ¦ delta: Type not in A12.01 schedule: RFI-W2-2 kept. Length resolved by image = 2.207 LF (item 22). If B2K were plain B2 without K panel: -2.207 ft x 8.0 ft UL752 panel per face side (-17.7 SF ballistic) ; @24" O.C. instead of 16": -1 stud x 15.375 ft | see work/etapas/3_revision/resolucion.md | /home/user/boa18a/work/agentes/R_W2/img/z_b2k.png
4 | Stage 3 estimator item (W2 #37/61 height (pier interior parts)): A = W2-16 / W2-17 height 15.375 ft (to deck, RFI-W2-1) ¦ B = EX-12 / EX-13 (same piers, EXT/OTH) height 14.358 ft (B.O.D. - W12x19, E26) ¦ delta: Same pier, two heights: if the interior 3 5/8" L also stops under the W12x19: -1.017 ft x 10 studs = -10.2 LF 3 5/8" stud; board -1.017 x (3.267 + 3.646) = -7.0 SF | see work/etapas/3_revision/resolucion.md | /home/user/boa18a/work/agentes/R_W2/img/ctx_vest.png
5 | Stage 3 estimator item (W2 #35): A = W2-6 type B 3.5 ft (PA0034 small boxed B, no leader) ¦ B = b1-16 type A1 default 3.5 ft ¦ delta: 0 LF; type only: B to underside of structure (12.743 ft) vs A1 to ceiling + 6" -> stud/board height on 3.5 ft | see work/etapas/3_revision/resolucion.md | /home/user/boa18a/work/agentes/R_W2/img/z_storage117.png
6 | Stage 3 estimator item (INTEG #INTEG-1 (DU ATM recess width)): A = A_ACC atm_recess width 4.5 ft (surround SUR54), furring rows 2; A_EXT opening atm_recess width 2.208 ft (R.O.), furring 0 ¦ B = - ¦ delta: Carried 5.177 ft = sistered 2 1/2" zone drawn on 7/A08.11 (vector): 5 studs x 6.0 + 2 x 5.177 = 40.35 LF. Surround 4.5: 39.0 LF (-1.35); R.O. 2.208 without furring: 18.0 LF (-22.35). RFI-ACC-7. | see work/etapas/3_revision/resolucion.md | /home/user/boa18a/work/agentes/INTEG/img/a0811_7du.png
7 | Stage 1 inventory (49 partition tags + B2K on A02.01): numbered list + circled image of every location in 1_inventario/inventario.md - confirm the list is complete (unattended mode). | A02.01; 2/A09.26; S2.20 | work/etapas/1_inventario/recortes/OVERVIEW_A02.01_p24.png
8 | Wall partition rule used: particion.py default mode (straight segment, PT2/PT3). Another session asked for the 'run' mode; not applied (see review note 02). | A02.01; 2/A09.26; S2.20 | work/etapas/1_inventario/recortes/OVERVIEW_A02.01_p24.png
9 | Storefront heads SF-W, SF-F, SF-100 carried as steel by others (S2.20 HSS9x5x5/8 LLV; E16); 6" CFMF to deck above them is in the EXT walls (2/A09.26). | A02.01; 2/A09.26; S2.20 | work/etapas/1_inventario/recortes/OVERVIEW_A02.01_p24.png

## Scope Checklist
Scope ID | Scope | Status | Note (quantity, NOT APPLICABLE + sheet, or RFI)
ALC-01 | Interior partition framing (studs + tracks) | QUANTIFIED | Quantified: family '3-5/8" stud (all gauges)' in Material Summary; sheets A00.00, A02.01, A02.02, A03.01, A08.11, A08.21, A09.21, A09.22
ALC-02 | Exterior wall framing (CFMF) | QUANTIFIED | Quantified: family '6" stud (all gauges)' in Material Summary; sheets A08.21, A09.21, A09.22, A09.23, A09.25, A09.33, E04.01, S1.10
ALC-03 | Parapet framing | QUANTIFIED | Quantified: family '6" parapet stud' in Material Summary; sheets A02.02, A09.01, A09.02, A09.21, A09.22, A09.23, A09.26, S5.10
ALC-04 | Top / deflection and bottom track | QUANTIFIED | Quantified: family 'bottom track (all)' in Material Summary; sheets A12.01, M00.03, S1.11, S5.10, S5.20
ALC-05 | Headers, sills and jambs at openings | QUANTIFIED | Quantified: family 'header / box beam' in Material Summary; sheets A00.30, A08.21, A09.25, A09.26, A09.27, A09.30, A12.01, A12.02
ALC-06 | Bracing / bridging | QUANTIFIED | Quantified: family 'bracing C.R. channel' in Material Summary; sheets A09.33, S1.10, S1.11, S5.10, S5.20
ALC-07 | Gypsum board on walls (layers per type) | QUANTIFIED | Quantified: family '5/8" gyp board regular (walls + ceilings)' in Material Summary; sheets A00.00, A02.02, A08.01, A08.11, A08.21, A09.25, A09.26, A09.27
ALC-08 | Moisture / abuse / special board at wet zones | QUANTIFIED | Quantified: family '5/8" gyp MOISTURE RESISTANT' in Material Summary; sheets A08.01
ALC-09 | Exterior gypsum / glass mat sheathing | QUANTIFIED | Quantified: family '5/8" glass mat sheathing' in Material Summary; sheets A09.21, A09.22, A09.23, A09.26, A09.27, A09.33
ALC-10 | FRT plywood sheathing / substrate | QUANTIFIED | Quantified: family 'FRT plywood (SF)' in Material Summary; sheets A00.00, A02.01, A02.02, A03.01, A08.11, A08.21, A09.21, A09.22
ALC-11 | Gypsum board ceilings | QUANTIFIED | Quantified: family '5/8" gyp board regular (walls + ceilings)' in Material Summary; sheets A04.01
ALC-12 | Ceiling suspension (furring / carrying channel / hanger wire / ceiling track) | QUANTIFIED | Quantified: family 'furring channel' in Material Summary; sheets A04.01, A09.33, M00.01, M00.02, P00.01
ALC-13 | Soffits and bulkheads (framing + board) | QUANTIFIED | Quantified: family 'ceiling / soffit track' in Material Summary; sheets A04.01, A05.01, A09.01, A09.02, A09.27, A09.33, A12.01, A12.08
ALC-14 | Canopy / marquee framing and sheathing | QUANTIFIED | Quantified: family 'FRT plywood (SF)' in Material Summary; sheets A00.60, A02.02, A09.01, A09.02, A09.21, A09.22, A09.23, A09.25
ALC-15 | Column furring / wraps | QUANTIFIED | Quantified: family '6" stud (all gauges)' in Material Summary; sheets A09.25 (5/A09.25 canopy column wraps CANOPY-COL)
ALC-16 | Blocking (FRT wood / metal) for millwork and accessories | QUANTIFIED | Quantified: family 'FRT blocking' in Material Summary; sheets A00.00, A00.30, A02.01, A02.02, A03.01, A04.01, A08.01, A08.21
ALC-17 | Framed openings (MEP, access panels, diffusers) | QUANTIFIED | Quantified: family 'framed openings MEP' in Material Summary; sheets A04.01, M00.01, P00.01
ALC-18 | Trim: corner bead, casing bead, control joints, reveals | QUANTIFIED | Quantified: family 'metal trim (corner bead, casing, shadow molding)' in Material Summary; sheets A00.00, A08.21, A09.01, A09.02, A09.22, A09.26, A09.31, A09.33
ALC-19 | Acoustical sealant / sound attenuation | QUANTIFIED | Quantified: family 'acoustical sealant' in Material Summary; sheets A12.01
ALC-20 | FRP / cement board / tile backer | QUANTIFIED | Quantified: family 'FRP' in Material Summary; sheets A05.01, A08.01, A09.26, A09.27
ALC-21 | Shaft walls / area separation walls | NOT APPLICABLE | NOT APPLICABLE: no shaft / area separation wall in the bid set (alcances scan 0 hits; A12.01 partition schedule has no shaft type)
ALC-22 | Rated assemblies (UL designs) and their board type | NOT APPLICABLE | NOT APPLICABLE: A12.01 partition schedule FIRE RATING and U.L. NUMBER columns are '--' for every type; A02.01 note 6 / E02.02 note 29 fire-rated plywood backboards are carried in 3/4" FRT plywood; E04.02 / M00.01 / M00.03 / E00.01 / A05.01 are generic firestop / paint notes (penetrations by MEP trades)
ALC-23 | Special panels (ballistic, lead-lined, abuse) | QUANTIFIED | Quantified: family 'ballistic panel' in Material Summary; sheets A12.01
ALC-24 | Finish level (Level 4 / Level 5) | QUANTIFIED | Quantified: family 'Level 5 finish' in Material Summary; sheets A00.40, A05.01
ALC-X25 | batt insulation | NOT APPLICABLE | EXCLUDED (estimator criterion: no insulation)