## Inputs
Bank of America CO1-111 Broomfield, CO ¦ METAL FRAMING & DRYWALL TAKEOFF
Bid set: 2025.08.26_CO1-111_Broomfield_PERMIT SET_BID SET.pdf · 2026-10-21 · Edit ONLY the yellow cells.
PARAMETER | VALUE | NOTE / SOURCE
Waste - ALL METAL, any type | 0.15 | Estimator standing rule: 15% on everything that is metal.
Waste - EVERYTHING THAT IS NOT METAL | 0.06 | Estimator standing rule: same figure as board.
Board sheet width (ft) | 4 | Sheet size is a parameter; buy the size that wastes least.
Board sheet length (ft) | 12 | Change it and every sheet count re-rounds.
SF per board sheet | 48 | Width x length.
Stud stock length (ft) | 20 | Stud, header, framed opening and stud blocking: sticks.
Track stock length (ft) | 10 | Track, sill track and purlin: runs.
Floor plan scale (pt/ft) | n/a | Project value (canon constants).
B.O. Deck (ft) | n/a | Project value (canon constants).
T.O. Parapet (ft) | n/a | Project value (canon constants).
Sealant coverage (LF per tube) | 25 | Sealant yield per tube - set your supplier's figure.
C.R. channel stock length (ft) | 16 | 1-1/2" cold-rolled channel (bracing, carrying channel).
Hat / furring channel stock (ft) | 12 | 7/8" hat furring channel.
Trim stick length (ft) | 10 | Corner bead, casing bead, shadow molding, PVC trim.
Hanger wire purchase | continuous coil (LF) | Bought by LF from a continuous coil; the hanger count goes on its own PCS row.
Drywall screws per SF of board | 1.2 | YIELD (GA-216 field / perimeter spacing).
Framing screws per stud piece | 4 | YIELD: 2 per stud-to-track connection, each end.
Power-driven pin spacing (ft) | 1 | YIELD: bottom track on slab, interior walls.
Joint compound (lb per SF) | 0.072 | YIELD: 72 lb per 1,000 SF, level 4 (estimator criterion).
Joint tape (LF per SF) | 0.37 | YIELD: 370 LF per 1,000 SF.
Expansion anchor spacing (ft) | 0.6667 | YIELD: exterior bottom track on slab.

## Partition Takeoff
ORGANIZED PARTITION TAKEOFF - Bank of America CO1-111 Broomfield, CO
Grouped by partition type. Every row cites its DETAIL/SHEET and its status.
Partition / Scope | Wall # | Length (LF) | Height (FT) | Layers | Stud Size | Stud O.C. (in) | Board (SF) | Location | Source (DETAIL/SHEET) | Status
TYPE EXT-6CFMF
EXT-6CFMF #A-EXT-UP-N-F47+A-EXT-N-F+A-EXT-UP-N-F78 - North facade grid F from pier G/4 to the NE corner (over storefront SF-F-4/8 and Office 105 wall A-EXT-N-F): infill row above the canopy beam up to the roof beam + North exterior wall, grid F between 7 and 8 (Office 105), from storefront SF-F-4/8 east jamb to the NE corner | A-EXT-UP-N-F47+A-EXT-N-F+A-EXT-UP-N-F78 | 53.458 | 4.216 | 0.25 | 6" | 16 | 209.2 | North facade grid F from pier G/4 to the NE corner (over storefront SF-F-4/8 and Office 105 wall A-EXT-N-F): infill row above the canopy beam up to the roof beam + North exterior wall, grid F between 7 and 8 (Office 105), from storefront SF-F-4/8 east jamb to the NE corner | C/A09.21 | [DERIVED]
EXT-6CFMF #A-EXT-E-8+A-EXT-UP-E-8 - East exterior wall, grid 8 from the NE corner (inside face of A-EXT-N-F) to the SE corner (inside face of A-EXT-S-A); Offices 105-108, Cash Window 116, Future FCAM, Work Room 119 + East facade grid 8 from the NE corner (inside face of A-EXT-UP-N-F) to grid B.2 (end of the canopy): infill row above the canopy beam up to the W12x19 (HI) roof beam; Offices 105-108, Cash Window 116 | A-EXT-E-8+A-EXT-UP-E-8 | 122.17 | 7.987 | 0.62 | 6" | 16 | 1030.2 | East exterior wall, grid 8 from the NE corner (inside face of A-EXT-N-F) to the SE corner (inside face of A-EXT-S-A); Offices 105-108, Cash Window 116, Future FCAM, Work Room 119 + East facade grid 8 from the NE corner (inside face of A-EXT-UP-N-F) to grid B.2 (end of the canopy): infill row above the canopy beam up to the W12x19 (HI) roof beam; Offices 105-108, Cash Window 116 | D/A09.22 | [DERIVED]
EXT-6CFMF #A-EXT-S-A - South exterior wall, grid A from the SW corner (exterior face of A-EXT-W-3) to the SE corner (exterior face of A-EXT-E-8); Wellness 115, Corridor 111 (door 123), NER 121, Break Room 118, Work Room 119 | A-EXT-S-A | 53.667 | 11.172 | 1 | 6" | 16 | 645.3 | South exterior wall, grid A from the SW corner (exterior face of A-EXT-W-3) to the SE corner (exterior face of A-EXT-E-8); Wellness 115, Corridor 111 (door 123), NER 121, Break Room 118, Work Room 119 | F/A09.22 | [DERIVED]
EXT-6CFMF #A-EXT-UP-W-3+A-EXT-W-3 - West facade grid 3 from the D-line return to grid B (Offices 109-110, Restroom 114 north part): infill row above the W16x26 (CANOPY) up to the W12x19 (HI) + West exterior wall (lower), grid 3 from the D-line return (exterior face of A-EXT-S-D23) to the SW corner (inside face of A-EXT-S-A); Offices 109-110, Restrooms 114 / 113, Janitor 112, Wellness 115 | A-EXT-UP-W-3+A-EXT-W-3 | 69.058 | 8.462 | 0.68 | 6" | 16 | 625.76 | West facade grid 3 from the D-line return to grid B (Offices 109-110, Restroom 114 north part): infill row above the W16x26 (CANOPY) up to the W12x19 (HI) + West exterior wall (lower), grid 3 from the D-line return (exterior face of A-EXT-S-D23) to the SW corner (inside face of A-EXT-S-A); Offices 109-110, Restrooms 114 / 113, Janitor 112, Wellness 115 | H/A09.23 | [DERIVED]
EXT-6CFMF #A-EXT-S-D23+A-EXT-UP-S-D23 - Exterior return wall facing south under the drive-up canopy, grid D between 2 and 3 (ATM Room 102 behind) + Return wall facing south on grid D between 2 and 3 (ATM Room 102 behind): infill row above the W12x19 (CANOPY) up to the W12x19 (HI) | A-EXT-S-D23+A-EXT-UP-S-D23 | 7.813 | 6.671 | 0.5 | 6" | 16 | 60.07 | Exterior return wall facing south under the drive-up canopy, grid D between 2 and 3 (ATM Room 102 behind) + Return wall facing south on grid D between 2 and 3 (ATM Room 102 behind): infill row above the W12x19 (CANOPY) up to the W12x19 (HI) | J/A09.23 | [DERIVED]
EXT-6CFMF #A-EXT-UP-W-2SF+A-EXT-UP-W-2S+A-EXT-W-2+A-EXT-W-2M - West facade grid 2 from the NW corner (inside face of A-EXT-UP-N-G) to the D-line return: infill row above the canopy beams (W16x26 G-E, W12x19 E-D) up to the W12x19 (HI); Vestibule 100, 24 HR Vestibule 101, ATM Room 102 + West exterior wall (upper), grid 2 from the vestibule storefront SF-2-F/E.4 south jamb to the D-line return; 24 HR Vestibule 101 and ATM Room 102 (drive-up ATM) | A-EXT-UP-W-2SF+A-EXT-UP-W-2S+A-EXT-W-2+A-EXT-W-2M | 66.817 | 4.421 | 0.33 | 6" | 16 | 330.84 | West facade grid 2 from the NW corner (inside face of A-EXT-UP-N-G) to the D-line return: infill row above the canopy beams (W16x26 G-E, W12x19 E-D) up to the W12x19 (HI); Vestibule 100, 24 HR Vestibule 101, ATM Room 102 + West exterior wall (upper), grid 2 from the vestibule storefront SF-2-F/E.4 south jamb to the D-line return; 24 HR Vestibule 101 and ATM Room 102 (drive-up ATM) | J/A09.23 | [DERIVED]
EXT-6CFMF #A-EXT-UP-N-G - North facade grid G between piers G/2 and G/4 (Vestibule 100 entrance): infill row above the W12x19 (CANOPY) up to the W12x19 (HI) roof beam, over the entrance storefront SF-F-2/4 and both piers | A-EXT-UP-N-G | 17.688 | 2.41 | 0 | 6" | 16 | 0 | North facade grid G between piers G/2 and G/4 (Vestibule 100 entrance): infill row above the W12x19 (CANOPY) up to the W12x19 (HI) roof beam, over the entrance storefront SF-F-2/4 and both piers | A/A09.21 | [DERIVED]
TYPE CANOPY-COL
CANOPY-COL #A-EXT-CCOL-1 - Drive-up canopy column 1 of 4 on grid 1 (from north), A02.01 bubble 5/A09.25 | A-EXT-CCOL-1 | 5.667 | 10.5 | 0 | 3-5/8" | 16 | 0 | Drive-up canopy column 1 of 4 on grid 1 (from north), A02.01 bubble 5/A09.25 | 5/A09.25 | [DERIVED]
CANOPY-COL #A-EXT-CCOL-2 - Drive-up canopy column 2 of 4 on grid 1 (from north), A02.01 bubble 5/A09.25 | A-EXT-CCOL-2 | 5.667 | 10.5 | 0 | 3-5/8" | 16 | 0 | Drive-up canopy column 2 of 4 on grid 1 (from north), A02.01 bubble 5/A09.25 | 5/A09.25 | [DERIVED]
CANOPY-COL #A-EXT-CCOL-3 - Drive-up canopy column 3 of 4 on grid 1 (from north), A02.01 bubble 5/A09.25 | A-EXT-CCOL-3 | 5.667 | 10.5 | 0 | 3-5/8" | 16 | 0 | Drive-up canopy column 3 of 4 on grid 1 (from north), A02.01 bubble 5/A09.25 | 5/A09.25 | [DERIVED]
CANOPY-COL #A-EXT-CCOL-4 - Drive-up canopy column 4 of 4 on grid 1 (from north), A02.01 bubble 5/A09.25 | A-EXT-CCOL-4 | 5.667 | 10.5 | 0 | 3-5/8" | 16 | 0 | Drive-up canopy column 4 of 4 on grid 1 (from north), A02.01 bubble 5/A09.25 | 5/A09.25 | [DERIVED]
TYPE G
G #A-N-G-01 - Office 105 front, north stub (office front line at grid 7, east side of Central Zone 103) | A-N-G-01 | 2.42 | 14.383 | 4.42 | 1-5/8" | 16 | 147.43 | Office 105 front, north stub (office front line at grid 7, east side of Central Zone 103) | 5/A12.01 | [DERIVED]
G #A-N-G-02 - Office front stub between Office 105 and Office 106 | A-N-G-02 | 3.467 | 14.383 | 4.59 | 1-5/8" | 16 | 215.88 | Office front stub between Office 105 and Office 106 | 5/A12.01 | [DERIVED]
G #A-N-G-03 - Office front stub between Office 106 and Office 107 | A-N-G-03 | 3.253 | 14.225 | 4.63 | 1-5/8" | 16 | 201.52 | Office front stub between Office 106 and Office 107 | 5/A12.01 | [DERIVED]
G #A-N-G-05 - Office front stub between Office 107 and Office 108 | A-N-G-05 | 3.253 | 14.225 | 4.63 | 1-5/8" | 16 | 201.52 | Office front stub between Office 107 and Office 108 | 5/A12.01 | [DERIVED]
G #A-N-G-04 - Demising wall Office 106 / Office 107 | A-N-G-04 | 11.771 | 15.375 | 4 | 1-5/8" | 16 | 723.9 | Demising wall Office 106 / Office 107 | 5/A12.01 | [CONFIRMED]
G #A-N-G-06 - Demising wall Office 107 / Office 108 | A-N-G-06 | 11.771 | 15.375 | 4 | 1-5/8" | 16 | 723.9 | Demising wall Office 107 / Office 108 | 5/A12.01 | [CONFIRMED]
G #A-N-G-08 - Demising wall Office 109 / Office 110 | A-N-G-08 | 11.625 | 15.185 | 4 | 1-5/8" | 16 | 706.1 | Demising wall Office 109 / Office 110 | 5/A12.01 | [CONFIRMED]
G #A-N-G-07 - South wall of Office 108 (Office 108 / Cash Window 116 teller area) | A-N-G-07 | 10.073 | 15.375 | 4 | 1-5/8" | 16 | 619.49 | South wall of Office 108 (Office 108 / Cash Window 116 teller area) | 5/A12.01 | [DERIVED]
G #A-N-G-09 - ATM Room 102 / Office 109 (south wall of ATM Room) | A-N-G-09 | 12.333 | 15.375 | 4 | 1-5/8" | 16 | 758.48 | ATM Room 102 / Office 109 (south wall of ATM Room) | 5/A12.01 | [DERIVED]
G #A-S-G-01 - Women's Restroom 114 north wall / Office 6 CB 110, grid B | A-S-G-01 | 11.625 | 15.375 | 4 | 1-5/8" | 16 | 714.94 | Women's Restroom 114 north wall / Office 6 CB 110, grid B | 5/A12.01 | [DERIVED]
TYPE G1
G1 #A-N-G1-01 - Demising wall Office 105 / Office 106 | A-N-G1-01 | 11.771 | 15.188 | 4 | 1-5/8" | 16 | 715.08 | Demising wall Office 105 / Office 106 | 5/A12.01 | [CONFIRMED]
G1 #A-N-G1-02 - Office front stub between Office 109 and Office 110 | A-N-G1-02 | 3.507 | 15.375 | 4.81 | 1-5/8" | 16 | 238.3 | Office front stub between Office 109 and Office 110 | 5/A12.01 | [DERIVED]
G1 #A-S-G1-01 - Office 6 east office-front end stub south of DFC-1A (vendor glass), north of door 111 | A-S-G1-01 | 3.18 | 15.375 | 4 | 1-5/8" | 16 | 195.58 | Office 6 east office-front end stub south of DFC-1A (vendor glass), north of door 111 | 5/A12.01 | [DERIVED]
TYPE B2K
B2K #A-N-B2K-01 - Kevlar wall at SW corner of Office 108, west end of teller line (hatched) | A-N-B2K-01 | 1.773 | 15.375 | 2.36 | 6" | 24 | 64.36 | Kevlar wall at SW corner of Office 108, west end of teller line (hatched) | 4/A12.01 | [DERIVED]
TYPE A1K
A1K #A-N-A1K-01 - Kevlar wall north side of teller station (Cash Window 116), below Office 108 south wall (hatched) | A-N-A1K-01 | 3.417 | 15.375 | 2 | 3-5/8" | 24 | 105.06 | Kevlar wall north side of teller station (Cash Window 116), below Office 108 south wall (hatched) | 4/A12.01 | [CONFIRMED]
A1K #A-S-A1K-01 - Cash Window 116 teller pod - lower ballistic run (customer queue / Break Room 118), west of teller counter | A-S-A1K-01 | 1.767 | 12.922 | 2 | 3-5/8" | 24 | 45.66 | Cash Window 116 teller pod - lower ballistic run (customer queue / Break Room 118), west of teller counter | 4/A12.01 | [DERIVED]
A1K #A-S-A1K-02 - Cash Window 116 teller pod - south ballistic run behind teller workstations (C1 FCAM furring on south face) | A-S-A1K-02 | 3.413 | 12.935 | 2 | 3-5/8" | 24 | 88.3 | Cash Window 116 teller pod - south ballistic run behind teller workstations (C1 FCAM furring on south face) | 4/A12.01 | [DERIVED]
TYPE B2
B2 #A-N-B2-01 - East wall of ATM Room 102 at grid 4 / E (HSS column wrap + door 102) | A-N-B2-01 | 5.66 | 15.375 | 2 | 6" | 16 | 111.44 | East wall of ATM Room 102 at grid 4 / E (HSS column wrap + door 102) | 1/A12.01 | [DERIVED]
B2 #A-S-B2-01a+A-S-B2-01b - Women's Restroom 114 east wall, north piece (deck break at grid B, split of A-S-B2-01b) + Women's Restroom 114 east wall at Corridor 111, door 114 | A-S-B2-01a+A-S-B2-01b | 5.542 | 13.286 | 2 | 6" | 16 | 100.6 | Women's Restroom 114 east wall, north piece (deck break at grid B, split of A-S-B2-01b) + Women's Restroom 114 east wall at Corridor 111, door 114 | 1/A12.01 | [DERIVED]
B2 #A-S-B2-02 - Corridor 111 west wall: Men's 113 / Storage 117 / Wellness 115 east walls, doors 113, 117, 115 | A-S-B2-02 | 15.787 | 12.865 | 2 | 6" | 16 | 266.2 | Corridor 111 west wall: Men's 113 / Storage 117 / Wellness 115 east walls, doors 113, 117, 115 | 1/A12.01 | [DERIVED]
B2 #A-S-B2-03 - Break Room 118 east wall (MW08) / Work Room 119 west wall (grid 7) | A-S-B2-03 | 11.407 | 11.633 | 2 | 6" | 16 | 265.38 | Break Room 118 east wall (MW08) / Work Room 119 west wall (grid 7) | 1/A12.01 | [DERIVED]
TYPE F
F #A-N-F-01 - Diagonal wall 24 HR Vestibule 101 (ATM lobby) / ATM Room 102, with walk-up ATM | A-N-F-01 | 17.762 | 15.375 | 2 | 3-5/8" | 16 | 325.38 | Diagonal wall 24 HR Vestibule 101 (ATM lobby) / ATM Room 102, with walk-up ATM | 12/A12.01 | [DERIVED]
TYPE A1
A1 #A-N-A1-01 - North wall of Calling Cubes 122 (Waiting 104 / Calling Cubes 122) | A-N-A1-01 | 17.021 | 15.375 | 1.41 | 3-5/8" | 16 | 243.02 | North wall of Calling Cubes 122 (Waiting 104 / Calling Cubes 122) | 3/A12.01 | [CONFIRMED]
A1 #A-N-A1-02 - East side of MW01 millwork niche (niche / Calling Cubes 122) | A-N-A1-02 | 3.533 | 15.375 | 2 | 3-5/8" | 16 | 74.2 | East side of MW01 millwork niche (niche / Calling Cubes 122) | 3/A12.01 | [DERIVED]
A1 #A-N-A1-03 - South side of MW01 millwork niche (niche / Calling Cubes 122) | A-N-A1-03 | 2.021 | 15.375 | 2 | 3-5/8" | 16 | 42.44 | South side of MW01 millwork niche (niche / Calling Cubes 122) | 3/A12.01 | [DERIVED]
A1 #A-S-A1-01 - Corridor 111 north wall with door 111 (between restroom B2 corner and calling cubes A5) | A-S-A1-01 | 5.587 | 15.375 | 2 | 3-5/8" | 16 | 47.22 | Corridor 111 north wall with door 111 (between restroom B2 corner and calling cubes A5) | 3/A12.01 | [DERIVED]
A1 #A-S-A1-03 - Calling Cubes 122 south wall / Break Room 118 north (MW21) | A-S-A1-03 | 15.232 | 12.967 | 2 | 3-5/8" | 16 | 274.18 | Calling Cubes 122 south wall / Break Room 118 north (MW21) | 3/A12.01 | [DERIVED]
A1 #A-S-A1-04 - Break Room 118 east end of MW21 / customer queue, below Calling Cubes east A5 | A-S-A1-04 | 2.14 | 11.821 | 2 | 3-5/8" | 16 | 39.59 | Break Room 118 east end of MW21 / customer queue, below Calling Cubes east A5 | 3/A12.01 | [DERIVED]
A1 #A-S-A1-05 - Break Room 118 north wall at customer queue, door 118A | A-S-A1-05 | 5.094 | 12.923 | 2 | 3-5/8" | 16 | 40.91 | Break Room 118 north wall at customer queue, door 118A | 3/A12.01 | [DERIVED]
A1 #A-S-A1-06 - Work Room 119 north wall / Cash Window 116, door 119 | A-S-A1-06 | 11.667 | 12.771 | 2 | 3-5/8" | 16 | 169.17 | Work Room 119 north wall / Cash Window 116, door 119 | 3/A12.01 | [DERIVED]
A1 #A-S-A1-07 - Corridor 111 east wall: Break Room 118 / Electrical 120 / NER 121 (grid 5), door 118B | A-S-A1-07 | 20.521 | 11.821 | 2 | 3-5/8" | 16 | 361.47 | Corridor 111 east wall: Break Room 118 / Electrical 120 / NER 121 (grid 5), door 118B | 3/A12.01 | [DERIVED]
TYPE A5
A5 #A-N-A5-01 - West wall of Calling Cubes 122 (Central Zone 103 / Calling Cubes 122) | A-N-A5-01 | 14.113 | 15.375 | 2 | 6" | 16 | 244.3 | West wall of Calling Cubes 122 (Central Zone 103 / Calling Cubes 122) | 3/A12.01 | [DERIVED]
A5 #A-N-A5-02+A-N-A5-02b - East wall of Calling Cubes 122 (Calling Cubes 122 / Central Zone 103) | A-N-A5-02+A-N-A5-02b | 19.406 | 13.71 | 2 | 6" | 16 | 379.92 | East wall of Calling Cubes 122 (Calling Cubes 122 / Central Zone 103) | 3/A12.01 | [DERIVED]
A5 #A-S-A5-01a+A-S-A5-01b - Calling Cubes 122 west wall, north piece (grid B deck break, split of A-S-A5-01b) + Calling Cubes 122 west wall at Corridor 111, door 122 | A-S-A5-01a+A-S-A5-01b | 5.28 | 12.543 | 2 | 6" | 16 | 48.38 | Calling Cubes 122 west wall, north piece (grid B deck break, split of A-S-A5-01b) + Calling Cubes 122 west wall at Corridor 111, door 122 | 3/A12.01 | [DERIVED]
A5 #A-S-A5-02 - Break Room 118 east wall / Cash Window 116, door 116 (grid 7) | A-S-A5-02 | 6.947 | 11.776 | 2 | 6" | 16 | 81.85 | Break Room 118 east wall / Cash Window 116, door 116 (grid 7) | 3/A12.01 | [DERIVED]
TYPE C1
C1 #A-N-C1-05 - Furring box at 85 in. display monitor, north face of Calling Cubes north wall (Waiting 104), keynote 7 | A-N-C1-05 | 11.333 | 15.375 | 1.12 | 3-5/8" | 16 | 194.76 | Furring box at 85 in. display monitor, north face of Calling Cubes north wall (Waiting 104), keynote 7 | 6/A12.01 | [CONFIRMED]
C1 #A-N-C1-01 - Storefront pier at NW corner of Vestibule 100 (grid 2 / G), interior part | A-N-C1-01 | 3.267 | 15.375 | 1 | 3-5/8" | 16 | 50.23 | Storefront pier at NW corner of Vestibule 100 (grid 2 / G), interior part | 1/A09.25 | [DERIVED]
C1 #A-N-C1-02 - Storefront pier at NE corner of Vestibule 100 (grid 4 / G), interior part | A-N-C1-02 | 3.82 | 15.375 | 1 | 3-5/8" | 16 | 58.73 | Storefront pier at NE corner of Vestibule 100 (grid 4 / G), interior part | 1/A09.25 | [DERIVED]
C1 #A-N-C1-03 - Coiling grille 103 north jamb box at grid 4 (Vestibule 100 / 24 HR Vestibule 101 / Central Zone 103) | A-N-C1-03 | 4 | 14.383 | 1 | 3-5/8" | 16 | 57.52 | Coiling grille 103 north jamb box at grid 4 (Vestibule 100 / 24 HR Vestibule 101 / Central Zone 103) | 3/A08.21 | [DERIVED]
C1 #A-N-C1-04 - Coiling grille 103 south jamb box at grid 4 / E (24 HR Vestibule 101 / Central Zone 103) | A-N-C1-04 | 2.893 | 14.383 | 1 | 3-5/8" | 16 | 41.61 | Coiling grille 103 south jamb box at grid 4 / E (24 HR Vestibule 101 / Central Zone 103) | 3/A08.21 | [DERIVED]
C1 #A-S-C1-01 - Restroom plumbing chase between Women's 114 and Men's 113 - WOMEN'S RESTROOM 114 face | A-S-C1-01 | 10.027 | 12.922 | 1 | 3-5/8" | 16 | 129.57 | Restroom plumbing chase between Women's 114 and Men's 113 - WOMEN'S RESTROOM 114 face | 6/A12.01 | [DERIVED]
C1 #A-S-C1-02 - Restroom plumbing chase between Women's 114 and Men's 113 - MEN'S RESTROOM 113 face | A-S-C1-02 | 10.027 | 12.893 | 1 | 3-5/8" | 16 | 129.27 | Restroom plumbing chase between Women's 114 and Men's 113 - MEN'S RESTROOM 113 face | 6/A12.01 | [DERIVED]
C1 #A-S-C1-03+A-S-C1-03r - FUTURE FCAM furring on Break Room side of teller pod A1K + FUTURE FCAM furring east return (R75.7, from the outside face) | A-S-C1-03+A-S-C1-03r | 3.56 | 12.922 | 1 | 3-5/8" | 16 | 46 | FUTURE FCAM furring on Break Room side of teller pod A1K + FUTURE FCAM furring east return (R75.7, from the outside face) | 6/A12.01 | [DERIVED]
TYPE BULKHEAD-G
BULKHEAD-G #A-N-OB-01a+A-N-OB-01b+A-N-OB-01c+A-N-OB-01d - Office bulkhead over Allsteel DFC-1A office front at Office 105 (east front; collinear bulkheads of one front = one wall, R74.4 / PT4) + Office bulkhead over Allsteel DFC-1A office front at Office 106 (east front; collinear bulkheads of one front = one wall, R74.4 / PT4) + Office bulkhead over Allsteel DFC-1A office front at Office 107 (east front; collinear bulkheads of one front = one wall, R74.4 / PT4) + Office bulkhead over Allsteel DFC-1A office front at Office 108 (east front; collinear bulkheads of one front = one wall, R74.4 / PT4) | A-N-OB-01a+A-N-OB-01b+A-N-OB-01c+A-N-OB-01d | 30 | 5.773 | 5 | 1-5/8" | 16 | 769 | Office bulkhead over Allsteel DFC-1A office front at Office 105 (east front; collinear bulkheads of one front = one wall, R74.4 / PT4) + Office bulkhead over Allsteel DFC-1A office front at Office 106 (east front; collinear bulkheads of one front = one wall, R74.4 / PT4) + Office bulkhead over Allsteel DFC-1A office front at Office 107 (east front; collinear bulkheads of one front = one wall, R74.4 / PT4) + Office bulkhead over Allsteel DFC-1A office front at Office 108 (east front; collinear bulkheads of one front = one wall, R74.4 / PT4) | 9/A12.01 | [CONFIRMED]
BULKHEAD-G #A-N-OB-02a+A-N-OB-02b - Office bulkhead over Allsteel DFC-1A office front at Office 109 (west front; collinear bulkheads of one front = one wall, R74.4 / PT4) + Office bulkhead over Allsteel DFC-1A office front at Office 110 (west front; collinear bulkheads of one front = one wall, R74.4 / PT4) | A-N-OB-02a+A-N-OB-02b | 15 | 6.844 | 5 | 1-5/8" | 16 | 448.74 | Office bulkhead over Allsteel DFC-1A office front at Office 109 (west front; collinear bulkheads of one front = one wall, R74.4 / PT4) + Office bulkhead over Allsteel DFC-1A office front at Office 110 (west front; collinear bulkheads of one front = one wall, R74.4 / PT4) | 9/A12.01 | [CONFIRMED]
TYPE B
B #A-S-B-01 - Men's Restroom 113 south wall / Janitor 112 + Storage 117 north, door 112 | A-S-B-01 | 11.719 | 12.452 | 2 | 3-5/8" | 16 | 245.18 | Men's Restroom 113 south wall / Janitor 112 + Storage 117 north, door 112 | 1/A12.01 | [DERIVED]
B #A-S-B-02 - Janitor 112 / Storage 117 partition | A-S-B-02 | 3.5 | 12.743 | 2 | 3-5/8" | 16 | 89.2 | Janitor 112 / Storage 117 partition | 1/A12.01 | [DERIVED]
B #A-S-B-03 - Wellness 115 north wall / Janitor 112 + Storage 117 south | A-S-B-03 | 11.719 | 12.149 | 2 | 3-5/8" | 16 | 284.74 | Wellness 115 north wall / Janitor 112 + Storage 117 south | 1/A12.01 | [DERIVED]
B #A-S-B-04 - Electrical 120 north wall / Break Room 118 (FEC-2 side) | A-S-B-04 | 9.99 | 12.827 | 2 | 3-5/8" | 16 | 256.28 | Electrical 120 north wall / Break Room 118 (FEC-2 side) | 1/A12.01 | [DERIVED]
B #A-S-B-05 - Electrical 120 / NER 121 east wall at Break Room 118, doors 120 and 121 | A-S-B-05 | 13.74 | 12.823 | 2 | 3-5/8" | 16 | 259.04 | Electrical 120 / NER 121 east wall at Break Room 118, doors 120 and 121 | 1/A12.01 | [DERIVED]
B #A-S-B-06 - Electrical 120 / NER 121 partition | A-S-B-06 | 9.583 | 12.699 | 2 | 3-5/8" | 16 | 243.38 | Electrical 120 / NER 121 partition | 1/A12.01 | [DERIVED]
TYPE EXT-PARAPET
EXT-PARAPET #A-PAR-01 - Tower (vestibule) north parapet, grids 2 to 4 | A-PAR-01 | 16.342 | 4.292 | 0 | 6" | 16 | 0 | Tower (vestibule) north parapet, grids 2 to 4 | 4/A09.26 | [DERIVED]
EXT-PARAPET #A-PAR-02 - Tower east return of parapet 2 at grid 4, stepping down to parapet 1 | A-PAR-02 | 3.923 | 4.292 | 0 | 6" | 16 | 0 | Tower east return of parapet 2 at grid 4, stepping down to parapet 1 | 4/A09.26 | [DERIVED]
EXT-PARAPET #A-PAR-03 - North parapet on grid F, grid 4 to grid 8 | A-PAR-03 | 39.856 | 2.042 | 0 | 6" | 16 | 0 | North parapet on grid F, grid 4 to grid 8 | 4/A09.26 | [DERIVED]
EXT-PARAPET #A-PAR-04+A-PAR-05 - East parapet on grid 8, F to B (main roof) + East parapet on grid 8, B to A (low roof, deck break at B) | A-PAR-04+A-PAR-05 | 75.938 | 2.901 | 0 | 6" | 16 | 0 | East parapet on grid 8, F to B (main roof) + East parapet on grid 8, B to A (low roof, deck break at B) | 4/A09.26 | [DERIVED]
EXT-PARAPET #A-PAR-06 - South parapet on grid A, grid 3 to grid 8 | A-PAR-06 | 52.333 | 4.885 | 0 | 6" | 16 | 0 | South parapet on grid A, grid 3 to grid 8 | 4/A09.26 | [DERIVED]
EXT-PARAPET #A-PAR-07 - Jog on grid D between grids 2 and 3 (south-facing, under the drive-up canopy) | A-PAR-07 | 3.865 | 4.292 | 0 | 6" | 16 | 0 | Jog on grid D between grids 2 and 3 (south-facing, under the drive-up canopy) | 4/A09.26 | [DERIVED]
EXT-PARAPET #A-PAR-08 - West parapet (tower) on grid 2, tower north to D | A-PAR-08 | 29 | 4.292 | 0 | 6" | 16 | 0 | West parapet (tower) on grid 2, tower north to D | 4/A09.26 | [DERIVED]
EXT-PARAPET #A-PAR-09+A-PAR-10 - West parapet on grid 3, D to B (main roof) + West parapet on grid 3, B to A (low roof, deck break at B) | A-PAR-09+A-PAR-10 | 47.927 | 3.403 | 0 | 6" | 16 | 0 | West parapet on grid 3, D to B (main roof) + West parapet on grid 3, B to A (low roof, deck break at B) | 4/A09.26 | [DERIVED]
| TOTAL - PARTITIONS | 1131.84 |  |  |  |  | 15785.77
TYPE OTHER FRAMING (NOT A PARTITION)
pier_part #A-EXT-PIER-G2 - Vestibule entrance pier at grid G / grid 2 (NW building corner, west of door 100) | A-EXT-PIER-G2 | 3.375 | 10.931 | 0 | 6" | 12 | 0 | Vestibule entrance pier at grid G / grid 2 (NW building corner, west of door 100) | 1/A09.25 | [DERIVED]
pier_part #A-EXT-PIER-G4 - Vestibule entrance pier at grid G / grid 4 (east of door 100, NE corner of the vestibule) | A-EXT-PIER-G4 | 2.896 | 10.931 | 0 | 6" | 12 | 0 | Vestibule entrance pier at grid G / grid 4 (east of door 100, NE corner of the vestibule) | 2/A09.25 | [DERIVED]
roof_step #A-RS-01 - Roof step at grid B, grids 3 to 8 - upper exterior row (above low roof deck, faces low roof) | A-RS-01 | 51.833 | 3.114 | 0 | 3-5/8" | 16 | 0 | Roof step at grid B, grids 3 to 8 - upper exterior row (above low roof deck, faces low roof) | 4/A02.02 | [DERIVED]
roof_step #A-RS-02 - Roof step at grid B, grids 3 to 8 - lower row below low roof deck (ceiling space south of grid B) | A-RS-02 | 51.833 | 1.131 | 1 | 3-5/8" | 16 | 58.6 | Roof step at grid B, grids 3 to 8 - lower row below low roof deck (ceiling space south of grid B) | 4/A02.02 | [DERIVED]
roof_step #A-RS-03 - Roof step at grid B, grids 3 to 8 - row on high side (ceiling space north of grid B), up to upper deck | A-RS-03 | 51.833 | 3.46 | 2 | 3-5/8" | 16 | 246.3 | Roof step at grid B, grids 3 to 8 - row on high side (ceiling space north of grid B), up to upper deck | 4/A02.02 | [DERIVED]
fascia_box #A-FAS-N - North canopy fascia (G side), full length | A-FAS-N | 77.572 | 1.865 | 0 | 3-5/8" | 16 | 0 | North canopy fascia (G side), full length | 3/A09.26 | [DERIVED]
fascia_box #A-FAS-W - Drive-up canopy west fascia (west of grid 1) | A-FAS-W | 55.933 | 1.865 | 0 | 3-5/8" | 16 | 0 | Drive-up canopy west fascia (west of grid 1) | 16/A09.27 | [DERIVED]
fascia_box #A-FAS-W2 - Drive-up canopy south fascia (B + 7 1/2"), to grid 3 wall | A-FAS-W2 | 21.2 | 1.865 | 0 | 3-5/8" | 16 | 0 | Drive-up canopy south fascia (B + 7 1/2"), to grid 3 wall | 16/A09.27 | [DERIVED]
fascia_box #A-FAS-E - East canopy fascia (3'-8" E of grid 8) | A-FAS-E | 51.994 | 1.865 | 0 | 3-5/8" | 16 | 0 | East canopy fascia (3'-8" E of grid 8) | 7/A09.26 | [DERIVED]
fascia_box #A-FAS-E2 - East canopy south end return to grid 8 wall | A-FAS-E2 | 2.694 | 1.865 | 0 | 3-5/8" | 16 | 0 | East canopy south end return to grid 8 wall | 7/A09.26 | [DERIVED]
fascia_box #A-FAS-S - South canopy (over door 123) fascia, 3'-0" S of A | A-FAS-S | 22.417 | 1.865 | 0 | 3-5/8" | 16 | 0 | South canopy (over door 123) fascia, 3'-0" S of A | 7/A09.26 | [DERIVED]
fascia_box #A-FAS-S2 - South canopy west return | A-FAS-S2 | 2.7 | 1.865 | 0 | 3-5/8" | 16 | 0 | South canopy west return | 7/A09.26 | [DERIVED]
fascia_box #A-FAS-S3 - South canopy east return | A-FAS-S3 | 2.7 | 1.865 | 0 | 3-5/8" | 16 | 0 | South canopy east return | 7/A09.26 | [DERIVED]
soffit_side #A-SS-116W-N - CSR soffit west drop line, north of grid B | A-SS-116W-N | 6.583 | 7.375 | 1 | 3-5/8" | 16 | 9.87 | CSR soffit west drop line, north of grid B | 10/A09.33 | [DERIVED]
soffit_side #A-SS-116W-S - CSR soffit west drop line, south of grid B | A-SS-116W-S | 5.438 | 5.052 | 1 | 3-5/8" | 16 | 8.16 | CSR soffit west drop line, south of grid B | 10/A09.33 | [DERIVED]
soffit_side #A-SS-116E-N - CSR soffit east drop line, north of grid B | A-SS-116E-N | 6.583 | 7.375 | 1 | 3-5/8" | 16 | 9.87 | CSR soffit east drop line, north of grid B | 10/A09.33 | [DERIVED]
soffit_side #A-SS-116E-S - CSR soffit east drop line, south of grid B | A-SS-116E-S | 5.438 | 5.052 | 1 | 3-5/8" | 16 | 8.16 | CSR soffit east drop line, south of grid B | 10/A09.33 | [DERIVED]
ceiling_transition #A-CT-104 - Waiting 104 GB island edges against Central Zone ACT-4 11'-6" (N, W, E) | A-CT-104 | 77.028 | 4.375 | 1 | 3-5/8" | 16 | 77.03 | Waiting 104 GB island edges against Central Zone ACT-4 11'-6" (N, W, E) | 8/A09.33 | [DERIVED]
vestibule_head #A-VH-S - Vestibule 100 / 24 HR Vestibule 101 all-glass line (door 101 pair), grids 2-4, from the grid 2 exterior wall to the 1'-0" post (C1) at grid 4 | A-VH-S | 15.646 | 4.812 | 0 | 3-5/8" | 16 | 0 | Vestibule 100 / 24 HR Vestibule 101 all-glass line (door 101 pair), grids 2-4, from the grid 2 exterior wall to the 1'-0" post (C1) at grid 4 | 5/A12.10 | [DERIVED]
vestibule_head #A-VH-E - Vestibule 100 / Central Zone 103 all-glass line on grid 4 (door 100A + sidelite), from pier C1 at G/4 to the 1'-0" post (C1) | A-VH-E | 6.417 | 3.821 | 1 | 3-5/8" | 16 | 12.83 | Vestibule 100 / Central Zone 103 all-glass line on grid 4 (door 100A + sidelite), from pier C1 at G/4 to the 1'-0" post (C1) | 6/A12.10 | [DERIVED]
grille_head #A-GH-01 - Coiling grille 103 head, grid 4 between E and F (24 HR Vestibule 101 west / Central Zone 103 east), between C1 jamb boxes | A-GH-01 | 13.333 | 2 | 3 | 2-1/2" | 16 | 37.21 | Coiling grille 103 head, grid 4 between E and F (24 HR Vestibule 101 west / Central Zone 103 east), between C1 jamb boxes | 4/A08.21 | [CONFIRMED]
storefront_cripples #A-SC-F24 - Above entry storefront SF-F-2/4 (door 100 pair), Vestibule 100 north facade, between piers G/2 and G/4 | A-SC-F24 | 12.562 | 1.556 | 1 | 6" | 16 | 86.37 | Above entry storefront SF-F-2/4 (door 100 pair), Vestibule 100 north facade, between piers G/2 and G/4 | A/A09.21 | [CONFIRMED]
storefront_cripples #A-SC-F48 - Above storefront SF-F-4/8, north facade grid F (Central Zone 103 / Waiting 104), from pier G/4 to the Office 105 corner | A-SC-F48 | 26.25 | 1.546 | 1 | 6" | 16 | 180.47 | Above storefront SF-F-4/8, north facade grid F (Central Zone 103 / Waiting 104), from pier G/4 to the Office 105 corner | 2/A09.26 | [CONFIRMED]
storefront_cripples #A-SC-2FE4 - Above storefront SF-2-F/E.4, Vestibule 100 west facade grid 2, from pier G/2 to the start of A-EXT-W-2 | A-SC-2FE4 | 6.5 | 1.067 | 1 | 6" | 16 | 44.69 | Above storefront SF-2-F/E.4, Vestibule 100 west facade grid 2, from pier G/2 to the start of A-EXT-W-2 | J/A09.23 | [CONFIRMED]
alcove #A-S-A1-02+A-S-A1-02t+A-S-A1-02b - Drinking-fountain alcove off Corridor 111 between restrooms - west wall (niche of B2 line, R74.3) + Drinking-fountain alcove top return (Women's 114 side) (niche of B2 line, R74.3) + Drinking-fountain alcove bottom return (Men's 113 side) (niche of B2 line, R74.3) | A-S-A1-02+A-S-A1-02t+A-S-A1-02b | 7.487 | 12.195 | 1.86 | 3-5/8" | 16 | 125.04 | Drinking-fountain alcove off Corridor 111 between restrooms - west wall (niche of B2 line, R74.3) + Drinking-fountain alcove top return (Women's 114 side) (niche of B2 line, R74.3) + Drinking-fountain alcove bottom return (Men's 113 side) (niche of B2 line, R74.3) | 3/A12.01 | [DERIVED]

## Material Summary
MATERIAL SUMMARY - NET / WASTE / PURCHASE
Waste lives HERE, in its own column, applied ONCE: Pieces = ROUNDUP(Net x (1 + waste) / stock). Every stock length, coverage and yield is an Inputs cell.
Material | Unit | Net | Waste % | Waste | Purchase | Selling unit | Pieces to buy | Where it comes from | Yield check (live formula)
6" metal stud (LF of material) | LF | 4363.89 | 0.15 | 654.5835 | 5018.4735 | stick 20 ft | 251 | familias_out.json '6" stud (all gauges)'
3-5/8" metal stud (LF of material) | LF | 6625.02 | 0.15 | 993.753 | 7618.773 | stick 20 ft | 381 | familias_out.json '3-5/8" stud (all gauges)'
1-5/8" metal stud (LF of material) | LF | 3785.8 | 0.15 | 567.87 | 4353.67 | stick 20 ft | 218 | familias_out.json '1-5/8" stud'
6" parapet infill stud (LF of material) | LF | 1001.47 | 0.15 | 150.2205 | 1151.6905 | stick 20 ft | 58 | familias_out.json '6" parapet stud'
Track, ceilings / soffits / canopy | LF | 1231.38 | 0.15 | 184.707 | 1416.087 | run 10 ft | 142 | familias_out.json 'ceiling / soffit track'
Bracing 1-1/2" C.R. channel | LF | 2332.26 | 0.15 | 349.839 | 2682.099 | C.R. channel 16 ft | 168 | familias_out.json 'bracing C.R. channel'
Purlin, top track to deck | LF | 260.44 | 0.15 | 39.066 | 299.506 | run 10 ft | 30 | familias_out.json 'purlin (track to deck)'
Header / metal stud box beam | LF | 796.59 | 0.15 | 119.4885 | 916.0785 | stick 20 ft | 46 | familias_out.json 'header / box beam'
Sill track | LF | 119.09 | 0.15 | 17.8635 | 136.9535 | run 10 ft | 14 | familias_out.json 'sill track'
Furring channel (ceilings) | LF | 786.08 | 0.15 | 117.912 | 903.992 | hat channel 12 ft | 76 | familias_out.json 'furring channel'
Carrying channel (ceilings) | LF | 315.94 | 0.15 | 47.391 | 363.331 | C.R. channel 16 ft | 23 | familias_out.json 'carrying channel'
Hanger wire | LF | 533.63 | 0.15 | 80.0445 | 613.6745 | continuous coil (LF) | 614 | familias_out.json 'hanger wire'
5/8" gypsum board, regular | SF | 17406.06 | 0.06 | 1044.3636 | 18450.4236 | 4x12 sheet | 385 | familias_out.json '5/8" gyp board regular (walls + ceilings)'
5/8" gypsum board, MOISTURE RESISTANT | SF | 258.84 | 0.06 | 15.5304 | 274.3704 | 4x12 sheet | 6 | familias_out.json '5/8" gyp MOISTURE RESISTANT'
Ballistic panel UL752 | SF | 85.74 | 0.06 | 5.1444 | 90.8844 | 4x8 sheet | 3 | familias_out.json 'ballistic panel'
3/8" gypsum board | SF | 65.88 | 0.06 | 3.9528 | 69.8328 | 4x8 sheet | 3 | familias_out.json '3/8" gyp board'
5/8" glass mat sheathing (exterior face of the stud) | SF | 358.87 | 0.06 | 21.5322 | 380.4022 | 4x8 sheet | 12 | familias_out.json '5/8" glass mat sheathing'
5/8" EXTERIOR gypsum sheathing | SF | 948.41 | 0.06 | 56.9046 | 1005.3146 | 4x8 sheet | 32 | familias_out.json '5/8" EXTERIOR gyp sheathing'
Blocking FRT / 2X FRT wood | LF | 857.71 | 0.06 | 51.4626 | 909.1726 | piece 16 ft | 57 | familias_out.json 'FRT blocking'
METAL trim - corner bead, casing bead, shadow molding, gypsum edge trim | LF | 1030.72 | 0.15 | 154.608 | 1185.328 | trim stick 10 ft | 119 | familias_out.json 'metal trim (corner bead, casing, shadow molding)'
Cement board (substrate under the FRP cove base band) | SF | 33.38 | 0.06 | 2.0028 | 35.3828 | 3x5 sheet | 3 | familias_out.json 'cement board'
FRP panels | SF | 349.75 | 0.06 | 20.985 | 370.735 | 4x8 sheet | 12 | familias_out.json 'FRP'
Framed openings - MEP, light slots and diffusers | LF | 241.38 | 0.15 | 36.207 | 277.587 | stick 20 ft | 14 | framed_openings_out.json 'framed openings MEP'
Bottom track 6" | LF | 476.62 | 0.15 | 71.493 | 548.113 | run 10 ft | 55 | familias_out.json track_by_element 'bottom track (all)' (R73.3)
Bottom track - other framing (not a partition type, see source) | LF | 64.92 | 0.15 | 9.738 | 74.658 | run 10 ft | 8 | familias_out.json track_by_element 'bottom track (all)' (R73.3)
Bottom track 3-5/8" | LF | 248.52 | 0.15 | 37.278 | 285.798 | run 10 ft | 29 | familias_out.json track_by_element 'bottom track (all)' (R73.3)
Bottom track 1-5/8" | LF | 290.1 | 0.15 | 43.515 | 333.615 | run 10 ft | 34 | familias_out.json track_by_element 'bottom track (all)' (R73.3)
Parapet bottom track | LF | 269.18 | 0.15 | 40.377 | 309.557 | run 10 ft | 31 | familias_out.json track_by_element 'bottom track (all)' (R73.3)
Bottom track - roof step and heads (vestibule / bulkhead) | LF | 177.56 | 0.15 | 26.634 | 204.194 | run 10 ft | 21 | familias_out.json track_by_element 'bottom track (all)' (R73.3)
Top / deflection track 6" | LF | 476.62 | 0.15 | 71.493 | 548.113 | run 10 ft | 55 | familias_out.json track_by_element 'top / deflection track (all)' (R73.3)
Top / deflection track - other framing (not a partition type, see source) | LF | 64.92 | 0.15 | 9.738 | 74.658 | run 10 ft | 8 | familias_out.json track_by_element 'top / deflection track (all)' (R73.3)
Top / deflection track 3-5/8" | LF | 248.52 | 0.15 | 37.278 | 285.798 | run 10 ft | 29 | familias_out.json track_by_element 'top / deflection track (all)' (R73.3)
Top / deflection track 1-5/8" | LF | 290.1 | 0.15 | 43.515 | 333.615 | run 10 ft | 34 | familias_out.json track_by_element 'top / deflection track (all)' (R73.3)
Parapet top track | LF | 269.18 | 0.15 | 40.377 | 309.557 | run 10 ft | 31 | familias_out.json track_by_element 'top / deflection track (all)' (R73.3)
Top track - roof step and heads (vestibule / bulkhead) | LF | 177.56 | 0.15 | 26.634 | 204.194 | run 10 ft | 21 | familias_out.json track_by_element 'top / deflection track (all)' (R73.3)
3-5/8" stud, framed soffit 9/A12.08 (LF) | LF | 37.58 | 0.15 | 5.637 | 43.217 | stick 20 ft | 3 | familias_out.json stud_by_element '3-5/8" stud (all gauges)' (v76)
5/8" FRT plywood sheathing (canopy and soffits) | SF | 1941.04 | 0.06 | 116.4624 | 2057.5024 | 4x12 ft sheet (Inputs) | 43 | familias_out.json FRT plywood by material; canon rows
Exterior sheathing 5/8" FRT plywood bonded to 2-1/2" polyiso | SF | 3909.2 | 0.06 | 234.552 | 4143.752 | 4x12 ft sheet (Inputs) | 87 | familias_out.json FRT plywood by material; canon rows
FRT plywood substrate (3/4 in.) | SF | 665.23 | 0.06 | 39.9138 | 705.1438 | 4x12 ft sheet (Inputs) | 15 | familias_out.json FRT plywood by material; canon rows
5/8" FRT plywood at canopy column wraps | SF | 238.01 | 0.06 | 14.2806 | 252.2906 | 4x12 ft sheet (Inputs) | 6 | familias_out.json FRT plywood by material; canon rows
FRT plywood substrate (5/8 in.) | SF | 7.25 | 0.06 | 0.435 | 7.685 | 4x12 ft sheet (Inputs) | 1 | familias_out.json FRT plywood by material; canon rows
Sealant at base of gypsum (exterior, not acoustical) | LF | 216.74 | 0.06 | 13.0044 | 229.7444 | tube (25 LF per tube) | 10 | familias_out.json sealant_exterior_lf 'base of gypsum (exterior)'
Hanger wire 12 ga - hanger count (one per hanger, height per room) | PCS | 113 | 0 | 0 | 113 |  | 113 | familias_out.json hanger_pcs.total_pcs; wire bought on the LF row
Additional head track at openings over 4'-0" wide | LF | 56 | 0.15 | 8.4 | 64.4 | run 10 ft | 7 | accesorios.py [CRITERION]: HEAD TRACK @ NON LOAD BRG: ADD FULL LENGTH ADDL HEAD TRACK @ OPNG > 4'-0"; Estimator user decision #1: R.O. + 1'-4" (8" bearing each side)
Stud reinforcement at MEP penetrations | PCS | 24 | 0 | 0 | 24 | each | 24 | accesorios.py [CRITERION]: 6/S5.20 TYPICAL PENETRATION THRU STUDS (S5.20 p69); M01.01 (p76) duct crossing found by mep.cruces (offset dx -571.92, dy 21.84) on the A02.01 band; size read on M01.01: lines 1530.36/1542.36 = 12 pt = 8 in.; label 8"x8" (EF-2); 6/S5.20 TYP
Extra framing - ATM recess (only what a detail prints at the recess; the wall stays in its type) | LF | 28.25 | 0.15 | 4.2375 | 32.4875 | stick 20 ft | 2 | accesorios.py [DERIVED]: 6/A08.11; A02.01, J/A09.23; 6/A08.11: "2 1/2" METAL STUD SISTERED TO 6" METAL STUD W/ MINERAL WOOL INSULATION"; 6/A08.11: "FIBER CEMENT PANEL ON FURRING ON 5/8" FRT PLYWOOD"; 4/A08.11; A02.01; 12/A12.01
2-1/2" CFMF @ 16" O.C. at coiling grille head (4/A08.21) | LF | 10.43 | 0.15 | 1.5645 | 11.9945 | stick 20 ft | 1 | accesorios.py [DERIVED]: 4/A08.21
Gypsum board jamb return at openings | SF | 67.16 | 0.06 | 4.0296 | 71.1896 | 4x12 ft sheet (Inputs) | 2 | accesorios.py [CRITERION]: Estimator criterion (return width = 6" stud depth, not dimensioned; RFI with delta at 0.20 ft)
PVC trim - edge trim molding and inside corner molding at the FRP | LF | 219.5 | 0.06 | 13.17 | 232.67 | trim stick 10 ft | 24 | accesorios.py [DERIVED]: A08.01 elevations '5'-0" TO TOP OF FRP' (dimension from top of the 6" CT-12C base; FRP WC-3 panel height 5'-0", top at 5'-6" AFF); A08.01 enlarged plan 1/A08.01 (vector polygon of the room, 6 vertices: 5 inside + 1 outside); A05.01 key note
Power-driven fasteners and duct sleeves | PCS | 291 | 0 | 0 | 291 | each | 291 | accesorios.py [DERIVED]: Parapet infill: PAFs SPACED AT 12" O.C. MAX to the steel beam; M01.01 (p76) duct crossing found by mep.cruces (offset dx -571.92, dy 21.84) on the A02.01 band; size read on M01.01: lines 1013.88/1025.88 = 12 pt = 8 in.; label 8"o; M01.01 (p
Access panel | PCS | 1 | 0 | 0 | 1 | each | 1 | accesorios.py [CONFIRMED]: A04.01 key note 4 (one circle, p29)
Drywall screws 1-1/4" bugle head | PCS | 21276.94 | 0 | 0 | 21276.94 | each | 21277 | accesorios.py [DERIVED]: Inputs!B20 (Drywall screws per SF of board = 1.2) x 17730.8 SF of board | 21276.96
Framing screws, pan head self-drilling | PCS | 7692 | 0 | 0 | 7692 | each | 7692 | accesorios.py [DERIVED]: Inputs!B21 (Framing screws per stud piece = 4) x 1923 stud pieces | 7692
Power-driven fasteners, slab pins for the bottom track | PCS | 534.52 | 0 | 0 | 534.52 | each | 535 | accesorios.py [DERIVED]: 534.52 LF of interior bottom track on slab / Inputs!B22 (Power-driven pin spacing (ft) = 1) | 534.52
Expansion anchors Hilti 1/4" Kwik Bolt II, exterior bottom track @ 8" O.C. | PCS | 586 | 0 | 0 | 586 | each | 586 | accesorios.py [DERIVED]: 390.67 LF of exterior bottom track on slab / Inputs!B25 (Expansion anchor spacing (ft) = 0.6667) | 585.9757
Joint compound, all purpose | LB | 1276.62 | 0 | 0 | 1276.62 | lb | 1277 | accesorios.py [DERIVED]: Inputs!B23 (Joint compound (lb per SF) = 0.072) x 17730.8 SF of board | 1276.6176
Joint tape, paper | LF | 6560.39 | 0 | 0 | 6560.39 | LF | 6561 | accesorios.py [DERIVED]: Inputs!B24 (Joint tape (LF per SF) = 0.37) x 17730.8 SF of board | 6560.396
Level 5 finish | SF | 859.26 | 0.06 | 51.5556 | 910.8156 | SF | 911 | accesorios.py [CRITERION]: A00.40 WC-18 'WALL SURFACE TO BE LEVEL 5'; A05.01 WC-18 tag at [1729, 363] (A05.01 pt); A00.40 WC-18 'WALL SURFACE TO BE LEVEL 5'; A05.01 WC-18 tag at [1729, 560] (A05.01 pt); A00.40 WC-18 'WALL SURFACE TO BE LEVEL 5'; A05.01 WC-18 tag at [
Deflection clips at non-load-bearing walls to structure | PCS | 0 | 0 | 0 | 0 | each | 0 | accesorios.py [CRITERION]: S1.11 LIGHT GAUGE STEEL FRAMING note 2 'PROVIDE MANUFACTURER'S STANDARD VERTICAL DEFLECTION CLIPS AT NON-LOAD-BEARING WALLS, CAPABLE OF ISOLATING THE WALL FRAMING FROM A MAX. 1 INCH VERTICAL UPWARD OR DOWNWARD MOVEMENT OF THE PRIMARY STRUCT

## Pending Items
RFI | Question / condition | Delta of each alternative
RFI-ACC-additional-head-track | additional head track: openings with their own box (openings_extra) > 4'-0": do they also take the additional head track of HEAD TRACK @ NON LOAD BRG: ADD FULL LENGTH ADDL HEAD TRACK @ OPNG > 4'-0"? | 100.54 lf
RFI-ACC-stud-reinforcement-mep | stud reinforcement MEP: plates at double-row stud walls: one per cut row (R72.9) vs one per crossing | -8 pcs
RFI-ACC-stud-reinforcement-mep-2 | stud reinforcement MEP: crossings read by hand (not found by mep.cruces): confirm each one on the M / P sheets (R73.5) | 12 pcs
RFI-ACC-gypsum-board-jamb-return | gypsum board jamb return: jamb return width not dimensioned | -40.29 sf
RFI-ACC-expansion-anchors | expansion anchors: untagged parts of piers / boxes (A-EXT-PIER-G2, A-EXT-PIER-G4) without anchorage in the schedule (R72.8) | 9.41 pcs
RFI-ACC-slab-pins | slab pins: pin spacing: 12" (interior anchorage) vs 16" (fastener schedule) vs 24" (type K box) | 16in: -133.63 pcs; 24in: -267.26 pcs
RFI-ACC-deflection-clips | deflection clips: deflection clips: the general note asks for them at non-load-bearing walls and the partition details draw a slip / deflection track (R73.6) | 773 pcs
RFI-ACC-stud-reinforcement-mep-3 | stud reinforcement MEP: 4 fire dampers (Electrical 120 / NER 121) sit at the wall line and are not found by mep.cruces; listed manual | +4 pcs (14", 14", 12", 12" at 16" O.C. = 1 stud each)
RFI-ACC-stud-reinforcement-mep-4 | stud reinforcement MEP: pipes > 1 in. through stud walls read on P01.01 (registro 14 < 25 votes): 2" ST x3, 4" OD x1, 3" ST x1 | +6 pcs
RFI-ACC-stud-reinforcement-mep-5 | stud reinforcement MEP: crossing at A5 wall of Calling Cubes 122 shows two parallel branches (12" and 10") not labeled at the crossing; confirm sizes | 0 / -1 pcs if a single duct
RFI-ACC-access-panel | access panel: M01.01 general note 2 and M00.03 note 16 require access panels for equipment / dampers above ceilings; only one panel drawn (RCP key note 4). Fire dampers at Electrical 120 / NER 121 are above ACT (no panel); GB ceilings (Vestibules 100/101, Waiting 104, Cash Window 116, Restrooms 113/114) may need more | +n pcs per equipment found above GB ceilings
RFI-ACC-extra-framing-atm | extra framing ATM: 6/A08.11: count and top extent of the 2 1/2" sistered studs and orientation/spacing of the furring not dimensioned (criterion 3 lines @ 16" O.C.); furring may belong to the fiber cement cladding installer | furring -12.423 LF if by cladding installer; studs +/- 5.276 LF per line
RFI-ACC-extra-framing-atm-2 | extra framing ATM: GC-built ATM plinths ((2) layers 3/4" FRT plywood 6/A08.11; 2X4/4X4 FRT framing + FRT plywood 3/A08.11) are rough carpentry, not counted | not quantified
RFI-ACC-level-5-finish | Level 5 finish: WC-20 (A05.01 key note 9) is not in the A00.40 legend and has no tag/extent; taken as the full vestibule face of the diagonal ATM wall to the 10'-0" ceiling | -146.377 SF if WC-20 covers less
RFI-ACC-pvc-trim-at-frp | PVC trim at FRP: mop sink width taken 24 in. from model TSH-24-TF2 (not dimensioned on A05.01) | per inch of width: 2 x 1/12 x ... (small)
RFI-01 | Exterior 6" CFMF studs: S1.11 note 5 requires 600S162-54 @ 16" O.C. (12" O.C. within 6 ft of building corners) while 7/S5.20 lists 600S137-33 for exterior walls. S1.11 (heavier) carried. Confirm. | gauge only: 54 mil vs 33 mil on all 6" exterior stud LF (no LF change)
RFI-02 | Elevation titles vs north arrow: A09.01 'SOUTH ELEVATION' draws the plan north facade and A09.02 'NORTH ELEVATION' the plan south facade (S2.20 'BUILDING FOOTPRINT MIRRORED'). Facades named by the A02.01 north arrow. Confirm for all trades. | n/a: naming only, no quantity change
RFI-03 | Plan bubbles cite A9.02 / A9.21-A9.23 while the sheets are numbered A09.xx; finish schedule 'A00.31' referenced on A05.01 / A03.01 is not in the set. | n/a: document coordination
RFI-04 | Canopy beam T.O.S. on grid F 7-8 not printed on S2.20; 11'-11 3/8" (grids 8 / G) carried. C/A09.21 vector gives 11'-9". | A-EXT-N-F studs -0.198 ft each / upper row +0.198 ft each (net 0 LF)
RFI-05 | Grid 2 HSS9x5x5/8 (LLV, B.O.S. 8'-7 1/2") taken as spanning G-E; studs below it stop at 8'-7 1/2" and a 6" row (A-EXT-W-2M) runs from the HSS top 9'-4 1/2" to the W16x26 canopy beam. Confirm the HSS extent. | if the HSS spans only SF-2-F/E.4: +1.8 ft x studs of 15.54 LF (approx +25 LF 6" stud) and -13.9 LF / -31.1 LF track of A-EXT-W-2M
RFI-06 | Drive-up ATM 6/A08.11: 2 1/2" sistered studs and the furring of the fiber cement surround are printed but count / spacing / extent not dimensioned; carried 3 lines of each in the section (28.25 LF). Furring may belong to the cladding installer. | full-height sistered reading 53.67 LF (+25.42 LF); furring by cladding -12.42 LF
RFI-07 | B2K tag on A02.01 is not in the A12.01 partition schedule; carried as A5K build-up (6" 14 ga @ 24" + ballistic panel + 3/8" gyp, 4/A12.01), 7.68" measured. | n/a: type definition; ballistic panel and 3/8" board of 1.77 LF depend on it
RFI-08 | Gauge of 1-5/8" studs (G / G1 double row) and 6" interior studs (A5 / B2) not printed (7/S5.20 lists only 362S137-33 interior). Carried 20 ga. | gauge only (no LF change)
RFI-09 | Carrying channel direction, furring / carrying / hanger spacing of the suspended GWB ceilings are not printed (A04.01 legend only). Carried carrying N-S, furring 16", carrying 48", hangers 48". | carrying E-W: +7.12 LF carrying, -17.69 LF furring
RFI-10 | Vestibule box headers 'METAL STUD FRAMING & BOX HEADER AS NEEDED' (4-7/A12.10): box size not printed; depth 6 1/8" taken from the 5/A12.10 vector. | box size changes header pieces only (4 pieces x (R.O. + 1'-4") already carried)
RFI-11 | Coiling grille 103 height: A00.30 prints 13'-6 1/2" while 2/A08.21 measures a 10'-0" head (24 HR vestibule ceiling); head 10'-0" carried. | n/a: header LF unchanged (R.O. 13'-4"); grille head framing height depends on it
RFI-12 | Parapet infill 11/S5.10 @ 16" O.C. vs S1.11 note 5 @ 12" within 6 ft of building corners: 11/S5.10 carried. | approx +26 pcs / +78 LF 6" parapet stud at the corners
RFI-13 | Drive-up canopy band 15/A09.27 does not label glass mat sheathing (3/A09.26 and 7/A09.26 do); west band carried without glass mat. | +109.9 SF glass mat if required
RFI-14 | Stud blocking at the edge of gypboard (4/S5.20 'PROVIDE BLOCKING AT THE EDGE OF GYPBOARD', NTS, no location): carried on every face whose board piece is taller than a 12 ft sheet, per stud row (R78.33). | (a) exterior + double-layer walls only: see Pending Items; 10 ft sheets add approx +50 LF
RFI-15 | Storefront pier jamb strips (3/4" FRT plywood at the 4 jambs of piers G/2 and G/4, 1/A09.25, 2/A09.25): width not measured with a validated scale; not carried. | approx +24 SF 3/4" FRT plywood
RFI-16 | HM door rough openings: carried door + 2 x 2" frame face (11/A12.02); a vector reading of 11/A12.02 gives door + 2.13". Header rows unchanged. | -2.34 LF header if door + 2.13"
RFI-17 | Walls partly under beams: A-N-G-09 (W12X19 / W8X10) kept to deck; G1-01, G-08, B-01, B-03 weighted under the printed beams (E26). | G-09 weighted: approx -0.3 ft average height (approx -8 LF 1-5/8" stud, -20 SF board)
RFI-18 | Waiting 104 ceiling transition (8/A09.33): its north edge runs parallel to the deck flutes; purlin (8/A09.33 view) not carried on the transition. | +12.77 LF purlin
RFI-19 | Office front jambs 10/A12.01: FRT plywood blocking counted at 10 jamb ends and corner bead at 11 (R73.15 same interface). | +8 LF FRT blocking or -16 LF corner bead
RFI-20 | Ballistic contour B2K: kevlar hatch may run to x 1661.76 (2.207 LF) instead of the 1.773 LF carried (hatch extent read by reading A). | +0.434 LF ballistic panel / 3/8" board / framing
RFI-21 | S1.10 note 7: COLD FORMED STEEL FRAMING and METAL CANOPIES are delegated design / deferred submittals. Engineering and sealed shop drawings excluded unless required. | n/a: engineering cost by others
RFI-22 | Control joints: no gypsum board control joint is labeled in the set (all CJ are stucco / concrete / civil). Excluded; confirm per ASTM C840 / GA-216. | n/a: none carried
RFI-23 | C1 'BLOCK PARTITION' (6/A12.01) has no schedule row: carried 3-5/8" studs + 5/8" gyp one face to deck (break line, R60.11); the block itself is by others. | n/a: C1 framing carried as drawn
RFI-24 | Canopy column wrap top (5/A09.25) not dimensioned: B/CANOPY 10'-6" carried (16/A09.27 soffit B/STUD 10'-7 1/4"). | +0.10 ft x 4 wraps (approx +2 LF 3-5/8" stud, +2 SF FRT plywood)
RFI-25 | Upper 6" CFMF infill row between the canopy beam and the roof beam (A09.21-A09.23 sections): bottom track on the canopy beam top flange not detailed. | n/a: track already carried on the infill rows
RFI-26 | Roof step 4/A02.02: two stacked rows bear on two decks (low and upper); purlin carried on both rows' top tracks. | -38.9 LF purlin if only one row (59.1)

## Review Items
19 questions in total, asked ONE at a time in this order: floor plan (partition types A-Z), then the details the floor plan calls, in order
# | Phase | Type / order | Item | Sheet + detail | Image
1/19 | Floor plan | A1 | A-N-A5-01 / MW01 printer alcove: the partition above the cabinet is carried inside the A5 west wall of Calling Cubes (R77.9), wall extended 3.11 ft over the alcove opening (header single track 4.46 LF). | 6/A12.03 | /home/user/boa28a/work/etapas/3_revision/res_img/item10_A5_N-A5-01_south.png
2/19 | Floor plan | A1K | A1K south run A-S-A1K-01: hatch extent 1.767 LF carried (R72.1); node-to-node reading 2.20 LF (delta +0.433 LF ballistic + framing). | 4/A12.01 | /home/user/boa28a/work/etapas/3_revision/res_img/item06_A1K.png
3/19 | Floor plan | B | A-S-B-03 Wellness north wall: stops under the printed W14x22 over 5.29 ft (weighted height 12.149 ft, E26); B-01 / G-08 / G1-01 same criterion. | 1/A12.01 | /home/user/boa28a/work/etapas/adversarial/img_V2/V2_H1_S2.20_B03_beam.png
4/19 | Floor plan | B2 | Drinking-fountain alcove between the restroom B2 runs: untagged A1 walls carried as a niche of the B2 line (R74.3), 7.49 LF in OTHER FRAMING 'alcove'. PT0025 run: A02.01 prints 5'-6 1/2" and A08.01 5'-5 3/4" (3/4" difference). | 1/A12.01 | /home/user/boa28a/work/etapas/3_revision/res_img/item08-09_A1_corner.png
5/19 | Floor plan | B2K | B2K is not in the A12.01 schedule (RFI-07); hatch 1.773 LF carried vs 2.207 LF if the kevlar hatch runs to the G-07 start (RFI-20, +0.434 LF). | 4/A12.01 | /home/user/boa28a/work/etapas/3_revision/res_img/item05_B2K.png
6/19 | Floor plan | C1 | FCAM furring C1: 2.98 LF + east return 0.58 LF measured from the outside face (R75.7) = 3.56 LF (A 2.98 / B 3.21). Storefront piers C1: interior faces only (R76.5). | 6/A12.01 | /home/user/boa28a/work/etapas/3_revision/res_img/item13_C1_S-C1-03.png
7/19 | Floor plan | EXT-6CFMF | Second 6" CFMF row between the canopy beam and the roof beam on grids G, F, 8, 2, D, 3 (A09.21-A09.23 sections) + row over the grid 2 HSS: carried as stacked walls (split_of). The Partition Takeoff sheet adds their LF to EXT-6CFMF (tool gap P02, about -159.8 LF in that sheet only). | J/A09.23 | /home/user/boa28a/work/etapas/adversarial/img_V1/H1_A02.01_W-2_solid_454-734.png
8/19 | Floor plan | EXT-6CFMF | Exterior LF excludes the storefront spans (R70.7) and runs node to node through the corners (resolution items 1-3, 28): N-F 13.60, W-2 21.89, S-A 53.67 LF. | C/A09.21 | /home/user/boa28a/work/etapas/3_revision/res_img/item03_EXT_N-F.png
9/19 | Floor plan | EXT-PARAPET | Parapet LF measured on the stud CL along each grid run (4/A09.26) with lf_override instead of W2's exterior-wall length, because the exterior LF excludes the storefront spans; corners @16" (RFI-12). | 4/A09.26 | /home/user/boa28a/work/etapas/3_revision/res_img/item22_EXT-PARAPET_A-PAR-03.png
10/19 | Floor plan | G | A-N-G-09 kept to deck although partly under W12X19 / W8X10 (RFI-17); office jamb blocking 10 ends vs corner bead 11 (RFI-19). | 5/A12.01 | /home/user/boa28a/work/etapas/2_lectura/A/img_T2A/A-N-G-09.png
11/19 | Floor plan | G1 | A-S-G1-01 untagged office-front end stub typed G1 by thickness 8.47" (R74.1); alternative A1 by note A. | 5/A12.01 | /home/user/boa28a/work/etapas/3_revision/res_img/item04_G1_S-G1-01.png
12/19 | Detail | 1 | Drive-up ATM recess: 2 1/2" sistered + furring printed, 3 lines each carried (28.25 LF, R79.2); full-height reading 53.67 LF (RFI-06). | 6/A08.11 | /home/user/boa28a/work/etapas/2_lectura/A/img_T7A/A0811_det6_DU_ATM_section.png
13/19 | Detail | 2 | Storefront pier jamb strips 3/4" FRT plywood not measured (RFI-15, approx +24 SF). | 2/A09.25 | /home/user/boa28a/work/etapas/adversarial/img_V1/H4_A09.25_det2_pier_jamb_FRT.png
14/19 | Detail | 3 | Coiling grille 103 head: head 10'-0" (2/A08.21 vector) vs 13'-6 1/2" on A00.30 (RFI-11); 2-1/2" head studs from the R79.1 chain. | 4/A08.21 | /home/user/boa28a/work/etapas/2_lectura/A/img_T8A/A08.21_4_grille_head.png
15/19 | Detail | 4 | HM door R.O. convention door + 4" vs door + 2.13" measured (RFI-16, -2.34 LF header). | 11/A12.02 | /home/user/boa28a/work/etapas/adversarial/img_V3/A12.02_11_jamb_HM.png
16/19 | Detail | 5 | Stud blocking at edge of gypboard: carried on faces taller than a 12 ft sheet per stud row (R78.33); two figures in RFI-14. | 4/S5.20 | /home/user/boa28a/work/etapas/adversarial/img_V4/S520_edge_gypboard.png
17/19 | Detail | 6 | Drive-up canopy band does not label glass mat (RFI-13, +109.9 SF). | 15/A09.27 | /home/user/boa28a/work/etapas/2_lectura/A/img_T5A/DET_15_A09.27_drive_up_canopy_band.png
18/19 | Detail | 7 | Roof step: purlin on both rows bearing on two decks (RFI-26). | 4/A02.02 | /home/user/boa28a/work/etapas/2_lectura/A/img_T5A/DET_4_A02.02_roof_step.png
19/19 | Detail | 8 | CSR soffit framed (9/A12.08 + 10/A09.33): corner bead and FRTW blocking at both drop edges added after the adversarial check (24.04 LF each). | 10/A09.33 | /home/user/boa28a/work/etapas/adversarial/img_V4/A0933_det10_CSR_cornerbead_FRTW.png

## Scope Checklist
Scope ID | Scope | Status | Note (quantity, NOT APPLICABLE + sheet, or RFI)
ALC-01 | Interior partition framing (studs + tracks) | QUANTIFIED | Material Summary: 3-5/8", 6", 1-5/8" metal stud + bottom / top track by size (familias_out.json); A12.01, 7/S5.20
ALC-02 | Exterior wall framing (CFMF) | QUANTIFIED | EXT-6CFMF walls + upper infill rows + storefront cripples (6" metal stud family); A09.21-A09.23, S1.11, S2.20
ALC-03 | Parapet framing | QUANTIFIED | 6" parapet infill stud, bay by bay (E3); 4/A09.26, 11/S5.10
ALC-04 | Top / deflection and bottom track | QUANTIFIED | Bottom track / Top deflection track rows by stud size and element (R71.8, R73.3); A12.01, S5.10
ALC-05 | Headers, sills and jambs at openings | QUANTIFIED | Header / box beam by pieces (E1/E2) + sill track (E18); 7/S5.20, 2/S5.20, A00.30
ALC-06 | Bracing / bridging | QUANTIFIED | Bracing C.R. channel rows = ROUNDUP(H x 12 / 48) - 1 (53.4); S1.11, S5.20
ALC-07 | Gypsum board on walls (layers per type) | QUANTIFIED | 5/8" gypsum board regular, face by face (board_caras); A12.01
ALC-08 | Moisture / abuse / special board at wet zones | QUANTIFIED | 5/8" MOISTURE RESISTANT behind toilet and lavatory only (A08.01 note F)
ALC-09 | Exterior gypsum / glass mat sheathing | QUANTIFIED | 5/8" glass mat sheathing (base strip + canopy band) and 5/8" EXTERIOR gypsum sheathing (parapet roof side); A09.26, A09.27
ALC-10 | FRT plywood sheathing / substrate | QUANTIFIED | FRT plywood by material and use (nailbase, substrate, column wrap, opening substrate, backboards); A09.21, A11.03, A12.01
ALC-11 | Gypsum board ceilings | QUANTIFIED | Suspended GWB ceilings in 5 rooms + CSR framed soffit (A04.01, A9.22 bubbles / A09.33)
ALC-12 | Ceiling suspension (furring / carrying channel / hanger wire / ceiling track) | QUANTIFIED | Furring channel, carrying channel, hanger wire (PCS + LF) and ceiling perimeter track; A04.01 legend, A9.22
ALC-13 | Soffits and bulkheads (framing + board) | QUANTIFIED | CSR soffit 10/A09.33 + office bulkheads 8,9/A12.01 + Waiting transition 8/A09.33 + vestibule heads A12.10
ALC-14 | Canopy / marquee framing and sheathing | QUANTIFIED | Canopy joists, fascia, canopy soffit track, glass mat band, FRT plywood; 3/A09.26, 7/A09.26, 16/A09.27
ALC-15 | Column furring / wraps | QUANTIFIED | CANOPY-COL wraps 5/A09.25 (FOS chain), storefront piers 1,2/A09.25, C1 boxes at grille 3/A08.21
ALC-16 | Blocking (FRT wood / metal) for millwork and accessories | QUANTIFIED | Blocking FRT / 2X FRT wood + metal stud blocking at wall-mounted items; A02.01 notes C, kn 5/6/7, A08.01 note E, A12.01, A00.50
ALC-17 | Framed openings (MEP, access panels, diffusers) | QUANTIFIED | Framed openings - MEP, light slots and diffusers (framed_openings_out.json); E00.01, E02.01, M01.01, A04.01
ALC-18 | Trim: corner bead, casing bead, control joints, reveals | QUANTIFIED | METAL trim row (corner bead, casing, shadow molding); control joints EXCLUDED with RFI (no gypsum CJ labeled: PROJECT_DATA.md section 7)
ALC-19 | Acoustical sealant / sound attenuation (EXCLUDED: estimator standing order, all projects) | NOT APPLICABLE | EXCLUDED: EXCLUDED in all projects (estimator standing order): no acoustical sealant row and no quantity
ALC-20 | FRP / cement board / tile backer | QUANTIFIED | FRP panels + cement board under the tile cove base band (A08.01, A05.01)
ALC-21 | Shaft walls / area separation walls | NOT APPLICABLE | NOT APPLICABLE: A02.01 and A12.01 show no shaft or area separation wall (one-story Type II-B, A00.00 code analysis)
ALC-22 | Rated assemblies (UL designs) and their board type | NOT APPLICABLE | NOT APPLICABLE: A12.02 / A11.03 / M00.01 mention fire-rated plywood and dampers only; no UL partition design in A12.01 (non-rated, A00.00 Type II-B unsprinklered B occupancy)
ALC-23 | Special panels (ballistic, lead-lined, abuse) | QUANTIFIED | Ballistic panel UL752 + 3/8" gypsum board at A1K / B2K (4/A12.01, A02.01 legend KEVLAR)
ALC-24 | Finish level (Level 4 / Level 5) | QUANTIFIED | Level 5 finish SF at WC-18 / WC-22 / WC-20 (A00.40, A05.01 kn 9/10, A11.04); Level 4 elsewhere (assumed, Clarifications)
ALC-X25 | batt insulation | NOT APPLICABLE | EXCLUDED (estimator criterion: no insulation)

## _reglas (hidden)
reglas.py compuerta OK
{"canon": "f9cf4c3d0c7b720e4e4390a17becad4c10cbb7055a1180cb1a5d17e427f01b2c", "evidencias": "b24aea026497f3d78ef21f1d3a6f59511673c702f7e178a4feb3055ff17d5c0b", "familias_out": "c00653f3bf0ad35ca7cd6f58a769f31de349e5c69a13419c7d86cf7ece8f1d61", "reglas": "765fa0be283da1e3f849c9ab1f1f94e210282701890f84fb96862890f4435793", "version": "v73"}