## Inputs
Barnes & Noble - Colorado Springs, CO (3173 Cinema Point) ¦ METAL FRAMING & DRYWALL TAKEOFF
Bid set: Barnes _ Noble - Colorado Springs, CO - COMBINED BID SET - 250918.pdf · 2026-10-24 · Edit ONLY the yellow cells.
PARAMETER | VALUE | NOTE / SOURCE
Waste - ALL METAL, any type | 0.15 | Estimator standing rule: 15% on everything that is metal.
Waste - EVERYTHING THAT IS NOT METAL | 0.06 | Estimator standing rule: same figure as board.
Board sheet width (ft) | 4 | Sheet size is a parameter; buy the size that wastes least.
Board sheet length (ft) | 12 | Change it and every sheet count re-rounds.
SF per board sheet | 48 | Width x length.
Stud stock length (ft) | 20 | Stud, header, framed opening and stud blocking: sticks.
Track stock length (ft) | 10 | Track, sill track and purlin: runs.
Floor plan scale (pt/ft) | n/a | Project value (not used in this take-off: heights are per wall in the Partition Takeoff).
B.O. Deck (ft) | n/a | Project value (not used in this take-off: heights are per wall in the Partition Takeoff).
T.O. Parapet (ft) | n/a | Project value (not used in this take-off: heights are per wall in the Partition Takeoff).
Sealant coverage (LF per tube) | 25 | Sealant yield per tube - set your supplier's figure.
C.R. channel stock length (ft) | 16 | 1-1/2" cold-rolled channel (bracing, carrying channel).
Hat / furring channel stock (ft) | 12 | 7/8" hat furring channel.
Trim stick length (ft) | 10 | Corner bead, casing bead, shadow molding, PVC trim.
Hanger wire purchase | continuous coil (LF) | Bought by LF from a continuous coil; the hanger count goes on its own PCS row.
Drywall screws per SF of board | 1.2 | YIELD: estimator 1.2 / SF; products per A-410 note 8.E (Type S 25/20 ga, Type S-12 18/16/14 ga) and A-001A Div 09 A.5.
Framing screws per stud piece | 4 | YIELD: 2 per stud-to-track connection, each end.
Power-driven pin spacing (ft) | 0.66667 | YIELD: A-410 note 8.F X-DNI 2 rows at 16" O.C. = 0.667 ft per pin (9/A-410 PAF @ 24" = alternative, RFI).
Joint compound (lb per SF) | 0.072 | YIELD: 72 lb per 1,000 SF; Level 4 finish printed on A-001A Div 09 A.8 "PROVIDE AT A MINIMUM A LEVEL 4 FINISH".
Joint tape (LF per SF) | 0.37 | YIELD: 370 LF per 1,000 SF.
Expansion anchor spacing (ft) | 0.66667 | YIELD: exterior bottom track on slab.

## Partition Takeoff
ORGANIZED PARTITION TAKEOFF - Barnes & Noble - Colorado Springs, CO (3173 Cinema Point)
Grouped by partition type. Every row cites its DETAIL/SHEET and its status.
Partition / Scope | Wall # | Length (LF) | Height (FT) | Layers | Stud Size | Stud O.C. (in) | Board (SF) | Location | Source (DETAIL/SHEET) | Status
TYPE 2
2 #W2-01+W2-02 - Storage 112 south wall (door 14, 3'-0" printed, inside wall) + Storage 112 west wall | W2-01+W2-02 | 53.76 | 25 | 2 | 3-5/8" 14 ga SJ | 16 | 2688 | Storage 112 south wall (door 14, 3'-0" printed, inside wall) + Storage 112 west wall | 2/A-410 | [DERIVED]
2 #W2-03 - Stock Room 111 / Sales + Corridor 110 (door 11 inside wall) | W2-03 | 94.24 | 25 | 2 | 3-5/8" 14 ga SJ | 16 | 4508.64 | Stock Room 111 / Sales + Corridor 110 (door 11 inside wall) ¦ Board by face: A Stock Room 111 94.24 x 25 ft (5/8 type X); B Sales Area 101 81.12 x 25 ft (5/8 type X); B Corridor 110 13.12 x 9.5 ft (5/8 type X) | 2/A-410 | [DERIVED]
2 #W2-04 - BOH north wall: Corridor 110 to Manager's Office 105 (Sales side) (door 4 inside wall) | W2-04 | 56.76 | 25 | 2 | 3-5/8" 14 ga SJ | 16 | 1958.22 | BOH north wall: Corridor 110 to Manager's Office 105 (Sales side) (door 4 inside wall) ¦ Board by face: A Sales Area 101 56.76 x 25 ft (5/8 type X); B Corridor 110 29.04 x 9.5 ft (5/8 type X); B Break Room 106 19.03 x 9.5 ft (5/8 type X); B Manager's Office 105 8.69 x 9.5 ft (5/8 type X) | 2/A-410 | [DERIVED]
2 #W2-05 - Corridor 110 / Women's 109 | W2-05 | 12.92 | 25 | 2 | 3-5/8" 14 ga SJ | 16 | 241.73 | Corridor 110 / Women's 109 ¦ Board by face: A Corridor 110 12.92 x 9.5 ft (5/8 type X); B Corridor 110 5.41 x 9.5 ft (5/8 type X); B Women's Restroom 109 7.51 x 9 ft (5/8 type X WR) | 2/A-410 | [DERIVED]
2 #W2-06.1+W2-06.2+W2-06.3+W2-06.4+W2-06.5 - Restrooms 108/109 + Janitor 107 north run with chase jog (doors 9, 8, 7 inside) | W2-06.1+W2-06.2+W2-06.3+W2-06.4+W2-06.5 | 27.54 | 25 | 2 | 3-5/8" 14 ga SJ | 16 | 580.04 | Restrooms 108/109 + Janitor 107 north run with chase jog (doors 9, 8, 7 inside) ¦ Board by face: W2-06.1 A Corridor 110 6.92 x 9.5 ft (5/8 type X); W2-06.1 B Women's Restroom 109 6.92 x 9 ft (5/8 type X WR); W2-06.2 A Women's Restroom 109 2.23 x 9 ft (5/8 type X WR); W2-06.2 B Corridor 110 2.23 x 9.5 ft (5/8 type X WR); W2-06.3 A Corridor 110 4.87 x 9.5 ft (5/8 type X WR); W2-06.3 B Women's Restroom 109 2.41 x 9 ft (5/8 type X WR); W2-06.3 B Men's Restroom 108 2.46 x 9 ft (5/8 type X WR); W2-06.4 A Corridor 110 2.23 x 9.5 ft (5/8 type X WR); W2-06.4 B Men's Restroom 108 2.23 x 9 ft (5/8 type X WR); W2-06.5 A Corridor 110 11.29 x 9.5 ft (5/8 type X); W2-06.5 B Men's Restroom 108 6.88 x 9 ft (5/8 type X WR); W2-06.5 B Janitor Closet 107 4.41 x 25 ft (5/8 type X WR) | 2/A-410 | [DERIVED]
2 #W2-07 - Men's 108 / Janitor 107 | W2-07 | 7.51 | 25 | 2 | 3-5/8" 14 ga SJ | 16 | 255.34 | Men's 108 / Janitor 107 ¦ Board by face: A Men's Restroom 108 7.51 x 9 ft (5/8 type X WR); B Janitor Closet 107 7.51 x 25 ft (5/8 type X WR) | 2/A-410 | [DERIVED]
2 #W2-08 - Janitor 107 / Break Room 106 (door 5 inside wall) | W2-08 | 12.92 | 25 | 2 | 3-5/8" 14 ga SJ | 16 | 361.89 | Janitor 107 / Break Room 106 (door 5 inside wall) ¦ Board by face: A Corridor 110 5.41 x 9.5 ft (5/8 type X); A Janitor Closet 107 7.51 x 25 ft (5/8 type X WR); B Break Room 106 12.92 x 9.5 ft (5/8 type X) | 2/A-410 | [DERIVED]
2 #W2-09 - Break Room 106 / Manager's Office 105 (door 6 inside wall) | W2-09 | 12.92 | 25 | 2 | 3-5/8" 14 ga SJ | 16 | 245.48 | Break Room 106 / Manager's Office 105 (door 6 inside wall) ¦ Board by face: A Break Room 106 12.92 x 9.5 ft (5/8 type X); B Manager's Office 105 12.92 x 9.5 ft (5/8 type X) | 2/A-410 | [DERIVED]
| SUBTOTAL TYPE 2 | 278.57 |  |  |  |  | 10839.34
TYPE 5
5 #W5-01 - Plumbing wall between Women's 109 / Men's 108 | W5-01 | 5.7 | 25 | 2 | 6" 20 ga SJ | 16 | 102.6 | Plumbing wall between Women's 109 / Men's 108 ¦ Board by face: A Women's Restroom 109 5.7 x 9 ft (5/8 type X WR); B Men's Restroom 108 5.7 x 9 ft (5/8 type X WR) | 5/A-410 | [DERIVED]
| SUBTOTAL TYPE 5 | 5.7 |  |  |  |  | 102.6
TYPE 3
3 #W3-01 - Cafe Seating 102, west low wall - west end post | W3-01 | 3.67 | 8 | 2 | 3-5/8" 20 ga | 16 | 58.72 | Cafe Seating 102, west low wall - west end post | 3/A-410 | [DERIVED]
3 #W3-02 - Cafe Seating 102, west low wall - run | W3-02 | 12 | 8 | 2 | 3-5/8" 20 ga | 16 | 192 | Cafe Seating 102, west low wall - run | 3/A-410 | [DERIVED]
3 #W3-03 - Cafe Seating 102, east low wall - run | W3-03 | 12 | 8 | 2 | 3-5/8" 20 ga | 16 | 192 | Cafe Seating 102, east low wall - run | 3/A-410 | [DERIVED]
3 #W3-04 - Cafe Seating 102, east low wall - east end post | W3-04 | 3.67 | 8 | 2 | 3-5/8" 20 ga | 16 | 58.72 | Cafe Seating 102, east low wall - east end post | 3/A-410 | [DERIVED]
3 #W3-05 - Cafe Seating 102, west low wall - east end post | W3-05 | 3.67 | 8 | 2 | 3-5/8" 20 ga | 16 | 58.72 | Cafe Seating 102, west low wall - east end post | 3/A-410 | [DERIVED]
3 #W3-06 - Cafe Seating 102, east low wall - west end post | W3-06 | 3.67 | 8 | 2 | 3-5/8" 20 ga | 16 | 58.72 | Cafe Seating 102, east low wall - west end post | 3/A-410 | [DERIVED]
| SUBTOTAL TYPE 3 | 38.68 |  |  |  |  | 618.88
TYPE 4
4 #W4-28a+W4-28b+W4-28c - Hourglass display feature, north end cap: bar + Hourglass display feature, north end cap: west end return + Hourglass display feature, north end cap: east end return | W4-28a+W4-28b+W4-28c | 12.68 | 7.5 | 2 | 3-5/8" 20 ga | 16 | 190.2 | Hourglass display feature, north end cap: bar + Hourglass display feature, north end cap: west end return + Hourglass display feature, north end cap: east end return | 4/A-410 | [DERIVED]
4 #W4-28d - Hourglass display feature, north end cap: west angled leg from end return to curved wall | W4-28d | 1.77 | 7.5 | 2 | 3-5/8" 20 ga | 16 | 26.56 | Hourglass display feature, north end cap: west angled leg from end return to curved wall | 4/A-410 | [DERIVED]
4 #W4-28e - Hourglass display feature, north end cap: east angled leg from end return to curved wall | W4-28e | 1.72 | 7.5 | 2 | 3-5/8" 20 ga | 16 | 25.8 | Hourglass display feature, north end cap: east angled leg from end return to curved wall | 4/A-410 | [DERIVED]
4 #W4-29a - Hourglass display feature, west curved wall (R=32'-9"), chord 1/6 from north (tagged) | W4-29a | 4.27 | 7.5 | 2 | 3-5/8" 20 ga | 16 | 64.04 | Hourglass display feature, west curved wall (R=32'-9"), chord 1/6 from north (tagged) | 4/A-410 | [DERIVED]
4 #W4-29b - Hourglass display feature, west curved wall (R=32'-9"), chord 2/6 from north | W4-29b | 4.27 | 7.5 | 2 | 3-5/8" 20 ga | 16 | 64.04 | Hourglass display feature, west curved wall (R=32'-9"), chord 2/6 from north | 4/A-410 | [DERIVED]
4 #W4-29c - Hourglass display feature, west curved wall (R=32'-9"), chord 3/6 from north | W4-29c | 4.29 | 7.5 | 2 | 3-5/8" 20 ga | 16 | 64.34 | Hourglass display feature, west curved wall (R=32'-9"), chord 3/6 from north | 4/A-410 | [DERIVED]
4 #W4-29d - Hourglass display feature, west curved wall (R=32'-9"), chord 4/6 from north | W4-29d | 4.29 | 7.5 | 2 | 3-5/8" 20 ga | 16 | 64.34 | Hourglass display feature, west curved wall (R=32'-9"), chord 4/6 from north | 4/A-410 | [DERIVED]
4 #W4-29e - Hourglass display feature, west curved wall (R=32'-9"), chord 5/6 from north | W4-29e | 4.27 | 7.5 | 2 | 3-5/8" 20 ga | 16 | 64.04 | Hourglass display feature, west curved wall (R=32'-9"), chord 5/6 from north | 4/A-410 | [DERIVED]
4 #W4-29f - Hourglass display feature, west curved wall (R=32'-9"), chord 6/6 from north | W4-29f | 4.29 | 7.5 | 2 | 3-5/8" 20 ga | 16 | 64.34 | Hourglass display feature, west curved wall (R=32'-9"), chord 6/6 from north | 4/A-410 | [DERIVED]
4 #W4-30a - Hourglass display feature, east curved wall (R=32'-9"), chord 1/6 from north (tagged) | W4-30a | 4.28 | 7.5 | 2 | 3-5/8" 20 ga | 16 | 64.2 | Hourglass display feature, east curved wall (R=32'-9"), chord 1/6 from north (tagged) | 4/A-410 | [DERIVED]
4 #W4-30b - Hourglass display feature, east curved wall (R=32'-9"), chord 2/6 from north | W4-30b | 4.28 | 7.5 | 2 | 3-5/8" 20 ga | 16 | 64.2 | Hourglass display feature, east curved wall (R=32'-9"), chord 2/6 from north | 4/A-410 | [DERIVED]
4 #W4-30c - Hourglass display feature, east curved wall (R=32'-9"), chord 3/6 from north | W4-30c | 4.28 | 7.5 | 2 | 3-5/8" 20 ga | 16 | 64.2 | Hourglass display feature, east curved wall (R=32'-9"), chord 3/6 from north | 4/A-410 | [DERIVED]
4 #W4-30d - Hourglass display feature, east curved wall (R=32'-9"), chord 4/6 from north | W4-30d | 4.28 | 7.5 | 2 | 3-5/8" 20 ga | 16 | 64.2 | Hourglass display feature, east curved wall (R=32'-9"), chord 4/6 from north | 4/A-410 | [DERIVED]
4 #W4-30e - Hourglass display feature, east curved wall (R=32'-9"), chord 5/6 from north | W4-30e | 4.28 | 7.5 | 2 | 3-5/8" 20 ga | 16 | 64.2 | Hourglass display feature, east curved wall (R=32'-9"), chord 5/6 from north | 4/A-410 | [DERIVED]
4 #W4-30f - Hourglass display feature, east curved wall (R=32'-9"), chord 6/6 from north | W4-30f | 4.28 | 7.5 | 2 | 3-5/8" 20 ga | 16 | 64.2 | Hourglass display feature, east curved wall (R=32'-9"), chord 6/6 from north | 4/A-410 | [DERIVED]
4 #W4-31a+W4-31b+W4-31c - Hourglass display feature, south end cap: bar (untagged TYP. copy of the PT0037 north cap) + Hourglass display feature, south end cap: west end return (untagged TYP. copy of the PT0037 north cap) + Hourglass display feature, south end cap: east end return (untagged TYP. copy of the PT0037 north cap) | W4-31a+W4-31b+W4-31c | 12.68 | 7.5 | 2 | 3-5/8" 20 ga | 16 | 190.2 | Hourglass display feature, south end cap: bar (untagged TYP. copy of the PT0037 north cap) + Hourglass display feature, south end cap: west end return (untagged TYP. copy of the PT0037 north cap) + Hourglass display feature, south end cap: east end return (untagged TYP. copy of the PT0037 north cap) | 4/A-410 | [DERIVED]
4 #W4-31d - Hourglass display feature, south end cap: west angled leg from end return to curved wall (untagged TYP. copy of the PT0037 north cap) | W4-31d | 1.75 | 7.5 | 2 | 3-5/8" 20 ga | 16 | 26.24 | Hourglass display feature, south end cap: west angled leg from end return to curved wall (untagged TYP. copy of the PT0037 north cap) | 4/A-410 | [DERIVED]
4 #W4-31e - Hourglass display feature, south end cap: east angled leg from end return to curved wall (untagged TYP. copy of the PT0037 north cap) | W4-31e | 1.68 | 7.5 | 2 | 3-5/8" 20 ga | 16 | 25.2 | Hourglass display feature, south end cap: east angled leg from end return to curved wall (untagged TYP. copy of the PT0037 north cap) | 4/A-410 | [DERIVED]
| SUBTOTAL TYPE 4 | 83.64 |  |  |  |  | 1254.54
TYPE H1
H1 #C-H1-N - Cafe Workroom 104 north wall (to Sales / Grab & Go) | C-H1-N | 29.98 | 25 | 1 | 6" 20 ga SJ | 16 | 678.44 | Cafe Workroom 104 north wall (to Sales / Grab & Go) ¦ Board by face: A Sales Area 101 25.9 x 25 ft (5/8 type X); A Grab & Go 4.08 x 7.58 ft (5/8 type X) | G/A-221 | [DERIVED]
H1 #C-H1-W - Cafe Workroom 104 west wall | C-H1-W | 12.17 | 25 | 1 | 6" 20 ga SJ | 16 | 115.61 | Cafe Workroom 104 west wall ¦ Board by face: A Manager's Office 105 12.17 x 9.5 ft (5/8 type X) | G/A-221 | [DERIVED]
| SUBTOTAL TYPE H1 | 42.15 |  |  |  |  | 794.05
TYPE H2A
H2A #C-H2a - Cafe Workroom 104 / Cafe Sales (4'-0" door inside wall) | C-H2a | 12.17 | 25 | 1 | 3-5/8" 14 ga SJ | 16 | 304.25 | Cafe Workroom 104 / Cafe Sales (4'-0" door inside wall) ¦ Board by face: B Cafe 103 12.17 x 25 ft (5/8 type X) | G/A-221 | [DERIVED]
| SUBTOTAL TYPE H2A | 12.17 |  |  |  |  | 304.25
TYPE H2B
H2B #C-H2b - Cafe Workroom 104 stub wall | C-H2b | 1.95 | 25 | 0 | 3-5/8" 14 ga SJ | 16 | 0 | Cafe Workroom 104 stub wall | G/A-221 | [DERIVED]
| SUBTOTAL TYPE H2B | 1.95 |  |  |  |  | 0
TYPE H3A
H3A #C-H3a - Grab & Go north wall | C-H3a | 4.08 | 25 | 1 | 6" 20 ga SJ | 16 | 30.94 | Grab & Go north wall ¦ Board by face: B Grab & Go 4.08 x 7.58 ft (5/8 type X) | H/A-221 | [DERIVED]
| SUBTOTAL TYPE H3A | 4.08 |  |  |  |  | 30.94
TYPE H3B
H3B #C-H3b - Grab & Go west wall | C-H3b | 6.17 | 25 | 2 | 6" 20 ga SJ | 16 | 151.68 | Grab & Go west wall ¦ Board by face: B Grab & Go 6.17 x 7.58 ft (5/8 type X); A Sales Area 101 6.17 x 17 ft (5/8 type X) | H/A-221 | [DERIVED]
| SUBTOTAL TYPE H3B | 6.17 |  |  |  |  | 151.68
TYPE E2
E2 #C-E2 - South wall, Cafe Workroom 104 (in front of demising / exterior wall) | C-E2 | 29.3 | 25 | 0 | 6" 20 ga SJ | 16 | 0 | South wall, Cafe Workroom 104 (in front of demising / exterior wall) | E/A-221 | [DERIVED]
| SUBTOTAL TYPE E2 | 29.3 |  |  |  |  | 0
TYPE E1
E1 #C-E1-B - Box at SE corner of Cafe Sales - west side | C-E1-B | 2.31 | 25 | 1 | 6" 20 ga SJ | 16 | 57.75 | Box at SE corner of Cafe Sales - west side | E/A-221 | [DERIVED]
E1 #C-E1-P.2 - Pier at Workroom door (1'-0" x 2'-8" HOLD printed) | C-E1-P.2 | 2.11 | 25 | 1 | 6" 20 ga SJ | 16 | 52.75 | Pier at Workroom door (1'-0" x 2'-8" HOLD printed) | E/A-221 | [DERIVED]
E1 #C-E1-S - South wall, Cafe Sales 103 (in front of exterior wall) | C-E1-S | 23.46 | 25 | 0.81 | 6" 20 ga SJ | 16 | 475 | South wall, Cafe Sales 103 (in front of exterior wall) ¦ Board by face: A Cafe 103 19 x 25 ft (1/2 cement board); A concealed: behind the Workroom door pier and inside the SE box (no cement board) 4.46 x 0 ft (1/2 cement board) | E/A-221 | [DERIVED]
| SUBTOTAL TYPE E1 | 27.88 |  |  |  |  | 585.5
TYPE F
F #C-F - Box at SE corner of Cafe Sales - north side (3'-3" printed) | C-F | 3.26 | 25 | 0 | 3-5/8" 14 ga SJ | 16 | 0 | Box at SE corner of Cafe Sales - north side (3'-3" printed) | F/A-221 | [DERIVED]
| SUBTOTAL TYPE F | 3.26 |  |  |  |  | 0
TYPE I
I #C-I - Box at SE corner of Cafe Sales - east side | C-I | 2.31 | 25 | 1 | 6" 20 ga SJ | 16 | 23.1 | Box at SE corner of Cafe Sales - east side ¦ Board by face: A Cafe 103 2.31 x 10 ft (5/8 type X) | I/A-221 | [DERIVED]
I #C-I-E1 - Type I end face (I SIM.) at the east end of C-H3a, Sales side | C-I-E1 | 0.603 | 25 | 1 | 6" 20 ga SJ | 16 | 6.03 | Type I end face (I SIM.) at the east end of C-H3a, Sales side ¦ Board by face: A Sales Area 101 0.6 x 10 ft (5/8 type X) | I/A-221 | [DERIVED]
I #C-I-E2 - Type I end face (I SIM.) at the east end of C-H1-N, Sales side | C-I-E2 | 0.603 | 25 | 1 | 6" 20 ga SJ | 16 | 6.03 | Type I end face (I SIM.) at the east end of C-H1-N, Sales side ¦ Board by face: A Sales Area 101 0.6 x 10 ft (5/8 type X) | I/A-221 | [DERIVED]
I #C-I-P.1 - 1'-0" return at the top of the Workroom door pier (I tag) | C-I-P.1 | 1 | 25 | 1 | 6" 20 ga SJ | 16 | 10 | 1'-0" return at the top of the Workroom door pier (I tag) ¦ Board by face: A Cafe 103 1 x 10 ft (5/8 type X) | I/A-221 | [DERIVED]
| SUBTOTAL TYPE I | 4.516 |  |  |  |  | 45.16
TYPE A
A #C-A-1 - Front counter - straight run | C-A-1 | 9.89 | 2.708 | 2 | 3-5/8" 20 ga | 16 | 53.56 | Front counter - straight run | A/A-221 | [DERIVED]
A #C-A-2 - Front counter - 45 deg segment | C-A-2 | 4.14 | 2.708 | 2 | 3-5/8" 20 ga | 16 | 22.42 | Front counter - 45 deg segment | A/A-221 | [DERIVED]
A #C-A-3 - Front counter - east run to box | C-A-3 | 6.24 | 2.708 | 2 | 3-5/8" 20 ga | 16 | 33.8 | Front counter - east run to box | A/A-221 | [DERIVED]
| SUBTOTAL TYPE A | 20.27 |  |  |  |  | 109.78
TYPE B
B #C-B - Pastry counter - west leg | C-B | 3.17 | 2.708 | 2 | 3-5/8" 20 ga | 16 | 17.16 | Pastry counter - west leg | B/A-221 | [DERIVED]
| SUBTOTAL TYPE B | 3.17 |  |  |  |  | 17.16
TYPE D
D #C-D - Pastry counter - south (between legs) | C-D | 5.14 | 1 | 2 | 3-5/8" 20 ga | 16 | 10.28 | Pastry counter - south (between legs) | D/A-221 | [DERIVED]
| SUBTOTAL TYPE D | 5.14 |  |  |  |  | 10.28
TYPE C
C #C-C - Pastry counter - east leg | C-C | 3.17 | 2.708 | 2 | 3-5/8" 20 ga | 16 | 17.16 | Pastry counter - east leg | C/A-221 | [DERIVED]
| SUBTOTAL TYPE C | 3.17 |  |  |  |  | 17.16
| TOTAL - PARTITIONS (GRAND TOTAL) | 569.816 |  |  |  |  | 14881.32
TYPE OTHER FRAMING (NOT A PARTITION)
column_wrap #CW-01 - Sales Area 101 - existing column, new 24"x24" GWB surround (keynote C25) | CW-01 | 8 | 8 | 1 | 3-5/8" 20 ga | 16 | 64 | Sales Area 101 - existing column, new 24"x24" GWB surround (keynote C25) | C25/A-101 | [DERIVED]
column_wrap #CW-02 - Sales Area 101 - existing column, new 24"x24" GWB surround (keynote C25) | CW-02 | 8 | 8 | 1 | 3-5/8" 20 ga | 16 | 64 | Sales Area 101 - existing column, new 24"x24" GWB surround (keynote C25) | C25/A-101 | [DERIVED]
column_wrap #CW-03 - Sales Area 101 - existing column, new 24"x24" GWB surround (keynote C25) | CW-03 | 8 | 8 | 1 | 3-5/8" 20 ga | 16 | 64 | Sales Area 101 - existing column, new 24"x24" GWB surround (keynote C25) | C25/A-101 | [DERIVED]
column_wrap #CW-04 - Sales Area 101 - existing column, new 24"x24" GWB surround (keynote C25) | CW-04 | 8 | 8 | 1 | 3-5/8" 20 ga | 16 | 64 | Sales Area 101 - existing column, new 24"x24" GWB surround (keynote C25) | C25/A-101 | [DERIVED]
column_wrap #CW-05 - Sales Area 101 - existing column, new 24"x24" GWB surround (keynote C25) | CW-05 | 8 | 8 | 1 | 3-5/8" 20 ga | 16 | 64 | Sales Area 101 - existing column, new 24"x24" GWB surround (keynote C25) | C25/A-101 | [DERIVED]
column_wrap #CW-06 - Sales Area 101 - existing column, new 24"x24" GWB surround (keynote C25) | CW-06 | 8 | 8 | 1 | 3-5/8" 20 ga | 16 | 64 | Sales Area 101 - existing column, new 24"x24" GWB surround (keynote C25) | C25/A-101 | [DERIVED]
column_wrap #CW-07 - Sales Area 101 - existing column, new 24"x24" GWB surround (keynote C25) | CW-07 | 8 | 8 | 1 | 3-5/8" 20 ga | 16 | 64 | Sales Area 101 - existing column, new 24"x24" GWB surround (keynote C25) | C25/A-101 | [DERIVED]
column_wrap #CW-08 - Sales Area 101 - existing column, new 24"x24" GWB surround (keynote C25) | CW-08 | 8 | 8 | 1 | 3-5/8" 20 ga | 16 | 64 | Sales Area 101 - existing column, new 24"x24" GWB surround (keynote C25) | C25/A-101 | [DERIVED]
column_wrap #CW-09 - Sales Area 101 - existing column, new 24"x24" GWB surround (keynote C25) | CW-09 | 8 | 8 | 1 | 3-5/8" 20 ga | 16 | 64 | Sales Area 101 - existing column, new 24"x24" GWB surround (keynote C25) | C25/A-101 | [DERIVED]
soffit_side #SS-N - Cafe 11'-0" zone N open edge to Sales | SS-N | 22.77 | 14 | 1 | 3-5/8" 20 ga | 16 | 227.7 | Cafe 11'-0" zone N open edge to Sales ¦ Board by face: A Cafe 103 22.77 x 10 ft (5/8 type X) | 2/A-221 | [DERIVED]
soffit_side #SS-E - Cafe 11'-0" zone E open edge to Sales | SS-E | 10.12 | 14 | 1 | 3-5/8" 20 ga | 16 | 101.2 | Cafe 11'-0" zone E open edge to Sales ¦ Board by face: A Cafe 103 10.12 x 10 ft (5/8 type X) | 2/A-221 | [DERIVED]
soffit_side #SS-IN-N - Cafe 11'-6" band N edge (6" step) | SS-IN-N | 20 | 13.5 | 1 | 3-5/8" 20 ga | 16 | 10 | Cafe 11'-6" band N edge (6" step) ¦ Board by face: A Cafe 103 20 x 0.5 ft (5/8 type X) | 2/A-221 | [DERIVED]
soffit_side #SS-IN-E - Cafe 11'-6" band E edge (6" step) | SS-IN-E | 6.25 | 13.5 | 1 | 3-5/8" 20 ga | 16 | 3.12 | Cafe 11'-6" band E edge (6" step) ¦ Board by face: A Cafe 103 6.25 x 0.5 ft (5/8 type X) | 2/A-221 | [DERIVED]
soffit_side #SS-GG - Grab & Go header soffit over the open east side (6'-2" HOLD) | SS-GG | 6.167 | 17.917 | 1 | 6" 20 ga SJ | 16 | 61.67 | Grab & Go header soffit over the open east side (6'-2" HOLD) ¦ Board by face: A Sales Area 101 6.17 x 10 ft (5/8 type X) | 3/A-221 | [DERIVED]

## Material Summary
MATERIAL SUMMARY - NET / WASTE / PURCHASE
Waste lives HERE, in its own column, applied ONCE: Pieces = ROUNDUP(Net x (1 + waste) / stock). Every stock length, coverage and yield is an Inputs cell.
Material | Unit | Net | Waste % | Waste | Purchase | Selling unit | Pieces to buy | Where it comes from | Yield check (live formula)
Bottom track 3-5/8" | LF | 450.02 | 0.15 | 67.503 | 517.523 | run 10 ft | 52 | N/SHEET: 2/A-410, 3/A-410, 4/A-410, G/A-221, F/A-221, A/A-221, B/A-221, D/A-221, C/A-221 ¦ Breakdown [DERIVED]: W2-01 48.77 + W2-02 4.99 + W2-03 94.24 + W2-04 56.76 + W2-05 12.92 + W2-06.1 6.92 + W2-06.2 2.23 + W2-06.3 4.87 + W2-06.4 2.23 + W2-06.5 11.29 + W2-07 7.51 + W2-08 12.92 + W2-09 12.92 + W3-01 3.67 + W3-02 12 + W3-05 3.67 + W3-03 12 + W3-06 3.67 + W3-04 3.67 + W4-28a 9 + W4-28b 1.84 + W4-28c 1.84 + W4-28d 1.77 + W4-28e 1.72 + W4-29a 4.27 + W4-29b 4.27 + W4-29c 4.29 + W4-29d 4.29 + W4-29e 4.27 + W4-29f 4.29 + W4-30a 4.28 + W4-30b 4.28 + W4-30c 4.28 + W4-30d 4.28 + W4-30e 4.28 + W4-30f 4.28 + W4-31a 9 + W4-31b 1.84 + W4-31c 1.84 + W4-31d 1.75 + W4-31e 1.68 + C-H2a 12.17 + C-H2b 1.95 + C-F 3.26 + C-A-1 9.89 + C-A-2 4.14 + C-A-3 6.24 + C-B 3.17 + C-D 5.14 + C-C 3.17 = 450.02 LF (wall length x rows) ¦ Track gauge = stud gauge (A-410 schedule note 2): 14 ga SJ 295.95 LF; 20 ga 154.07 LF
Bottom track 6" | LF | 118.59 | 0.15 | 17.7885 | 136.3785 | run 10 ft | 14 | N/SHEET: 5/A-410, G/A-221, H/A-221, E/A-221, I/A-221 ¦ Breakdown [DERIVED]: W5-01 5.7 + C-H1-N 29.98 + C-H1-W 12.17 + C-H3a 4.08 + C-H3b 6.17 + C-E2 29.3 + C-E1-S 23.46 + C-I-P.1 1 + C-E1-P.2 2.11 + C-E1-B 2.31 + C-I 2.31 = 118.59 LF (wall length x rows) ¦ Track gauge = stud gauge (A-410 schedule note 2): 20 ga SJ 118.59 LF
Bottom track - other framing (not a partition type, see source) | LF | 72 | 0.15 | 10.8 | 82.8 | run 10 ft | 9 | N/SHEET: C25/A-101 ¦ Breakdown [DERIVED]: CW-01 8 + CW-02 8 + CW-03 8 + CW-04 8 + CW-05 8 + CW-06 8 + CW-07 8 + CW-08 8 + CW-09 8 = 72 LF (wall length x rows) ¦ Track gauge = stud gauge (A-410 schedule note 2): 20 ga 72 LF
Top / deflection track 3-5/8" | LF | 450.02 | 0.15 | 67.503 | 517.523 | run 10 ft | 52 | N/SHEET: 2/A-410, 3/A-410, 4/A-410, G/A-221, F/A-221, A/A-221, B/A-221, D/A-221, C/A-221 ¦ Breakdown [DERIVED]: W2-01 48.77 + W2-02 4.99 + W2-03 94.24 + W2-04 56.76 + W2-05 12.92 + W2-06.1 6.92 + W2-06.2 2.23 + W2-06.3 4.87 + W2-06.4 2.23 + W2-06.5 11.29 + W2-07 7.51 + W2-08 12.92 + W2-09 12.92 + W3-01 3.67 + W3-02 12 + W3-05 3.67 + W3-03 12 + W3-06 3.67 + W3-04 3.67 + W4-28a 9 + W4-28b 1.84 + W4-28c 1.84 + W4-28d 1.77 + W4-28e 1.72 + W4-29a 4.27 + W4-29b 4.27 + W4-29c 4.29 + W4-29d 4.29 + W4-29e 4.27 + W4-29f 4.29 + W4-30a 4.28 + W4-30b 4.28 + W4-30c 4.28 + W4-30d 4.28 + W4-30e 4.28 + W4-30f 4.28 + W4-31a 9 + W4-31b 1.84 + W4-31c 1.84 + W4-31d 1.75 + W4-31e 1.68 + C-H2a 12.17 + C-H2b 1.95 + C-F 3.26 + C-A-1 9.89 + C-A-2 4.14 + C-A-3 6.24 + C-B 3.17 + C-D 5.14 + C-C 3.17 = 450.02 LF (wall length x rows) ¦ Track gauge = stud gauge (A-410 schedule note 2): 14 ga SJ 295.95 LF; 20 ga 154.07 LF
Top / deflection track 6" | LF | 118.59 | 0.15 | 17.7885 | 136.3785 | run 10 ft | 14 | N/SHEET: 5/A-410, G/A-221, H/A-221, E/A-221, I/A-221 ¦ Breakdown [DERIVED]: W5-01 5.7 + C-H1-N 29.98 + C-H1-W 12.17 + C-H3a 4.08 + C-H3b 6.17 + C-E2 29.3 + C-E1-S 23.46 + C-I-P.1 1 + C-E1-P.2 2.11 + C-E1-B 2.31 + C-I 2.31 = 118.59 LF (wall length x rows) ¦ Track gauge = stud gauge (A-410 schedule note 2): 20 ga SJ 118.59 LF
Top / deflection track - other framing (not a partition type, see source) | LF | 72 | 0.15 | 10.8 | 82.8 | run 10 ft | 9 | N/SHEET: C25/A-101 ¦ Breakdown [DERIVED]: CW-01 8 + CW-02 8 + CW-03 8 + CW-04 8 + CW-05 8 + CW-06 8 + CW-07 8 + CW-08 8 + CW-09 8 = 72 LF (wall length x rows) ¦ Track gauge = stud gauge (A-410 schedule note 2): 20 ga 72 LF
8" stud (all gauges) | LF | 25.33 | 0.15 | 3.7995 | 29.1295 | stick 20 ft | 2 | N/SHEET: 8/A-210 ¦ Breakdown [DERIVED]: VEST-BOX-BEAM-STUD 25.33 = 25.33 LF (per wall: field + jambs + nodes + cripples x height; plus listed elements)
6" metal stud (LF of material) | LF | 3162.5 | 0.15 | 474.375 | 3636.875 | stick 20 ft | 182 | N/SHEET: 5/A-410, G/A-221, H/A-221, E/A-221, I/A-221, 3/A-221, 8/A-410 ¦ Breakdown [DERIVED]: W5-01 175 + C-H1-N 650 + C-H1-W 300 + C-H3a 150 + C-H3b 175 + C-E2 575 + C-E1-S 525 + C-I-P.1 75 + C-E1-P.2 75 + C-E1-B 125 + C-I 75 + SS-GG 107.5 + CROSS-MEMBERS-8-A410-6 155 = 3,162.5 LF (per wall: field + jambs + nodes + cripples x height; plus listed elements) ¦ By gauge (A-410 Metal Stud Schedule): 20 ga SJ 3,007.5 LF; elements (gauge in their operation) 155 LF
3-5/8" metal stud (LF of material) | LF | 11601.59 | 0.15 | 1740.2385 | 13341.8285 | stick 20 ft | 668 | N/SHEET: 2/A-410, 3/A-410, 4/A-410, G/A-221, F/A-221, A/A-221, B/A-221, D/A-221, C/A-221, 2/A-221, C25/A-101, 7/A-210, 8/A-410 ¦ Breakdown [DERIVED]: W2-01 1,061 + W2-02 125 + W2-03 1,879 + W2-04 1,211 + W2-05 300 + W2-06.1 311 + W2-06.2 100 + W2-06.3 150 + W2-06.4 100 + W2-06.5 447 + W2-07 200 + W2-08 386 + W2-09 386 + W3-01 32 + W3-02 96 + W3-05 32 + W3-03 96 + W3-06 32 + W3-04 32 + W4-28a 75 + W4-28b 30 + W4-28c 30 + W4-28d 30 + W4-28e 30 + W4-29a 45 + W4-29b 45 + W4-29c 45 + W4-29d 45 + W4-29e 45 + W4-29f 45 + W4-30a 45 + W4-30b 45 + W4-30c 45 + W4-30d 45 + W4-30e 45 + W4-30f 45 + W4-31a 75 + W4-31b 30 + W4-31c 30 + W4-31d 22.5 + W4-31e 22.5 + C-H2a 376 + C-H2b 100 + C-F 125 + C-A-1 29.79 + C-A-2 16.25 + C-A-3 18.96 + C-B 16.25 + C-D 6 + C-C 10.83 + SS-N 280 + SS-E 126 + SS-IN-N 243 + SS-IN-E 81 + CW-01 96 + CW-02 96 + CW-03 96 + CW-04 96 + CW-05 96 + CW-06 96 + CW-07 96 + CW-08 96 + CW-09 96 + DIAG-BRACES-T2 468 + VEST-POSTS-STUD 126 + WH-BACKING-STUD 8 + WH-STEEL-BLOCKING 2.67 + DIAG-BRACES-CAFE 44 + CROSS-MEMBERS-8-A410-3 550 + SOFFIT-CROSS-BRACING-2-A221 90 + F-NESTED-BRACING 6.52 + NESTED-BRACING-T3-T4 122.32 = 11,601.59 LF (per wall: field + jambs + nodes + cripples x height; plus listed elements) ¦ By gauge (A-410 Metal Stud Schedule): 14 ga SJ 7,257 LF; 20 ga 2,927.08 LF; elements (gauge in their operation) 1,417.51 LF
Ceiling perimeter track at GWB ceilings (size not printed, RFI) | LF | 180.99 | 0.15 | 27.1485 | 208.1385 | run 10 ft | 21 | N/SHEET: 1/A-121, 5/A-121 ¦ Breakdown [DERIVED]: Women's Restroom 109 32.33 + Men's Restroom 108 32.33 + Cafe 103 - 11'-6" GWB band 52.51 + Cafe 103 - 9'-0" GWB band 43.33 + Grab & Go 20.49 = 180.99 LF
Bracing 1-1/2" C.R. channel @ 48" O.C. | LF | 2883.65 | 0.15 | 432.5475 | 3316.1975 | C.R. channel 16 ft | 208 | N/SHEET: 5/A-410, 2/A-410, 5/A-410, 3/A-410, 4/A-410, C25/A-101, G/A-221, H/A-221, E/A-221, I/A-221, F/A-221, 2/A-221, 3/A-221 ¦ Breakdown [DERIVED]: W2-01 292.62 + W2-02 29.94 + W2-03 565.44 + W2-04 340.56 + W2-05 77.52 + W2-06.1 41.52 + W2-06.2 13.38 + W2-06.3 29.22 + W2-06.4 13.38 + W2-06.5 67.74 + W2-07 45.06 + W2-08 77.52 + W2-09 77.52 + W5-01 34.2 + W3-01 3.67 + W3-02 12 + W3-05 3.67 + W3-03 12 + W3-06 3.67 + W3-04 3.67 + W4-28a 9 + W4-28b 1.84 + W4-28c 1.84 + W4-28d 1.77 + W4-28e 1.72 + W4-29a 4.27 + W4-29b 4.27 + W4-29c 4.29 + W4-29d 4.29 + W4-29e 4.27 + W4-29f 4.29 + W4-30a 4.28 + W4-30b 4.28 + W4-30c 4.28 + W4-30d 4.28 + W4-30e 4.28 + W4-30f 4.28 + W4-31a 9 + W4-31b 1.84 + W4-31c 1.84 + W4-31d 1.75 + W4-31e 1.68 + CW-01 8 + CW-02 8 + CW-03 8 + CW-04 8 + CW-05 8 + CW-06 8 + CW-07 8 + CW-08 8 + CW-09 8 + C-H1-N 179.88 + C-H1-W 73.02 + C-H2a 73.02 + C-H2b 11.7 + C-H3a 24.48 + C-H3b 37.02 + C-E2 175.8 + C-E1-S 140.76 + C-I-P.1 6 + C-E1-P.2 12.66 + C-E1-B 13.86 + C-F 19.56 + C-I 13.86 + SS-N 68.31 + SS-E 30.36 + SS-IN-N 60 + SS-IN-E 18.75 + SS-GG 24.67 = 2,883.65 LF (rows = ROUNDUP(H x 12 / 48) - 1, x length)
Furring channel (ceilings) | LF | 207.45 | 0.15 | 31.1175 | 238.5675 | hat channel 12 ft | 20 | N/SHEET: 5/A-121, 1/A-121 ¦ Breakdown [DERIVED]: Women's Restroom 109 42.36 + Men's Restroom 108 42.31 + Cafe 103 - 11'-6" GWB band 68.78 + Cafe 103 - 9'-0" GWB band 29.34 + Grab & Go 24.67 = 207.46 LF
Carrying channel (ceilings) | LF | 159.16 | 0.15 | 23.874 | 183.034 | C.R. channel 16 ft | 12 | N/SHEET: 5/A-121, 1/A-121 ¦ Breakdown [DERIVED]: Women's Restroom 109 24.48 + Men's Restroom 108 24.44 + Cafe 103 - 11'-6" GWB band 60 + Cafe 103 - 9'-0" GWB band 38 + Grab & Go 12.24 = 159.16 LF
Hanger wire | LF | 2689.79 | 0.15 | 403.4685 | 3093.2585 | continuous coil (LF) | 3094 | N/SHEET: 5/A-121, 1/A-121 ¦ Breakdown [DERIVED]: Women's Restroom 109 144 + Men's Restroom 108 144 + Cafe 103 - 11'-6" GWB band 243 + Cafe 103 - 9'-0" GWB band 192 + Cafe Seating Area 102 - GWB cloud 715 + Grab & Go 107.5 + HANGERS-FIXTURES-5-A121 401 + SPLAY-WIRES-5-A121 743.29 = 2,689.79 LF (hangers @ 48" O.C. x drop to deck per room)
Blocking FRT / 2X FRT wood | LF | 568.27 | 0.15 | 85.2405 | 653.5105 | 2x lumber 8 ft | 82 | N/SHEET: 7/A-413, 8A/A-413, 4/A-412, 6/A-412, 4/A-101, 2/A-500 ¦ Breakdown [DERIVED]: BLK-STOCK 387 + BLK-RECEIVING 69 + BLK-OFFICE 85.6 + BLK-BREAK 10.67 + BLK-FE-CABINETS 16 = 568.27 LF
5/8" gypsum board, Type X | SF | 15109.29 | 0.06 | 906.5574 | 16015.8474 | 4x12 ft sheet (Inputs) | 334 | N/SHEET: 2/A-410, 3/A-410, 4/A-410, C25/A-101, G/A-221, H/A-221, I/A-221, 2/A-221, 3/A-221, 5/A-121, 4/A-121, 4/A-210, 2/A-210, A-001A ¦ Breakdown [DERIVED]: W2-01 2,438.5 + W2-02 249.5 + W2-03 4,508.64 + W2-04 1,958.22 + W2-05 174.14 + W2-06.1 65.74 + W2-06.5 107.25 + W2-08 174.14 + W2-09 245.48 + W3-01 58.72 + W3-02 192 + W3-05 58.72 + W3-03 192 + W3-06 58.72 + W3-04 58.72 + W4-28a 135 + W4-28b 27.6 + W4-28c 27.6 + W4-28d 26.56 + W4-28e 25.8 + W4-29a 64.04 + W4-29b 64.04 + W4-29c 64.34 + W4-29d 64.34 + W4-29e 64.04 + W4-29f 64.34 + W4-30a 64.2 + W4-30b 64.2 + W4-30c 64.2 + W4-30d 64.2 + W4-30e 64.2 + W4-30f 64.2 + W4-31a 135 + W4-31b 27.6 + W4-31c 27.6 + W4-31d 26.24 + W4-31e 25.2 + CW-01 64 + CW-02 64 + CW-03 64 + CW-04 64 + CW-05 64 + CW-06 64 + CW-07 64 + CW-08 64 + CW-09 64 + C-H1-N 678.44 + C-H1-W 115.61 + C-H2a 304.25 + C-H3a 30.94 + C-H3b 151.68 + C-I-P.1 10 + C-I 23.1 + SS-N 227.7 + SS-E 101.2 + SS-IN-N 10 + SS-IN-E 3.12 + SS-GG 61.67 + C-I-E1 6.03 + C-I-E2 6.03 + ceiling Cafe 103 - 11'-6" GWB band 125.07 + ceiling Cafe 103 - 9'-0" GWB band 50.67 + ceiling Cafe Seating Area 102 - GWB cloud 573.69 + ceiling Cafe 103 - 11'-0" GWB zone 109.65 + ceiling Grab & Go 25.16 + VEST-GWB 105.5 + SS-GG-BOTTOM-GWB 3.73 + VEST-GWB-BANDS 14.96 = 15,109.23 SF (faces: length x face height x layers - openings; ceilings: RCP area)
5/8" gypsum board, Type X W.R. (water resistant) | SF | 1092.59 | 0.06 | 65.5554 | 1158.1454 | 4x12 ft sheet (Inputs) | 25 | N/SHEET: 2/A-410, 5/A-410, 5/A-121, 22/A-201, A-001A ¦ Breakdown [DERIVED]: W2-05 67.59 + W2-06.1 62.28 + W2-06.2 41.25 + W2-06.3 90.1 + W2-06.4 41.25 + W2-06.5 172.17 + W2-07 255.34 + W2-08 187.75 + W5-01 102.6 + ceiling Women's Restroom 109 61.19 + ceiling Men's Restroom 108 61.11 + RESTROOM-BASE-WR-DEDUCT -50.04 = 1,092.59 SF (faces: length x face height x layers - openings; ceilings: RCP area)
8" metal joist (ceiling box) | LF | 88 | 0.15 | 13.2 | 101.2 | stick 20 ft | 6 | N/SHEET: 4/A-210 ¦ 8" JOISTS @ 16" O.C.: ROUNDUP(152/16)+1 = 11 x (7'-8" + 2" + 2" = 8.0 ft) = 88.0 LF (1/A-210 12'-8" N-S)
USG drywall suspension main tee DGLW26 | LF | 194.16 | 0.15 | 29.124 | 223.284 | main tee 12 ft (manufacturer length) | 19 | N/SHEET: 4/A-121, 1/A-121 ¦ USG drywall suspension grid: main tee ROUNDUP(14.773/4.0)+1 = 5 x 38.833 = 194.16; cross tee ROUNDUP(38.833/1.333)+1 = 31 x 14.773 = 457.96; channel + angle molding 107.21 each
USG drywall suspension cross tee DGLW424 | LF | 457.96 | 0.15 | 68.694 | 526.654 | cross tee 4 ft (manufacturer length) | 132 | N/SHEET: 4/A-121, 1/A-121 ¦ USG drywall suspension grid: main tee ROUNDUP(14.773/4.0)+1 = 5 x 38.833 = 194.16; cross tee ROUNDUP(38.833/1.333)+1 = 31 x 14.773 = 457.96; channel + angle molding 107.21 each
USG channel molding DGCM27 | LF | 107.21 | 0.15 | 16.0815 | 123.2915 | molding 12 ft (manufacturer length) | 11 | N/SHEET: 4/A-121, 1/A-121 ¦ USG drywall suspension grid: main tee ROUNDUP(14.773/4.0)+1 = 5 x 38.833 = 194.16; cross tee ROUNDUP(38.833/1.333)+1 = 31 x 14.773 = 457.96; channel + angle molding 107.21 each
USG angle molding DGWM24 | LF | 107.21 | 0.15 | 16.0815 | 123.2915 | molding 12 ft (manufacturer length) | 11 | N/SHEET: 4/A-121, 1/A-121 ¦ USG drywall suspension grid: main tee ROUNDUP(14.773/4.0)+1 = 5 x 38.833 = 194.16; cross tee ROUNDUP(38.833/1.333)+1 = 31 x 14.773 = 457.96; channel + angle molding 107.21 each
Clip angle 16 ga (5/A-410 bracing clips + 7/A-210 nested header clips) | PCS | 2522 | 0.15 | 378.3 | 2900.3 | piece | 2901 | N/SHEET: 5/A-410, 7/A-210 ¦ Breakdown [DERIVED]: CLIP-ANGLES-5-A410 2,518 + CLIP-ANGLES-7-A210 4 = 2,522 PCS ¦ 2" x 2" 16 GA. CLIP ANGLE at each stud per bracing row, (4) TEK SCREWS (5/A-410): rows x studs = W2-01 6x38 + W2-02 6x5 + W2-03 6x72 + W2-04 6x44 + W2-05 6x11 + W2-06.1 6x7 + W2-06.2 6x3 + W2-06.3 6x5 + W2-06.4 6x3 + W2-06.5 6x10 + W2-07 6x7 + W2-08 6x11 + W2-09 6x11 + W5-01 6x6 + W3-01 1x4 + W3-02 1x10 + W3-05 1x4 + W3-03 1x10 + W3-06 1x4 + W3-04 1x4 + W4-28a 1x8 + W4-28b 1x3 + W4-28c 1x3 + W4-28d 1x3 + W4-28e 1x3 + W4-29a 1x5 + W4-29b 1x5 + W4-29c 1x5 + W4-29d 1x5 + W4-29e 1x5 + W4-29f 1x5 + W4-30a 1x5 + W4-30b 1x5 + W4-30c 1x5 + W4-30d 1x5 + W4-30e 1x5 + W4-30f 1x5 + W4-31a 1x8 + W4-31b 1x3 + W4-31c 1x3 + W4-31d 1x3 + W4-31e 1x3 + CW-01 1x12 + CW-02 1x12 + CW-03 1x12 + CW-04 1x12 + CW-05 1x12 + CW-06 1x12 + CW-07 1x12 + CW-08 1x12 + CW-09 1x12 + C-H1-N 6x24 + C-H1-W 6x11 + C-H2a 6x11 + C-H2b 6x3 + C-H3a 6x5 + C-H3b 6x6 + C-E2 6x23 + C-E1-S 6x19 + C-I-P.1 6x2 + C-E1-P.2 6x3 + C-E1-B 6x3 + C-F 6x4 + C-I 6x3 + SS-N 3x19 + SS-E 3x9 + SS-IN-N 3x16 + SS-IN-E 3x6 + SS-GG 4x6 = 2518 pcs; 3"x3"x16 GA. CLIP ANGLES at the nested header to jamb connection (7/A-210): 2 header ends x 2 (front / back) = 4 pcs (conservative; count not printed - RFI-51)
#8 pan head self-tapping screws, relief channel to structure (8/A-410) | PCS | 291 | 0.15 | 43.65 | 334.65 | piece | 335 | N/SHEET: 8/A-410 ¦ Breakdown [DERIVED]: PAN-HEAD-8-A410 291 = 291 PCS ¦ 8/A-410 "CONTINUOUS 20 GA. X 2" MIN DEEP RELIEF CHANNEL - ANCHOR TO STEEL PLATE WITH #8 PAN HEAD SELF TAPPING SCREWS AT 24" O.C. AND 6" FROM ENDS": sum(ROUNDUP(L / 2) + 1) over 32 runs to structure (479.85 LF) = 291 pcs; note 8.C X-EDNI = alternative in RFI-51)
#10-16 x 3/4" Tek screws, pan head, at 16 ga clip angles and nested header / column / beam (5/A-410; 7/A-210; 8/A-210; A-410 note 8.A) | PCS | 10668 | 0.15 | 1600.2 | 12268.2 | piece | 12269 | N/SHEET: 5/A-410, 7/A-210, 8/A-210, 1/A-210 ¦ Breakdown [DERIVED]: TEK-SCREWS-CLIPS 10,668 = 10,668 PCS ¦ 5/A-410 "2" x 2" 16 GA. CLIP ANGLE ... (4) TEK SCREWS": 2518 clips x 4 = 10072 + 7/A-210 "(4) #10-16 SCREWS": 4 clips x 4 = 16 + 7/A-210 "RUNNER TRACK ATTACHED TO HEADER SUING (2) TEK SCREWS AT 16" O.C" top and bottom runner: 2 runners x 2 x (ROUNDUP(12.667 / 1.333) + 1) = 44 + 8/A-210 "(8) #10-16 TEKS 16"O.C., TYP.": nested beam (ROUNDUP(12.667 / 1.333) + 1) x 8 = 88 + nested columns 6 x (ROUNDUP(10.5 / 1.333) + 1) x 8 = 432 + 7/A-210 head attachment "#10-16 TEK SCREWS (TYP.)": 2 clips x 8 = 16; total 10668 pcs. Header 12'-8" = 1/A-210 front dimension chain (152"). Size: 5/A-410 prints none; the clip is 16 ga, so A-410 note 8.A "18/16 GAUGE - #10 - 16 X 3/4" TEKS" applies (7/A-210 and 8/A-210 print #10-16)
16 ga wire at seismic brace points (5/A-121) | LF | 131.42 | 0.15 | 19.713 | 151.133 | continuous coil (LF) | 152 | N/SHEET: 5/A-121 ¦ Breakdown [DERIVED]: SEISMIC-VERTICAL-WIRE-5-A121 131.42 = 131.42 LF ¦ 5/A-121 "16 GA. WIRE 12'-0\" O.C. EACH WAY AND WITHIN 6'-0\" OF EACH WALL" vertical wire at each brace point: groups Women's 1 x drop 16.0; Men's 1 x drop 16.0; Cafe 11'-6" band 1 x drop 13.5; Cafe 9'-0" band 1 x drop 16.0; Cafe cloud 4 x drop 13.0; Grab & Go 1 x drop 17.917 -> sum(groups x drop) = 131.42 LF (conservative - RFI-38) the 1-5/8" x 16 ga metal joist framing @ 48" O.C. on 5/A-121 is the horizontal carrying member (no post drawn)
P.A.F. 3/16" x 3/8" at cross member ends (8/A-410) | PCS | 282 | 0.15 | 42.3 | 324.3 | piece | 325 | N/SHEET: 8/A-410 ¦ Breakdown [DERIVED]: PAF-CROSS-MEMBERS-8-A410 282 = 282 PCS ¦ 8/A-410 PARALLEL TO STRUCTURE "METAL STUD PER SCHEDULE W/ (1) 3/16" 3/8" P.A.F. AT EACH END": 141 cross members x 2 = 282 pcs (RFI-41)
5/8" cement board (tile base) | SF | 50.04 | 0.06 | 3.0024 | 53.0424 | 4x12 ft sheet (Inputs) | 2 | N/SHEET: 22/A-201 ¦ Breakdown [DERIVED]: RESTROOM-BASE-CEMENT 50.04 = 50.04 SF ¦ 5/8" CEMENT BOARD BASE 1'-2" (22/A-201; A-001A Div 09 J.2): W2-05 7.51 + W2-06.1 6.92 + W2-06.2 2.23 + W2-06.3 2.41 + W2-06.3 2.46 + W2-06.4 2.23 + W2-06.5 6.88 + W2-07 7.51 + W5-01 5.7 + W5-01 5.7 = 49.55 LF - doors 8, 9 (6.66) = 42.89 LF x 1'-2" = 50.04 SF
Plywood screws #10-24 x 1-1/4" Teks/3 (A-410 note 8.D) | PCS | 2331 | 0.15 | 349.65 | 2680.65 | piece | 2681 | N/SHEET: A-410 ¦ Breakdown [DERIVED]: PLYWOOD-SCREWS-8D 2,331 = 2,331 PCS ¦ A-410 Partition Notes 8.D "#10-24 X 1-1/4\" TEKS/3 ... 24\" O.C. FIELD, 12\" O.C. PERIMETER": 4x8 sheet on studs @ 16" = 24 perimeter + 10 field = 34 screws / 32 SF; 2192.98 SF FRT plywood x 34/32 = 2331 pcs
Cement board screws 1-1/4" (manufacturer spacing) | PCS | 1686 | 0.15 | 252.9 | 1938.9 | piece | 1939 | N/SHEET: E/A-221, A/A-221, B/A-221, C/A-221, D/A-221, 22/A-201 ¦ Breakdown [DERIVED]: CEMENT-BOARD-SCREWS 1,686 = 1,686 PCS ¦ cement board screws @ 8" O.C. on studs @ 16" (manufacturer standard, spacing not printed - RFI-51): 3x5 board = 4 studs x 8 = 32 screws / 15 SF; 789.94 SF x 32/15 = 1686 pcs
Nested inner runner at the deflection head (3/A-410) | LF | 479.85 | 0.15 | 71.9775 | 551.8275 | run 10 ft | 56 | N/SHEET: 3/A-410 ¦ Breakdown [DERIVED]: NESTED-RUNNER-3-A410 479.85 = 479.85 LF ¦ 3/A-410 "METAL RUNNER AT STUDS - SECURE GWB TO METAL RUNNER" + "DO NOT SECURE METAL STUDS OR GWB TO DEEP LEG TRACK": inner runner = length of every wall / soffit side to deck = W2-01 48.77 + W2-02 4.99 + W2-03 94.24 + W2-04 56.76 + W2-05 12.92 + W2-06.1 6.92 + W2-06.2 2.23 + W2-06.3 4.87 + W2-06.4 2.23 + W2-06.5 11.29 + W2-07 7.51 + W2-08 12.92 + W2-09 12.92 + W5-01 5.7 + C-H1-N 29.98 + C-H1-W 12.17 + C-H2a 12.17 + C-H2b 1.95 + C-H3a 4.08 + C-H3b 6.17 + C-E2 29.3 + C-E1-S 23.46 + C-I-P.1 1.0 + C-E1-P.2 2.11 + C-E1-B 2.31 + C-F 3.26 + C-I 2.31 + SS-N 22.77 + SS-E 10.12 + SS-IN-N 20.0 + SS-IN-E 6.25 + SS-GG 6.167 = 479.85 LF (RFI-40 confirms the reading)
METAL trim - corner bead, casing bead, shadow molding, gypsum edge trim | LF | 957.03 | 0.15 | 143.5545 | 1100.5845 | trim stick 10 ft | 111 | N/SHEET: 3/A-410, 4/A-410, 4/A-121 ¦ Breakdown [DERIVED]: CORNER-BEAD-SOFFITS 65.31 + Corner bead - type 3 partial height walls (top edges + free ends) 205.36 + Corner bead - type 4 partial height walls (top edges + free ends) 164.94 + Corner bead - corridor recess (drinking fountain alcove, W2-06) outside corners 19 + Corner bead - column surrounds C25 (9 ea) outside corners 288 + Corner bead - Cafe Seating GWB cloud bottom edge 107.21 + J-bead - Cafe Seating GWB cloud top of fascia 107.21 = 957.03 LF
1/2" cement board / cementitious backer | SF | 739.9 | 0.06 | 44.394 | 784.294 | 4x12 ft sheet (Inputs) | 17 | N/SHEET: E/A-221, A/A-221, B/A-221, D/A-221, C/A-221 ¦ Breakdown [DERIVED]: C-E1-S Cafe 103 475 + C-E1-P.2 Cafe 103 52.75 + C-E1-B Cafe 103 57.75 + C-A-1 Cafe 103 26.78 + C-A-1 Cafe 103 26.78 + C-A-2 Cafe 103 11.21 + C-A-2 Cafe 103 11.21 + C-A-3 Cafe 103 16.9 + C-A-3 Cafe 103 16.9 + C-B Cafe 103 8.58 + C-B Cafe 103 8.58 + C-D Cafe 103 5.14 + C-D Cafe 103 5.14 + C-C Cafe 103 8.58 + C-C Cafe 103 8.58 = 739.88 SF
Track 3-5/8" at soffits, fire stop at ceiling line and nested columns | LF | 281.09 | 0.15 | 42.1635 | 323.2535 | run 10 ft | 33 | N/SHEET: 3/A-410, 2/A-221, 8/A-210 ¦ Breakdown [DERIVED]: SS-N 45.54 + SS-E 20.24 + SS-IN-N 40 + SS-IN-E 12.5 + VEST-POSTS-TRACK 5 + FIRESTOP-W2-04 56.76 + FIRESTOP-W2-05 12.92 + FIRESTOP-W2-06.1 6.92 + FIRESTOP-W2-06.2 2.23 + FIRESTOP-W2-06.3 4.87 + FIRESTOP-W2-06.4 2.23 + FIRESTOP-W2-06.5 11.29 + FIRESTOP-W2-07 7.51 + FIRESTOP-W2-08 12.92 + FIRESTOP-W2-09 12.92 + FIRESTOP-C-H2a 12.17 + FIRESTOP-W2-03 13.12 + FIRESTOP-C-H2b 1.95 = 281.09 LF
Track 6" at soffits, fire stop at ceiling line and nested beam | LF | 144.06 | 0.15 | 21.609 | 165.669 | run 10 ft | 17 | N/SHEET: 3/A-410, 3/A-221, 8/A-210 ¦ Breakdown [DERIVED]: SS-GG 12.33 + VEST-BOX-BEAM-TRACK 25.33 + FIRESTOP-W5-01 5.7 + FIRESTOP-C-H1-N 29.98 + FIRESTOP-C-H1-W 12.17 + FIRESTOP-C-E2 29.3 + FIRESTOP-C-H3a 4.08 + FIRESTOP-C-H3b 6.17 + FIRESTOP-C-E1-S 19 = 144.06 LF
8" ledger track (4/A-210) | LF | 12.67 | 0.15 | 1.9005 | 14.5705 | run 10 ft | 2 | N/SHEET: 4/A-210 ¦ Breakdown [DERIVED]: VEST-LEDGER 12.67 = 12.67 LF
#8 screws at the top chord, cross members and track (8/A-410) | PCS | 775 | 0.15 | 116.25 | 891.25 | piece | 892 | N/SHEET: 8/A-410 ¦ Breakdown [DERIVED]: SCREWS-8-A410 775 = 775 PCS ¦ 8/A-410 PARALLEL TO STRUCTURE: "(2) #8 SCREW AT EACH STUD" 141 cross members x 2 = 282 + "ATTACH TO TRACK W/ #8 SCREWS AT 24" O.C." sum(ROUNDUP(L / 2) + 1) over the walls parallel to the joists = 141 + "ATTACH TO TOP CORD OF EXIST'G STRUCTURE #8 SCREWS" 141 cross members x 2 ends = 282; PERPENDICULAR TO STRUCTURE: "ATTACH TO TOP CORD OF EXIST'G STRUCTURE W/ #8 SCREWS" one per joist crossing, sum(ROUNDUP(L / 5.0) + 1) over 262.46 LF = 70 (joist spacing 5'-0" not printed, same assumption as the cross members - RFI-41); total 775 pcs
3-5/8" stud, framed soffit 2/A-221 (LF) | LF | 61.31 | 0.15 | 9.1965 | 70.5065 | stick 20 ft | 4 | N/SHEET: 2/A-221, 1/A-121 ¦ Breakdown [DERIVED]: Cafe 103 - 11'-0" GWB zone: framed_soffit: ROUNDUP(23.25/2)+1 = 13 joists x 4.716 = 61.31 LF 3-5/8" joists = 61.31 LF (framed soffit joists, 2/A-221)
Blocking 2X wood (not labeled FRT) | LF | 17 | 0.15 | 2.55 | 19.55 | 2x lumber 8 ft | 3 | N/SHEET: 7/A-413, 8A/A-413, 4/A-412, 6/A-412, 4/A-101, 2/A-500 ¦ Breakdown [DERIVED]: BLK-CASED-OPENING 17 = 17 LF
FRT plywood substrate (5/8 in.) | SF | 1790.51 | 0.06 | 107.4306 | 1897.9406 | 4x12 ft sheet (Inputs) | 40 | N/SHEET: G/A-221, H/A-221, E/A-221, F/A-221, I/A-221, 1/A-226A, 6/A-226A, 3/A-221, A-410 (ALL PLYWOOD NEEDS TO BE FRT) ¦ Breakdown [DERIVED]: C-H1-N-B-FRT 314.79 + C-H1-W-B-FRT 127.78 + C-H2a-A-FRT 127.78 + C-H2b-A-FRT 20.47 + C-H2b-B-FRT 20.47 + C-H3a-A-FRT 102 + C-H3b-A-FRT 49.36 + C-E2-A-FRT 307.65 + C-F-A-FRT 81.5 + C-I-P.1-A-FRT 15 + C-I-A-FRT 34.65 + SS-N-WD1-FRT 318.78 + SS-E-WD1-FRT 141.68 + SS-GG-FRT 110.49 + C-I-E1-A-FRT 9.04 + C-I-E2-A-FRT 9.04 = 1,790.48 SF (strip length x height)
FRT plywood substrate (3/4 in.) | SF | 402.46 | 0.06 | 24.1476 | 426.6076 | 4x12 ft sheet (Inputs) | 9 | N/SHEET: A/A-221, B/A-221, 4/A-226A, 21/A-201, 5/A-210, 4/A-210, 11/A-200, 2/E-103, A-410 (ALL PLYWOOD NEEDS TO BE FRT) ¦ Breakdown [DERIVED]: C-A-1-A-FRT 26.78 + C-A-2-A-FRT 11.21 + C-A-3-A-FRT 16.9 + C-B-A-FRT 8.58 + MENU-BOARD-FRT 60.6 + RESTROOM-BACKING-FRT 17.77 + VEST-POSTS-PLYWOOD 105 + VEST-PLYWOOD 106.62 + JANITOR-FRT-11-A200 17 + SERVER-ROOM-BACKBOARD 32 = 402.46 SF (strip length x height)
Hanger wire 12 ga - hanger count (one per hanger, height per room) | PCS | 109 | 0 | 0 | 109 |  | 109 | N/SHEET: 5/A-121, 1/A-121 ¦ Breakdown [DERIVED]: Women's Restroom 109 9 + Men's Restroom 108 9 + Cafe 103 - 11'-6" GWB band 18 + Cafe 103 - 9'-0" GWB band 12 + Cafe Seating Area 102 - GWB cloud 55 + Grab & Go 6 = 109 PCS (one per hanger)
Additional head track at openings over 4'-0" wide | LF | 10.67 | 0.15 | 1.6005 | 12.2705 | run 10 ft | 2 | N/SHEET: A-500 ¦ Door 11 (W2-03): (4.0 + 2 x 0.667) x 1 = 5.33; Door 3 (C-H2a): (4.0 + 2 x 0.667) x 1 = 5.33
Stud reinforcement at MEP penetrations | PCS | 0 | 0 | 0 | 0 | each | 0 | [RFI] N/SHEET: 6/A-410, 7/A-410 ¦ RFI: MEP sweep not registrable: the registration check of M-102 (page 48) vs A-101 (page 6) gave 20 / 14 matching wall segments (< 25 required); the HVAC sheet is not used for geometric crossings (registration rule). Ducts crossing the full-height type 2 / 5 / E walls must be counted from M-102 by the estimator. Delta: per duct crossing a stud wall: + MAX(1, ROUNDUP(duct width / 16")) stud reinforcement plates x stud rows (take-off default, not printed: 6/A-410 and 7/A-410 are pipe firestopping only); plus 1 duct sleeve each
Extra framing - ATM recess (only what a detail prints at the recess; the wall stays in its type) | LF | 0 | 0.15 | 0 | 0 | stick 20 ft | 0 | [DERIVED] N/SHEET: A-101 ¦ none: No ATM / equipment recess in the set (A-101, A-500, A-221 reviewed) (A-101)
2-1/2" CFMF @ 16" O.C. at coiling grille head (detail per plans) | LF | 0 | 0.15 | 0 | 0 | stick 20 ft | 0 | N/SHEET: A-000, A-101, A-410, A-500 ¦ none: no parapet infill, coiling grille or duct sleeve detail in the set (A-000 index; A-101, A-410, A-500)
Gypsum board jamb return at openings | SF | 0 | 0.06 | 0 | 0 | 4x12 ft sheet (Inputs) | 0 | [DERIVED] N/SHEET: 1/A-500 ¦ none: No opening with a gypsum board return: doors in hollow metal frames (1/A-500); cased opening 2/A-500 is wood jamb + B-1 trim; storefronts are Div 08 (1/A-500)
PVC trim - edge trim molding and inside corner molding at the FRP | LF | 0 | 0.06 | 0 | 0 | trim stick 10 ft | 0 | [DERIVED] N/SHEET: 4/A-226B, 12/A-200 ¦ none: FRP-1 (A-510): Cafe Work Room 104 FRP-1 full height to the 10'-0" ceiling (1-4/A-226B); Janitor 107 FRP-1 to 96" A.F.F. (A-131) / 8'-0" (9-12/A-200); Cafe 103 below countertop. Installer not defined (A-002) - not carried, RFI-13 with delta (1,030.64 SF) - PVC trim with it.
Power-driven fasteners and duct sleeves | PCS | 0 | 0 | 0 | 0 | each | 0 | [DERIVED] N/SHEET: A-000, A-101, A-410, A-500 ¦ none: no parapet infill, coiling grille or duct sleeve detail in the set (A-000 index; A-101, A-410, A-500)
Access panel | PCS | 0 | 0 | 0 | 0 | each | 0 | [DERIVED] N/SHEET: A-121 ¦ none: No access panel shown in GWB ceilings or walls (A-121 ceiling key notes 1-11, M-102 and P sheets reviewed) (A-121)
Drywall screws #7 x 1-1/4" Type S bugle head (board on 25/20 ga studs) | PCS | 6114.04 | 0 | 0 | 6114.04 | each | 6115 | [DERIVED] N/SHEET: A-410, A-001A ¦ Inputs!B20 (Drywall screws per SF of board = 1.2) x 5095.03 SF of board | 6114.036
Framing screws #8-18 x 1/2" pan head (25/20 ga studs) | PCS | 1940 | 0 | 0 | 1940 | each | 1940 | [DERIVED] N/SHEET: A-410 note 8.A ¦ Inputs!B21 (Framing screws per stud piece = 4) x 485 stud pieces ¦ Breakdown [DERIVED]: 4 x 485 stud pieces [partition walls (per-wall stud pieces) 673; CW-01 12; CW-02 12; CW-03 12; CW-04 12; CW-05 12; CW-06 12; CW-07 12; CW-08 12; CW-09 12; C-I-E1.6" 0; C-I-E2.6" 0 - 296 heavy-gauge pieces] = 1940 | 1940
Power-driven fasteners, slab pins for the bottom track | PCS | 777.43 | 0 | 0 | 777.43 | each | 778 | [DERIVED] N/SHEET: 9/A-410 ¦ 518.29 LF of interior bottom track on slab / Inputs!B22 (Power-driven pin spacing (ft) = 0.666667) | 777.4346
Expansion anchors Hilti 1/4" Kwik Bolt II, exterior bottom track @ 8" O.C. | PCS | 0 | 0 | 0 | 0 | each | 0 | [DERIVED] N/SHEET: 1/DM-101 ¦ none: no new exterior wall on slab - perimeter walls 1 / 1A / 1B / 1C are EXISTING (RFI-01; 1/DM-101, A-101) | 0
Joint compound, all purpose | LB | 1166.54 | 0 | 0 | 1166.54 | lb | 1167 | [DERIVED] N/SHEET: A-001A Div 09 A.8 ¦ Inputs!B23 (Joint compound (lb per SF) = 0.072) x 16201.9 SF of board | 1166.5368
Joint tape, paper | LF | 5994.7 | 0 | 0 | 5994.7 | LF | 5995 | [DERIVED] N/SHEET: A-001A Div 09 A.8 ¦ Inputs!B24 (Joint tape (LF per SF) = 0.37) x 16201.9 SF of board | 5994.703
Level 5 finish | SF | 0 | 0.06 | 0 | 0 | SF | 0 | [DERIVED] N/SHEET: A-510 ¦ none: No LEVEL 5 finish in A-510 room finish schedule / finish notes (paint finishes PT-1..PT-8 only) (A-510)
Deflection clips at non-load-bearing walls to structure | PCS | 0 | 0 | 0 | 0 | each | 0 | [DERIVED] N/SHEET: 3/A-410 ¦ none: Deflection by deep leg track / slotted deflection at the top of full height walls (3/A-410 Top Track Detail, 2/A-410 "SLOTTED DEFLECTION", A-410 partition note 7 "PROVIDE DEFLECTION TRACK AS REQUIRED"); no deflection clips called
Heavy-gauge framing screws #10-16 x 3/4" pan head (18/16/14 ga studs) | PCS | 1776 | 0 | 0 | 1776 | each | 1776 | [DERIVED] N/SHEET: A-410 ¦ 6 (3 per connection x 2 ends) x 296 stud pieces of the 18/16/14 ga walls (C-F 5 + C-H2a 16 + C-H2b 4 + W2-01 43 + W2-02 5 + W2-03 76 + W2-04 49 + W2-05 12 + W2-06.1 13 + W2-06.2 4 + W2-06.3 6 + W2-06.4 4 + W2-06.5 19 + W2-07 8 + W2-08 16 + W2-09 16 = 296) = 1776
Type S-12 drywall screws #6 x 1-1/4" (board on 18/16/14 ga studs) | PCS | 13328.22 | 0 | 0 | 13328.22 | each | 13329 | [DERIVED] N/SHEET: A-410 ¦ 1.2 x (11143.59 SF of board on the 18/16/14 ga walls (C-F, C-H2a, C-H2b, W2-01, W2-02, W2-03, W2-04, W2-05, W2-06.1, W2-06.2, W2-06.3, W2-06.4, W2-06.5, W2-07, W2-08, W2-09) - 36.74 SF cement board base on those walls (22/A-201) = 11106.85 SF) = 13328.22

## Pending Items
RFI | Question / condition | Delta of each alternative
RFI-ACC-slab-pins | slab pins: pin spacing: carried one pin every 8.0" (A-410 note 8.F X-DNI 2 rows @ 16" O.C. (printed, conservative); 9/A-410 0.177" PAF @ 24" = alternative); alternatives: one row @ 16" / one row @ 24" | 16in: -388.72 pcs; 24in: -518.29 pcs
RFI-ACC-stud-reinforcement-mep | stud reinforcement MEP: MEP sweep not registrable: the registration check of M-102 (page 48) vs A-101 (page 6) gave 20 / 14 matching wall segments (< 25 required); the HVAC sheet is not used for geometric crossings (registration rule). Ducts crossing the full-height type 2 / 5 / E walls must be counted from M-102 by the estimator. | per duct crossing a stud wall: + MAX(1, ROUNDUP(duct width / 16")) stud reinforcement plates x stud rows (take-off default, not printed: 6/A-410 and 7/A-410 are pipe firestopping only); plus 1 duct sleeve each
RFI-01 | CLOSED - estimator decision 2026-10-24 (rev1): perimeter walls types 1 / 1A / 1B / 1C are EXISTING (1/DM-101 legend solid = to remain + key note 3 "EXTERIOR WALL PATCH AND REPAIR AS REQUIRED TO MAINTAIN EXISTING FIRE RATING"; A-101 Construction Legend "EXISTING EXTERIOR WALL" / "EXISTING PARTITION"; A-002 "PERIMETER STUDS, INSULATION, VAPOR BARRIER F/I BY LL"). Perimeter framing (studs, track, bracing, 1B sheathing) EXCLUDED. Interior face patch & repair (1/DM-101 key note 3, A-101 C5) = ALLOWANCE, amount: $ ________ (blank, estimator to fill). rev2 (estimator decision 2026-10-25): break room kitchenette W.R. on existing EXT-07 (6/A-412, 7/A-412) is INSIDE this patch & repair allowance; allowance amount stays BLANK (decided).(rev7): A-410 types 1, 1A, 1B, 1C label the interior board "5/8" GYP BD BY FUTURE TENANT": EXCLUDED with that citation, consistent with this decision. A-413 7/8A general note "IF SHELVING IS TO BE INSTALLED ON EXISTING WALL, G.C. IS TO REMOVE AND REPLACE GYP. BOARD AS REQUIRED FOR INSTALLATION OF WOOD BLOCKING": inside this patch & repair allowance. | Applied: - 417.43 LF of perimeter walls (17 walls); 3-5/8" stud 16,812.96 -> 10,120.39 LF; 8" stud 2,332.99 -> 0; 1/2" exterior sheathing 2,469.22 -> 0 SF; bottom / top track 1,051.87 -> 634.44 LF each; bracing 5,230.74 -> 2,827.81 LF. Allowance: blank.; board by future tenant on the existing perimeter (A-410 types 1 / 1A / 1B / 1C): upper bound 417.43 LF x 25.0 = 10,436 SF 5/8" Type X if it were ever in our scope.
RFI-02 | N/A after RFI-01 (perimeter walls existing, rev1): the north 1A / 1 boundary no longer affects the take-off (both types are existing, excluded). | none
RFI-03 | B.O. deck is V.I.F. and sloped: 24'-0" (2/A-400B) to 25'-7" (2/A-400A); walls to deck loaded at 25'-0" (1/A-400A, 1/A-400B), east facade 25'-7", west 24'-0".(rev7): the elevations also print 21'-9" V.I.F. at the right end of 2/A-400A and 23'-8" V.I.F. on A-400B (joists sloping): the B.O. deck range is wider than 24'-0" to 25'-7". | Each 1 ft of deck height = 414.54 LF of studs-to-deck walls x 1 ft (studs, board where to deck, bracing rows)
RFI-04 | CLOSED - Review Item rev3 (estimator decision 2026-10-26): type 2 > 22 ft: 3-5/8" 14 ga SJ + diagonal braces @ 32" O.C. to structure (3/A-410 Top Track Detail "PROVIDE DIAGONAL BRACING AT 32" O.C. TO STRUCTURE ABOVE (TYP.)"); brace member / length not printed - estimator choice 3-5/8" 20 ga stud x 4 ft at 45 deg.(rev7): same precedent applied to the Cafe 3-5/8" walls to deck (C-H2a, C-H2b, C-F): 14 ga SJ + 11 diagonal braces = 44.0 LF. | Applied: 117 braces x 4.0 ft = 468.0 LF (type 2) + 44.0 LF (Cafe) 3-5/8" 20 ga stud (member and length = estimator choice). Citation history: rev0-rev2 cited the partition type 3 section, rev3-rev6 cited 8/A-410 (that bubble is the Typ. Connection Detail); the Top Track Detail is bubble 3/A-410.
RFI-05 | Cafe south line: type 1 on A-101 and E1 / E2 (6" studs, void at existing wall) on 1/A-221. Counted ONCE as E1 / E2. E2 / E1 change point not drawn. | If both furring and 6" wall exist: + 50.24 LF type 1 furring (3-5/8") x 25'-0". E2 / E1 split at the H2a faces: 0.20 LF moves.
RFI-06 | CLOSED - Review Item rev3 (estimator decision 2026-10-26): Cafe walls H1, H2a, H2b, H3a, H3b, F studs TO DECK 25'-0" (1/A-400B draws the Cafe walls floor to B.O. DECK; A-226A elevations break at the top; no section prints a stud top). Board per face = ceiling + 6" (A-410 partition note 3): Workroom ACT-1 10'-0" -> 10'-6"; Grab & Go GWB 7'-1" -> 7'-7"; Cafe open-to-deck strip at H2a (1/A-121 PT-6 OPEN TO DECK) -> to deck. | Applied (faces already at these heights in rev2; RCP evidence on 1/A-121).
RFI-07 | N/A after RFI-01 (perimeter walls existing, rev1): exterior furring 3-5/8" over 22'-0" (types 1, 1A, 1C) is existing, excluded. | none
RFI-08 | CLOSED - Review Item rev3 (estimator decision 2026-10-26): type I WD-1 top = 15'-0" A.F.F. (6/A-226A; elevation bubble on 1/A-221 looks west at the type I face, verified). | Applied (rev3 + rev5): type I 5/8" FRT plywood floor to 15'-0" (6/A-226A) = (C-I 2.31 + C-I-P.1 1.00 + end faces C-I-E1 / C-I-E2 1.21) 4.52 LF x 15.0 = 67.74 SF; GWB 15'-0" to deck 4.52 x 10.0 = 45.16 SF.
RFI-09 | Door headers: no header schedule in the set and 1/A-500 shows no header; headers carried 0 LF. | If a 2-piece track header is required at every door: + 83.32 LF ((R.O. + 1'-4") x 2)
RFI-10 | N/A after RFI-01 (perimeter walls existing, rev1): doors 10, 12, 13 are existing doors in existing perimeter walls (A-500 EXISTING V.I.F.); no framing in our scope. | none
RFI-11 | CLOSED - estimator decision RFI-11 (rev1) + W.R. gypsum board on all faces of Women's 109, Men's 108, Janitor 107 and the drinking fountain alcove (A-410 Partition Notes 2 "PROVIDE WATER RESISTANT GYPSUM BOARD IN ALL BATHROOMS AND JANITOR'S CLOSET FOR WALL AND CEILING CONSTRUCTION", note 7, "*" note, 2/A-410, 5/A-410; A-001A Div 09 A.4) and on the restroom GWB ceilings (same note 2; 1/A-121 GWB 9'-0"). Cafe Work Room 104: NO W.R. - G/A-221 draws only 5/8" FRT plywood on the Work Room side (FRP-1 finish, A-510); there is no gypsum board on that face (rev6 removes the 570.36 SF GWB faces). | Applied (rev7): 5/8" Type X W.R. = 1,092.59 SF = walls (Women's 222.93 + Men's 223.02 + Janitor 485.75 + alcove corridor 88.63) + restroom ceilings 122.30 - 1'-2" cement board base 50.04 (22/A-201).
RFI-12 | CLOSED (base) / OPEN (installer of tile)(rev7): 22/A-201 Tile Base Detail prints "5/8" CEMENT BOARD" with "1'-2" CEMENT BOARD BASE" and 5/8" W.R. GYP. BD. above (A-001A Div 09 J.2). Corridor 110 wall tile (A-510) backer: not detailed. | Applied: + 50.04 SF cement board base on the restroom faces of new walls and the same SF out of W.R. Open: Corridor 110 wall tile backer - each 1 ft of tile height = 93.44 SF cement board instead of Type X.
RFI-13 | FRP-1 (A-510): Cafe Work Room 104 FRP-1 full height to the 10'-0" ceiling (1-4/A-226B); Janitor 107 FRP-1 to 96" A.F.F. (A-131) / 8'-0" (9-12/A-200). Who furnishes / installs the FRP is not defined (A-002). Substrate: E/A-221 and G/A-221 call 5/8" FRT plywood on the Work Room faces; 3/A-225 draws a dotted (board) fill - conflict. Not carried(rev7): heights corrected. | If FRP is in our scope: Cafe Work Room 87.52 LF x 10.0 = 875.20 SF + Janitor 19.43 LF x 8.0 = 155.44 SF = 1,030.64 SF FRP-1 gross (doors not deducted) + PVC trim (J-mold, inside corners).
RFI-14 | CLOSED - estimator answer (rev4): Cafe soffit bottom = 11'-0" (A-121 RCP governs over 1/A-226A 9'-0"); north face sign band WD-1 top = 15'-0" (same as east face, 6/A-226A). Both faces: WD-1 11'-0" to 15'-0" with 5/8" FRT plywood behind; GWB above to deck and at the soffit bottom (2/A-221). | Applied: SS-N FRT 22.77 x 4.0 = 91.08 SF (rev3 45.54 at 9'-0"/11'-0"); SS-N GWB 14 -> 10 ft; SS-E unchanged (FRT 40.48 SF, GWB 10 ft).
RFI-15 | CLOSED - Review Item rev3 (estimator decision 2026-10-26): Cafe Seating cloud = USG drywall suspension grid as drawn on 4/A-121 (DGLW26 main tee, DGLW424 cross tee, DGCM27 channel molding, DGWM24 angle molding); carrying channel direction E-W confirmed (joists N-S: 1/A-400A joists cut in section, 2/A-400A joists in profile). | Applied: main tee 194.16 LF (5 x 38.833, @ 48" USG standard), cross tee 457.96 LF (31 x 14.773 = 124 pcs, @ 16" USG standard; 24" alt. = 22 rows / 88 pcs), DGCM27 107.21 LF, DGWM24 107.21 LF; removed from the cloud: furring -310.23 LF, carrying -194.17 LF, ceiling track -107.21 LF.
RFI-16 | CLOSED - estimator answer (rev4): vestibule post sheathing = 3/4" FRT plywood, 4 faces, full height (5/A-210 "5/8 GYP. BOARD SHEATHING AS REQUIRED" -> estimator: plywood). | Applied: 6 posts x 4 faces x 5" x 10.5 ft = 105.0 SF 3/4" FRT plywood (6 posts per 1/A-210).
RFI-17 | CLOSED - estimator answer (rev4): column surrounds C25 stud spacing = 16" O.C. (as carried); count 9. | none (as carried)
RFI-18 | CLOSED - Review Item rev3 (estimator decision 2026-10-26): type 4 curved walls = face-average arc 25.68 LF each (estimator choice vs printed 25'-1"). | Applied: + 1.17 LF type 4 (83.64 LF).
RFI-19 | CLOSED - Review Item rev3 (estimator decision 2026-10-26): board height where a ceiling exists = ceiling + 6" (2/A-410, A-410 partition note 3). Kept. | none
RFI-20 | CLOSED - audit rev4 row 6 (rev5): Grab & Go header soffit QUANTIFIED from the plan: 6'-2" HOLD (1/A-221) x (B.O. deck 25'-0" - Grab & Go GWB 7'-1", 1/A-121) with 6" metal studs @ 16" O.C. (3/A-221); 5/8" FRT plywood substrate on the east face, GWB at the soffit bottom. T.O. WD-1 not printed -> RFI-34. | Applied: SS-GG 6" studs 6 x 17.917 = 107.5 LF; ceiling / soffit track 6.167 x 2 = 12.33 LF; bracing 4 rows x 6.167 = 24.67 LF (5/A-410); 5/8" FRT plywood 6.167 x 17.917 = 110.49 SF; bottom GWB 3.73 SF.
RFI-21 | Cafe Seating GWB cloud edge: 6" fascia (4/A-121, measured on the detail, not dimensioned) and edge molding DGCM27. | 107.21 LF edge x 0.5 ft = 53.6 SF GWB + 107.21 LF edge trim
RFI-22 | Types 3 and 4: "F.R.P. over 5/8" plywood where shelving occurs" (3/A-410, 4/A-410) - fixture plan A-111 does not define the extent on the partial walls. | 5/8" plywood + FRP on 122.32 LF x height per face where shelving occurs
RFI-23 | CLOSED - estimator decision 2026-10-24 (rev1): FRT blocking taken off with the counts and rows per detail: stock room shelving 7/A-413 (3 rows), receiving table 8A/A-413 (4 rows), Manager's Office 3, 4/A-412 (4 rows), break room cabinets 6/A-412 (2 rows); restroom backing 21, 26/A-201 (10 pcs 3/4" FRT plywood); Cafe menu boards 4/A-226A continuous 3/4" FRT plywood 31" high x C-E1-S. | Applied: FRT blocking 568.27 LF FRT + 2X wood 17.00 LF (2/A-500) (387.0 + 69.0 + 85.6 + 10.67 + FE cabinets 16.0, rev7); 3/4" FRT plywood + 60.61 SF menu boards (23.46 x 31/12) + 17.78 SF restroom backing (10 pcs x 16" bay x 16" high, rev2 (estimator decision 2026-10-25): 13.33 x 16/12). rev5: water heater backing (P-201) carried conservatively -> RFI-32; janitor 3/4" FRT plywood area (11/A-200) carried 17.0 SF -> RFI-33; W-3 surface blocking (1/A-414, 7/A-414) -> RFI-36.
RFI-24 | Gypsum board control joints: none labeled or detailed on A-410, A-121, A-221 or A-510 ("CJ" only in the M-100 legend). ASTM C840 limits uninterrupted wall runs to 30 ft; type 2 walls W2-01 (48.77 LF), W2-03 (94.24 LF), W2-04 (56.76 LF) exceed it. Not carried - confirm. | Type 2: floor(L / 30) = 1 + 3 + 1 = 5 joints x 25.0 ft x 2 faces = + 250.0 LF control joint; if RFI-01 brings exterior gyp bd into scope: EXT-02 5 x 25.0 + EXT-03 2 x 24.0 + EXT-07 1 x 25.0 = + 198.0 LF (one face)
RFI-25 | Merged into RFI-01 allowance (rev1): demising / perimeter wall patch & repair (A-101 C5, 1/DM-101 key note 3) = ALLOWANCE, amount blank. | Allowance: $ ________ (blank)
RFI-26 | N/A after RFI-01 (perimeter walls existing, rev1): type 1B (and its 1/2" exterior gyp sheathing) is existing, excluded. | none
RFI-27 | CLOSED - estimator decision 2026-10-24 (rev1): all 5/8" gyp bd on new walls AND GWB ceilings = Type X (A-001A Div 09 A.2; 4/A-121, 5/A-121 - rev2 (estimator decision 2026-10-25): ceilings to Type X); W.R. faces = 5/8" Type X W.R. No 5/8" regular remains. | Applied (rev7): 5/8" Type X 15,109.29 SF = walls 14,100.86 + GWB ceilings 884.24 (Cafe 103 - 11'-6" GWB band 125.07, Cafe 103 - 9'-0" GWB band 50.67, Cafe Seating Area 102 - GWB cloud 573.69, Cafe 103 - 11'-0" GWB zone 109.65, Grab & Go 25.16) + VEST-GWB 105.5 + SS-GG-BOTTOM-GWB 3.73 + VEST-GWB-BANDS 14.96; Type X W.R. 1,092.59 SF; 5/8" regular 0.
RFI-28 | Types 3 and 4 base anchorage: 3/A-410, 4/A-410 and A/A-410 draw a moment clip at the stud base with Hilti Kwik HUS-EZ anchors; spacing not printed separately. Not carried (expansion anchors 0); their bottom track is not on slab pins (3/A-410, 4/A-410 "3 5/8" X 20GA TRACK W/ (2)-1/4"ø X 1 5/8" HILTI KWIK HUSEZ CONCRETE SCREW AND MOMENT CLIP - SEE DETAIL"). | If one clip per stud: + 162 moment clips (type 3 = 40 studs, type 4 = 122 studs, per-wall stud count) + 324 Kwik HUS-EZ 1/4" x 1-5/8" (2 per clip) + 324 #10-16 screws (A/A-410 "(1) #10-16 SCREW @ EACH FLANGE": 162 clips x 2). Slab pins already exclude the 122.32 LF of type 3 / 4 track.
RFI-29 | Corner guards: A-101 key note C22 "STAINLESS STEEL CORNER GUARDS AT 48" A.F.F. FOR ALL OUTSIDE GYPSUM BOARD CORNERS AT STOCKROOM WALLS" vs A-001A "METAL CORNER GUARDS (2"X2"X72") AT ALL OUTSIDE CORNERS". Extent and installer (drywall vs Div 10) not defined. Not carried. | C22: stock room outside corners only, about 4 to 6 corners x 4 ft; spec: every outside corner x 6 ft including 36 column surround corners (9 x 4)
RFI-30 | Access panels: M-100 general note 30 and E general note 12 "THE GENERAL CONTRACTOR SHALL INSTALL ACCESS PANELS"; A-002 F/I tenant contractor; quantity not shown on any sheet. Not carried. | Install only: allowance of 4 to 6 panels in the GWB ceilings (restrooms, Cafe bands / soffit, vestibule)
RFI-31 | Additional head track at openings: the note "ADD FULL LENGTH ADDL HEAD TRACK @ OPNG > 4'-0"" quoted in rev0-rev4 is NOT on A-410 / A-500 (take-off criterion (not printed); citation corrected, audit rev4 row 8 (rev5)). Carried conservatively at the two 4'-0" doors: door 3 (C-H2a, 4'-0" x 8'-0") and door 11 (W2-03, 4'-0" x 7'-0"), A-500 door schedule. | Carried 10.67 LF = 2 x (R.O. 4.00 ft measured jamb gap + 2 x 8" bearing); if not required: - 10.67 LF. Auditor 11.17 LF assumed R.O. 4'-3" (frame not printed): + 0.50 LF if the R.O. is 4'-3".
RFI-32 | P-201 WATER HEATER DETAIL ("FOR RESTROOMS AND BREAKROOM"): 2x4 metal stud backing + steel blocking between studs at the anchor locations; member sizes and lengths not printed (Janitor 107, 11/A-200). audit rev4 row 5 (rev5): carried conservatively. | Carried: 3-5/8" stud backing 2 x 4.0 ft = 8.0 LF + steel blocking 2 rows x 1.33 ft = 2.67 LF (3-5/8" stud pieces); if by the plumber: - 10.67 LF 3-5/8" stud.
RFI-33 | 11/A-200 Janitor 107: "AREA OF 3/4" FIRE RESISTANT PLYWOOD BLOCKING (TYP)" - extent not dimensioned. audit rev4 row 4 (rev5): carried at the conservative upper bound (width measured on 11/A-200 x 8'-0" HOLD). | Carried 2.125 x 8.0 = 17.0 SF 3/4" FRT plywood; confirm extent (delta down to 0 SF).
RFI-34 | CLOSED(rev7): T.O. WD-1 at the Grab & Go header = 15'-0" (5/A-226A 11'-0" + 4'-0" WD-1; 6/A-226A 15'-0"). 3/A-221: 5/8" FRT plywood full face, 5/8" GWB over it above T.O. WD-1. | Applied: + 6.167 x 10.0 = 61.67 SF 5/8" Type X (15'-0" to deck); FRT plywood unchanged (110.49 SF).
RFI-35 | 3/A-410 Top Track Detail "METAL STUD/TRACK FIRE STOP AT CEILING LINE, TYP." (rev5-rev6 cited 8/A-410, which is the Typ. Connection Detail: applied to every full-height wall with a ceiling on at least one face (1/A-121); carried; confirm with the GC. | Carried per wall (Material Summary breakdown) = 264.21 LF; if not required: minus that LF.
RFI-36 | Surface-mounted 3/4" FRT plywood blocking at the W-3 wall fixtures "BY GC/FIXTURE INSTALLER" (1/A-414, 7/A-414): who furnishes / installs is ambiguous and the W-3 count on A-111 is not taken. Not carried - audit rev4 row 11 (rev5). | If by the drywall contractor: + one 3/4" FRT plywood strip per W-3 unit (size per 1/A-414, 7/A-414) x W-3 count from A-111 - PENDING count.
RFI-37 | CLOSED - resolved from the plan (rev6): the Sales / Cafe faces of C-H1-N and C-H2a are 5/8" gypsum board only. G/A-221 draws one layer on the Sales Floor side ("5/8" GYPSUM BOARD"); C-H1-N Sales face = Sales Area 101 PAINTED GYP. BD. (A-510); C-H2a Cafe face = PT-3 painted wall around door 3 (1/A-225 finish plan, 5/A-226A Cafe Service Line Elevation); the narrow WD-1 left of the door is the type I return C-I-P.1 (already carried). images 12-14. | Applied: - 951.75 SF 5/8" FRT plywood (C-H1-N A 25.90 x 25.0 = 647.50 + C-H2a B 12.17 x 25.0 = 304.25), carried since rev0; GWB on those faces unchanged.
RFI-38 | Ceiling seismic bracing: A-121 Ceiling Notes 1 "SEE A-420 DRAWINGS REGARDING CEILING BRACING" - A-420 is not in the set; 5/A-121 draws splay wires and a 16 ga wire @ 12'-0" O.C. each way at each brace point (the 1-5/8" x 16 ga metal joist framing @ 48" is the horizontal carrying member); A-002 Div 10 "SEISMIC BRACING" F/I by the tenant contractor. Carried conservatively on the GWB suspended ceilings. | Carried: splay wires 743.29 LF (hanger wire row) + vertical 16 ga wire at each brace point 131.42 LF (16 ga wire row); the 1-5/8" x 16 ga metal joist framing @ 48" on 5/A-121 is the horizontal carrying member (no post). If not required: minus both.
RFI-39 | Recessed fire extinguisher cabinets (A-101 C11, A-111 KN 9, 4/A-101 "F.R.T. WOOD STUD HEADER ABOVE AND BASE BELOW CABINET"): 4 in new walls (W2-01, W2-03 x 2, Cafe Workroom); cabinet width / rough opening not printed (Cosmopolitan fully recessed, Ambassador 1017F10). | Carried 16.0 LF FRT 2x (4 x (2.0 + 2.0 ft)); each +1 ft of cabinet width = +8.0 LF FRT; jamb studs inside the field studs.
RFI-40 | 3/A-410 Top Track Detail: "METAL RUNNER AT STUDS - SECURE GWB TO METAL RUNNER" with "DO NOT SECURE METAL STUDS OR GWB TO DEEP LEG TRACK" read as a nested inner runner at every deflection head. Carried; confirm. | Carried 479.85 LF nested inner runner; if a single deep leg track is accepted: minus that LF.
RFI-41 | 8/A-410 Typ. Connection Detail (PARALLEL TO STRUCTURE): full-height walls parallel to the joists (N-S) hang from metal studs spanning joist to joist; joist spacing not printed (A-400A / A-400B). | Carried 705.0 LF (members @ 24" O.C. along the wall x 5.0 ft assumed joist spacing); each 1 ft of joist spacing = 141.0 LF. #8 screws (8/A-410) carried in their own row (775 pcs) with joists at 5'-0": one screw per joist crossing on the walls perpendicular to the joists = 70; at 4'-0" spacing: + 15 pcs.
RFI-42 | 2/A-221 framed soffit drop "CROSS BRACING AS REQ'D": member / spacing not printed. | Carried 90.0 LF 3-5/8" stud (pairs @ 4'-0" x 5.0 ft); if not required: minus that LF.
RFI-43 | E/A-221 type E1 (Cafe south wall C-E1-S, C-E1-P.2, C-E1-B): 1/2" cement board height not printed; carried to deck 25'-0" (studs to deck). The Cafe 9'-0" GWB band runs along C-E1-S (1/A-121). | If the cement board stops at 9'-0" + 6" (A-410 Partition Notes 3): C-E1-S 19.0 x 15.5 = - 294.5 SF, C-E1-P.2 2.11 x 15.5 = - 32.7 SF, C-E1-B 2.31 x 15.5 = - 35.8 SF.
RFI-44 | H/A-221 "H3a = PLYWOOD TO TOP OF WD-1": T.O. WD-1 on the H3a Sales face not printed (A-225, A-226A). Carried: FRT plywood to deck (25'-0"), no GWB. | If T.O. WD-1 = 15'-0" as on the Grab & Go header (6/A-226A): FRT plywood - 40.8 SF (4.08 x 10.0) and 5/8" Type X + 40.8 SF.
RFI-45 | 1/A-221 Workroom door pier (1'-0" x 2'-8" HOLD) against H2a with an internal void: the C-H2a Cafe face may be concealed along the pier. | If concealed: - 2.67 x 25.0 = - 66.7 SF 5/8" Type X on C-H2a (pier faces carried as C-E1-P.2 / C-I-P.1).
RFI-46 | F/A-221 "3 5/8" METAL STUDS @ 16" O.C. TO BOTTOM OF NESTED STUD BRACING": the nested stud bracing member is not drawn; studs carried to deck (estimator decision RI 7).(rev8): the same phrase is printed on the partition types 3 and 4 (3/A-410, 4/A-410): nested stud at the top of each wall. | Carried 6.52 LF (F) + 122.32 LF (types 3 / 4) 3-5/8" stud; define member / elevation; if not required: minus both.
RFI-47 | Plywood material / thickness conflicts on A-225: 5/A-225 die wall "3/4" THICK MARINE GRADE PLYWOOD" vs A/A-221, B/A-221 "3/4" FRT PLYWOOD SUBSTRATE" and A-410 "ALL PLYWOOD NEEDS TO BE FRT"; 10/A-225 "1/2" F.R.T. PLYWOOD SUBSTRATE" vs I/A-221, G/A-221, H/A-221 5/8" FRT plywood. Carried as FRT, thickness per the A-221 sections. | Same SF; material / thickness change only: die wall 63.47 SF marine vs FRT; type I end faces 18.08 SF 1/2" instead of 5/8".
RFI-48 | Stock room shelving blocking: 7/A-413 "FRT WOOD BLOCKING IN PARTITION" vs 7A/A-413 "SURFACE MOUNT WOOD BLOCKING" (no FRT). Carried in-partition FRT 2x, 3 rows (387 LF). | Quantity unchanged; if surface-mounted: material / installation method change only (not FRT, no board cut-outs).
RFI-49 | 2/A-500 Cased Opening Detail: "WOOD BLOCKING" across the stud return; the number / location of cased openings is not marked on A-101. | Carried 1 opening x 17.0 LF wood blocking (not labeled FRT); each additional opening + 17.0 LF.
RFI-50 | 2/E-103 Server Room: "4'x8' FRT PLYWOOD SHEET AND POWER BY GC - ALL OTHER WORK BY OTHERS" (E-301 "fire-rated plywood terminal board"). Carried in the drywall scope (FRT plywood substrate); confirm the trade. | Carried 32.0 SF 3/4" FRT plywood; if by the electrical contractor: - 32.0 SF.
RFI-52 | Vestibule GWB bands above B.O. ceiling 10'-6": top of the band 11'-3 1/2" V.I.F. (2/A-210, 3/A-210, "VESTIBULE ASSEMBLY TO MATCH EXISTING STOREFRONT SYSTEM V.I.F."). | Carried 14.96 SF; each 1" of band height = 1.89 SF (front 12.67 + sides 2 x 8.42 ft / 12).
RFI-53 | Light fixtures in the Cafe GWB bands (11'-6" and 9'-0", 1/A-121): fixture count in the bands not taken; 5/A-121 "PROVIDE ADDITIONAL WIRE SUPPORT AT ALL LIGHT FIXTURES".(rev8): E-301 Sec. 265119: "THIS CONTRACTOR SHALL PROVIDE AND INSTALL ALL NECESSARY SUPPORT MEDIA FOR ALL LIGHTING FIXTURES ... FIXTURES SHALL NOT BE SUPPORTED FROM ROOF DECK" - overlap with the 5/A-121 fixture wires carried. | Each fixture in a band = + 1 hanger x 13.5 / 16.0 ft wire. If the fixture supports are by the electrical contractor (E-301 265119): - 401.0 LF hanger wire (29 hangers).
RFI-51 | Fastener counts not printed: 7/A-210 3"x3"x16 ga clip angles (count per header end); cement board screw spacing (manufacturer standard 8" O.C. used); plywood screws per A-410 note 8.D (24" field / 12" perimeter on 4x8 sheets). | Carried: clip angles 7/A-210 4 pcs; cement board screws 1686 pcs; plywood screws 2331 pcs - adjust to the estimator yields. Framing screws count the stud pieces of the walls and column wraps (781) by gauge (A-410 note 8.A); the 8/A-410 #8 screws (top chord, cross members, track) have their own row; the other detail members (braces, bracing clips) are in the Tek screw row. 9/A-410 calls #8 screws stud to track while note 8.A calls #10-16 on 18/16 ga - carried per 8.A.(rev8): relief channel to structure carried with 8/A-410 #8 pan head screws (291 pcs) + P.A.F. at cross members (282 pcs); note 8.C X-EDNI (2 rows @ 16" = 720 pcs) is the alternative if the track bears directly on structural steel. Slab pins carried per note 8.F (2 rows @ 16" X-DNI); 9/A-410 alternative 0.177" PAF @ 24" = - 640.61 pcs. 8/A-210 "(8) #10-16 TEKS 16"O.C., TYP." read as 8 per station at 16" O.C. (520 pcs carried); if 8 per member in total: - 464 pcs. 7/A-210 head attachment clips: 2 assumed (16 screws), count not printed.
RFI-54 | Ceiling perimeter track at the suspended GWB ceilings (Women's 109, Men's 108, Cafe 103 bands 11'-6" and 9'-0", Grab & Go 7'-1"): 5/A-121 draws the perimeter attachment but prints no track size; the stud size of the wall it attaches to varies. | Carried 180.99 LF in its own row (size not printed). If the perimeter is the USG angle molding DGWM24 already carried: - 180.99 LF of track; if 3-5/8" track: no LF change (price only).

## Review Items
0 questions in total, asked ONE at a time in this order: floor plan (partition types A-Z), then the details the floor plan calls, in order
# | Phase | Type / order | Item | Sheet + detail | Image

## Scope Checklist
Scope ID | Scope | Status | Note (quantity, NOT APPLICABLE + sheet, or RFI)
ALC-01 | Interior partition framing (studs + tracks) | QUANTIFIED | Quantified (rev1): partition types 2, 5, 3, 4 (A-410) and Cafe types H1, H2a, H2b, H3a, H3b, E2, E1, F, I, A, B, D, C (A-221) on A-101 / A-221; 3-5/8" and 6" stud families in Material Summary. Perimeter types 1 / 1A / 1B / 1C EXISTING - EXCLUDED (RFI-01).
ALC-02 | Exterior wall framing (CFMF) | NOT APPLICABLE | NOT APPLICABLE (rev1, estimator decision RFI-01): perimeter walls types 1 / 1A / 1B / 1C are existing; their interior board is labeled "5/8" GYP BD BY FUTURE TENANT" on 1, 1A, 1B, 1C/A-410 - EXCLUDED with that citation.
ALC-03 | Parapet framing | NOT APPLICABLE | NOT APPLICABLE: no parapet framing in scope - partition schedule A-410 and sections A-400A, A-400B show no parapet type; M-301 (p50) mention is a mechanical roof-edge note
ALC-04 | Top / deflection and bottom track | QUANTIFIED | Bottom track and top / deflection track = partition LF per type (A-101, A-221; 2/A-410, 3/A-410); + fire stop track at ceiling line (own rows by size, 3/A-410) (3/A-410, RFI-35) and additional head track 10.67 LF (RFI-31); M-302 (p51) mention is plumbing expansion fittings; nested inner runner at deflection heads (3/A-410, RFI-40); 8/A-410 #8 pan head screws + P.A.F. + #8 screws (own rows); X-EDNI 8.C = alternative in RFI-51; cross members at walls parallel to joists (8/A-410 Typ. Connection, RFI-41).
ALC-05 | Headers, sills and jambs at openings | RFI | RFI-09 door headers: no header schedule in the set and 1/A-500 shows no header; jambs carried as studs; sill track not called (A-500 door schedule)
ALC-06 | Bracing / bridging | QUANTIFIED | Bracing C.R. channel @ 4'-0" O.C. per A-410 partition note 4 and 5/A-410 = 2,883.65 LF; diagonal bracing type 2 > 22'-0" per 3/A-410 Top Track Detail (RFI-04 CLOSED rev3: 117 braces = 468.0 LF) + 2" x 2" 16 ga clip angles at every stud per bracing row (5/A-410) and 2/A-221 soffit cross bracing (RFI-42).
ALC-07 | Gypsum board on walls (layers per type) | QUANTIFIED | Quantified (rev6): 5/8" Type X 15,109.29 SF + 5/8" Type X W.R. 1,092.59 SF (A-410, A-001A, RFI-27, RFI-11); no 5/8" regular. Perimeter walls existing (RFI-01).
ALC-08 | Moisture / abuse / special board at wet zones | QUANTIFIED | Quantified (rev6): 5/8" Type X W.R. 1,092.59 SF = all faces of Women's 109, Men's 108, Janitor 107 and drinking fountain alcove corridor faces (A-410 Partition Notes 2 and 7, '*' note, 2/A-410, 5/A-410) + restroom GWB ceilings 122.30 SF (A-410 Partition Notes 2); Cafe Work Room 104 = FRT plywood + FRP-1, no gypsum (G/A-221, A-510); existing EXT-07 faces = patch allowance.
ALC-09 | Exterior gypsum / glass mat sheathing | NOT APPLICABLE | NOT APPLICABLE (rev1): the only sheathing in the set is 1/2 in exterior gyp sheathing of type 1B (1B/A-410), an EXISTING perimeter wall - EXCLUDED (RFI-01, 1/DM-101, A-002); M-301 (p50) 'plastic sheathing' is temporary protection.
ALC-10 | FRT plywood sheathing / substrate | QUANTIFIED | FRT plywood 5/8" 1,790.51 SF (Cafe types G, H, E2, F, I and Grab & Go soffit 3/A-221; soffit faces 2/A-221) + 3/4" 402.46 SF (counters A/B, menu boards 4/A-226A, restroom backing 21/A-201, vestibule 4/A-210, 5/A-210, janitor 11/A-200) - breakdown in Material Summary
ALC-11 | Gypsum board ceilings | QUANTIFIED | Quantified (rev7): suspended GWB ceilings and soffits per A-121 (5/A-121, 4/A-121) and 2/A-221 = 1,006.54 SF (incl. Grab & Go 7'-1" 25.16 SF): 5/8" Type X + restroom ceilings 5/8" Type X W.R. (A-410 Partition Notes 2).
ALC-12 | Ceiling suspension (furring / carrying channel / hanger wire / ceiling track) | QUANTIFIED | Furring channel @ 24", carrying channel @ 48", hanger wire 109 pcs at 48" + 29 at light fixtures, ceiling track per 5/A-121 on A-121; carrying direction E-W (RFI-15 CLOSED rev3: joists N-S on 1/A-400A, 2/A-400A); Cafe Seating cloud = USG drywall suspension grid 4/A-121; M-100 (p46), M-101 (p47), M-102 (p48) hangers are MEP; Grab & Go GWB ceiling 7'-1" added; additional hangers at light fixtures and seismic splay wires per 5/A-121 (RFI-38); 16 ga tie wire (5/A-121) = consumable of the furring / carrying install, no separate row.
ALC-13 | Soffits and bulkheads (framing + board) | QUANTIFIED | Quantified: framed soffit 2/A-221 (SS-N, SS-E, SS-IN-N, SS-IN-E) and Grab & Go header soffit 3/A-221 (SS-GG, RFI-20 CLOSED rev5; T.O. WD-1 RFI-34); E-102 (p36) bulkhead is signage (by others)
ALC-14 | Canopy / marquee framing and sheathing | NOT APPLICABLE | NOT APPLICABLE: E-102 (p36) 'MOUNT WITHIN CANOPY BULKHEAD' is an electrical sign note at the existing canopy; no canopy framing on A-101, A-121, A-210
ALC-15 | Column furring / wraps | QUANTIFIED | Column wraps C25 x 9 on A-101, studs @ 16" O.C. (RFI-17 CLOSED rev4), carried under OTHER FRAMING
ALC-16 | Blocking (FRT wood / metal) for millwork and accessories | QUANTIFIED | Quantified (rev1, RFI-23): FRT blocking 568.27 LF (7/A-413 387.0, 8A/A-413 69.0, 3-4/A-412 85.6, 6/A-412 10.67, 4/A-101 FE cabinets 16.0) + 2X wood 17.0 LF (2/A-500) + 3/4" FRT plywood menu boards 60.61 SF (4/A-226A) + restroom backing 17.78 SF (21/A-201) + janitor 17.0 SF (11/A-200, RFI-33); water heater backing P-201 10.67 LF 3-5/8" stud (RFI-32); W-3 surface blocking 1/A-414 RFI-36.
ALC-17 | Framed openings (MEP, access panels, diffusers) | RFI | RFI: access panels RFI-30; recessed FE cabinets framed per 4/A-101 (FRT header + base, RFI-39); no framed MEP opening drawn in GWB walls (A-121, M-102, P-101A).
ALC-18 | Trim: corner bead, casing bead, control joints, reveals | QUANTIFIED | Metal trim (corner bead, J-bead) per A-410, A-121, A-510 Finish Notes 8 (incl. soffit bottom edges 65.31 LF); no control joint printed (RFI-24).
ALC-19 | Acoustical sealant / sound attenuation (EXCLUDED: estimator standing order, all projects) | NOT APPLICABLE | EXCLUDED: EXCLUDED in all projects (estimator standing order): no acoustical sealant row and no quantity
ALC-20 | FRP / cement board / tile backer | QUANTIFIED | Cement board at wet walls (A-510 tile finishes, RFI-12 incl. Corridor 110 wall tile); FRP-1 extent RFI-13 / RFI-22 not carried
ALC-21 | Shaft walls / area separation walls | NOT APPLICABLE | NOT APPLICABLE: no shaft wall / area separation wall in partition schedule A-410 or plan A-101
ALC-22 | Rated assemblies (UL designs) and their board type | NOT APPLICABLE | NOT APPLICABLE: all partition types are Non-Rated per A-410 titles (2/A-410, 3/A-410, 4/A-410, 5/A-410); E-201 (p40), E-202 (p42), E-301 (p44), M-100 (p46) mentions are generic penetration notes
ALC-23 | Special panels (ballistic, lead-lined, abuse) | NOT APPLICABLE | NOT APPLICABLE: no ballistic, lead-lined or abuse panels in A-410 schedule or A-510 finish schedule
ALC-24 | Finish level (Level 4 / Level 5) | QUANTIFIED | QUANTIFIED: Level 4 finish printed - A-001A Div 09 A.8 "PROVIDE AT A MINIMUM A LEVEL 4 FINISH" (joint compound / tape yields per Inputs); no Level 5 (A-510).
ALC-X40 | Acoustical lay-in ceilings ACT-1 / ACT-3 (tile + Prelude XL grid + wires) | NOT APPLICABLE | EXCLUDED: Div 09 51 acoustical ceilings by the ACT contractor - A-002 lists "ACOUSTICAL CEILING SYSTEM" as its own line (F/I tenant contractor); ACT-1 Cafe Workroom 10'-0", ACT-3 Corridor, Break Room, Manager's Office 9'-0" (1/A-121, A-510 finish legend); ACT portion of 5/A-121. Wall board heights use these ceilings + 6".
ALC-X41 | Unistrut space frame / strut channel | NOT APPLICABLE | EXCLUDED: A-001A Div 05 D "UNISTRUT SPACE FRAME GRID SYSTEM ... AS REQUIRED FOR LIGHTING, CEILING ACCESSORIES OR MECHANICAL SYSTEMS SUSPENSION" and A-002 cafe signage "STRUT CHANNEL" = lighting / sign / MEP supports by those trades; the sign blocking is carried (4/A-226A menu boards).
ALC-X42 | Caulk at the base of wet-area walls | NOT APPLICABLE | EXCLUDED: A-101 general note 8 "BOTTOM OF THE WALL CAULKED AT FLOOR LEVEL" = joint sealant (Div 07), excluded like all sealants (estimator standing order).
ALC-X43 | Partition seismic bracing (A-002 Div 10) | NOT APPLICABLE | EXCLUDED as a separate item: A-002 Div 10 "SEISMIC BRACING" is listed with the specialties; partition lateral bracing is carried per 5/A-410 and 3/A-410; ceiling bracing per 5/A-121 carried under RFI-38.
ALC-X44 | Remove & replace existing GWB for shelving blocking (7/A-413) | RFI | Inside the RFI-01 patch & repair allowance (existing perimeter walls): A-413 general note "G.C. IS TO REMOVE AND REPLACE GYP. BOARD AS REQUIRED FOR INSTALLATION OF WOOD BLOCKING".
ALC-X30 | batt insulation | NOT APPLICABLE | EXCLUDED (estimator criterion: no insulation)

## _reglas (hidden)
reglas.py compuerta OK
{"canon": "3a857f2353c1cf566d9820315ad3dc5df331942160dbcb381fc69e009b95c6e6", "evidencias": "82f4ec13c901d7191f9772989e98854d158340ab19499f6cfbada96ca6cbd21e", "familias_out": "6cf45300148701901df2a2f0b9986058adbbd0e1749b3f37c23c01779106e52a", "reglas": "ba8bd6e1d9f05fc9d972b956fc70d6670e442c3778886e8c3bd2d878c81dab17", "version": "v73"}