## Audit Comparison
AUDIT COMPARISON - Barnes & Noble Colorado Springs - take-off rev4 - independent final auditor (step 11) - 2026-10-27
Every difference found by the auditor. The estimator decides; the take-off Excel was NOT changed. [DERIVED] = operation written; PENDING = not printed.
# | Check | Item | Take-off value | Auditor value | Delta | Source N/SHEET | Image | Recommendation
1 | 1 Tag sweep | Type I tags 'I SIM.' at the east end faces of C-H3a and C-H1-N (wall thickness 7 1/4" printed) | 0 LF type I at these two faces (no row) | 2 x 0.60 = 1.21 LF type I end faces [DERIVED: 7 1/4" printed x 2]; 5/8" FRT plywood to 15'-0" = 18.13 SF; 5/8" GWB 15'-0" to deck = 12.08 SF | +1.21 LF type I; +18.13 SF 5/8" FRT plywood; +12.08 SF GWB (framing already inside C-H3a / C-H1-N) | 1/A-221 ('I SIM.' x2), I/A-221, 6/A-226A (WD-1 top 15'-0") | img/C1_A-221_I_SIM_tags_no_row.png | Estimator to decide: add the two end-face finishes as type I rows (or note them inside C-H3a / C-H1-N). Framing LF does not change.
2 | 2 Re-measure | Type 4 curved walls W4-29a..f and W4-30a..f (R=32'-9" printed) | 25.68 LF per curved wall (6 chord markups; consecutive chords overlap about 0.8 pt each) | 25.20 LF per curved wall [DERIVED: circle R=32'-9" through the vector end points, chord 24.6 ft]; printed 25'-1" on one face | -0.48 LF per wall (-1.9 %), -0.96 LF type 4 total; within the 2 % tolerance | 1/A-101 (R32'-9", 25'-1"), 4/A-410 | img/C2_A-101_type4_curved_walls.png | Estimator decision RFI-18 (face-average arc) - observation only. If changed: type 4 = 82.68 LF.
3 | 4 Scope sweep | Men's 108 / Women's 109 GWB ceilings (GWB 9'-0") | Carried as 5/8" Type X inside the 981.38 SF of GWB ceilings (RFI-27) | 5/8" Type X W.R. on these ceilings: 2 x (8'-8" x 7'-6" - chase notch 2.19 x 2.23) = 120.2 SF [DERIVED] | Type X -120.2 SF; Type X W.R. +120.2 SF | A-410 Partition Notes 2 ('W.R. gypsum board in all bathrooms and janitor's closet for wall AND ceiling construction'); 1/A-121 ceiling tags; 1/A-101 (8'-8", 7'-6" TYP.) | img/C4_A-121_restroom_GWB_ceilings.png ; img/C4_A-410_partition_note_2_WR_ceilings.png | Move the two restroom ceilings to Type X W.R. (plan note is explicit).
4 | 4 Scope sweep | Janitor 107 - 'AREA OF 3/4" FIRE RESISTANT PLYWOOD BLOCKING (TYP)' behind the shelving / water heater shelf | 0 (not in the RFI-23 blocking list) | about 2.13 ft x 8'-0" = 17.0 SF 3/4" FRT plywood [DERIVED: width measured at 1/2"=1'-0" on 11/A-200; height = printed 8'-0" HOLD; upper bound] | +17.0 SF 3/4" FRT plywood (PENDING exact extent) | 11/A-200 | img/C4_A-200_11_janitor_FR_plywood.png | Add as blocking (RFI-23 family) or confirm extent with an RFI.
5 | 4 Scope sweep | Water heater backing in the janitor closet - P-201 'WATER HEATER DETAIL ... FOR RESTROOMS AND BREAKROOM': 2x4 metal stud backing + steel blocking between studs at anchor locations | Not carried (RFI-23 note: 'Water heater backing (P-201) not carried') | 2x4 metal stud backing + steel blocking at the anchor points (sizes not printed) - PENDING | PENDING (small: one wall bay) | P-201 (water heater detail), 11/A-200 | img/C4_P-201_water_heater_backing.png | Estimator decision - observation. The detail is printed; if in scope, add one row.
6 | 4 Scope sweep | Grab & Go header soffit 3/A-221 | RFI-20 'not priced' (ALC-13 lists it as QUANTIFIED) | Plan resolves it: 6'-2" HOLD (1/A-221) x (deck 25'-0" - GWB 7'-1" A-121) = 17.92 ft; 6" studs @16" (3/A-221): 6 x 17.92 = 107.5 LF; 6" track 2 x 6.17 = 12.34 LF; face 6.17 x 17.92 = 110.6 SF (5/8" FRT plywood to T.O. WD-1 + GWB above, split PENDING); bottom GWB 3.73 SF [DERIVED] | +107.5 LF 6" stud; +12.34 LF 6" track; +110.6 SF board/plywood; +3.73 SF GWB | 3/A-221, 1/A-221 (6'-2" HOLD), 1/A-121 (Grab & Go GWB 7'-1") | img/C4_A-221_3_GrabGo_soffit_6-2_HOLD.png ; img/C3_A-221_soffits_2_3.png | Quantify from 3/A-221 (rule: do not ask what the plan resolves); keep only T.O. WD-1 as RFI.
7 | 4 Scope sweep | 8/A-410 'METAL STUD/TRACK FIRE STOP AT CEILING LINE, TYP.' | Not carried | Candidate LF = full-height walls with a ceiling on at least one face: W2-04 56.76 + W2-05 12.92 + W2-06 27.54 + W2-07 7.51 + W2-08 12.92 + W2-09 12.92 + W5-01 5.70 + C-H1-N 29.98 + C-H1-W 12.17 + C-H2a 12.17 + C-E2 29.30 + C-H3a 4.08 + C-H3b 6.17 = 230.14 LF [DERIVED] | + up to 230.14 LF track at ceiling line | 8/A-410, 1/A-121 | img/C4_A-410_8_firestop_track_ceiling_line.png | Estimator to decide whether the typical top-track detail applies (it is N.T.S. and generic).
8 | 4 Scope sweep | Additional head track at openings > 4'-0" | 0 LF; Material Summary row 32 quotes 'ADD FULL LENGTH ADDL HEAD TRACK @ OPNG > 4'-0"' without N/SHEET | Doors 3 (4'-0" x 8'-0") and 11 (4'-0" x 7'-0", HM frame 1/A-500): R.O. above 4'-0" -> (R.O. + 1'-4") x 1 = about 5.58 LF each = 11.17 LF [DERIVED, R.O. not printed] | +11.17 LF (only if the note exists in the set; auditor did not find it on A-410 / A-500) | A-500 door schedule, 1/A-500 | img/C4_A-500_door_schedule_doors_3_11.png | Cite the sheet of the note; if it does not exist, change the source text; if it does, add about 11.2 LF.
9 | 4 Scope sweep | W.R. board on Cafe wet walls | Not carried (RFI-11 decision covers restrooms, janitor, drinking fountain alcove only) | 2/A-410 'RESTROOM/CAFE WALLS ONLY: PROVIDE W.R. GYPSUM BOARD ON WET SIDE(S)' + A-410 '*' note ('... KITCHEN ...'): Cafe Work Room GWB faces of C-H1-N / C-H1-W / C-H2a (about 54.3 LF x 10'-6" = 570 SF upper bound) [DERIVED] | Type X -> Type X W.R. up to 570 SF (no change in total board) | 2/A-410, A-410 '*' note, G/A-221, A-510 (104 FRP-1) | img/C3_A-410_2_type2.png | Estimator decision - observation (RFI-11 scope).
10 | 4 Scope sweep | FRP-1 at Cafe Work Room 104 and Janitor 107; wall tile at Corridor 110 | FRP RFI-13 open (not quantified); RFI-12 covers restroom tile only | A-510 Room Finish Schedule: 104 FRP-1 all walls, 107 FRP, 110 ceramic / porcelain wall tile | Not quantified (PENDING, open RFI) | A-510 Room Finish Schedule | img/C4_A-510_room_finish_FRP_tile.png | Add Corridor 110 wall tile to RFI-12; keep FRP under RFI-13.
11 | 4 Scope sweep | Surface-mounted 3/4" FRT plywood blocking at W-3 wall fixtures 'BY GC/FIXTURE INSTALLER' | Not carried (RFI-23 note) | Printed on 1/A-414 and 7/A-414 | PENDING (by GC vs fixture installer) | 1/A-414, 7/A-414 | img/C4_A-414_surface_FRT_blocking.png | Estimator decision - observation.
12 | 4 Scope sweep | Sound batting (A-002 'SOUND BATTING' tenant contractor; Thermafiber on 2/A-410, 5/A-410) | EXCLUDED (estimator standing criterion) | Printed in scope of the tenant contractor | none (decision) | A-002, 2/A-410, 5/A-410 | img/C4_A-002_sound_batting.png | Estimator decision - observation: keep the exclusion visible in the bid clarifications.
13 | 5 Arithmetic | 3-5/8" metal stud (Material Summary row 12) | 10,778.08 LF | Traceable from the deliverable: field studs (ROUNDUP(L x 12/16) + 1) x H = 7,023.8 (partitions) + 1,193.0 (other framing) + diagonal braces 468.0 (RFI-04) + vestibule posts 126.0 (RFI-16) = 8,810.8 LF | 1,967.3 LF (18.3 %) not traceable (jambs, nodes, other) - no breakdown in the Excel | Partition Takeoff, Pending Items RFI-04 / RFI-16 | - | Add the stud breakdown (field / jambs / nodes / braces / posts) in 'Where it comes from'.
14 | 5 Arithmetic | 6" metal stud (Material Summary row 11) | 2,900 LF | Field studs (ROUNDUP(L x 12/16) + 1) x 25 = 2,625 LF | 275 LF (11 studs x 25 ft) not traceable | Partition Takeoff | - | Same as above.
15 | 5 Arithmetic | 5/8" FRT plywood (Material Summary row 29) | 2,709.63 SF | Traceable: type I 49.65 + SS-N 91.08 + SS-E 40.48 = 181.21 SF; the rest (2,528.42 SF) has no breakdown | 2,528.42 SF not traceable | Pending Items RFI-08 / RFI-14; G, H, E, F/A-221; 3, 4/A-410 | - | Add the face list for FRT plywood.
16 | 5 Arithmetic | Scope Checklist ALC-07 / ALC-08 quantities | ALC-07: Type X 15,538.74 SF; ALC-08: W.R. 1,024.02 SF (rev2 text) | Material Summary rev4: Type X 15,579.48 SF; W.R. 1,020.33 SF | +40.74 SF / -3.69 SF (text stale) | Scope Checklist vs Material Summary | - | Update the two notes to the rev4 figures.
17 | 5 Arithmetic | USG cross tee DGLW424 (RFI-15) | Excel 457.96 LF / 124 pcs | DECISIONES_ESTIMADOR.md RI 10/11 records 443.19 LF / 120 pcs | +14.77 LF vs the decision record | Pending Items RFI-15, 4/A-121 | - | Confirm which count the estimator approved (31 vs 30 rows).
18 | 6 Format | Material Summary 'Where it comes from' | 39 of 44 rows cite internal files (familias_out.json / accesorios.py) and no N/SHEET | Rule: every row cites its N/SHEET in 'Source (DETAIL/SHEET)' / 'Where it comes from' | 39 rows | Material Summary column I | - | Replace the internal file names with the plan citations.
19 | 6 Format | Partition Takeoff Board (SF) vs Length x Height x Layers | 19 rows where Board (SF) <> L x H x Layers (board per face, ceiling + 6"; Height column = stud height) | Per-face heights are not shown in the sheet (e.g. W2-04 1,958.22 vs 56.76 x 25 x 2 = 2,838; SS-IN-N 10 vs 270) | traceability | Partition Takeoff column H | - | Write the face heights in the Location / Status text of each row.
20 | 6 Format | Scope Checklist notes not updated to closed RFIs | ALC-06 cites 3/A-410 for diagonal bracing; ALC-12 'direction assumed E-W (RFI-15)'; ALC-15 'stud spacing assumed 16" (RFI-17)'; ALC-13 lists 3/A-221 as quantified | RFI-04 corrected the source to 8/A-410; RFI-15 and RFI-17 are CLOSED; RFI-20 says 'not priced' | text | Scope Checklist | - | Update the notes.
21 | 6 Format | Wall ID C-E1-P.1 listed under TYPE I | ID prefix says E1, row is type I | Wall ID should carry its type | naming | Partition Takeoff row 74 | - | Rename (e.g. C-I-P.1) in Excel, markups and images together.
22 | 6 Format | Hidden 7th sheet '_reglas' | Workbook has 6 visible sheets + hidden '_reglas' (gate seal) | Template seal by design (plantilla_excel 'libro sellado') | none | Workbook | - | Observation only.
23 | 7 Bluebeam | Markup PDF revision | Markups are the rev3 PDF (no geometry change in rev4); SS-N Depth 14'-0" = stud height | Contents and Depth match the rev4 Excel rows (SS-N Height 14 in both) | none | Barnes_Noble_ColoradoSprings_FINAL_markups_rev3.pdf | - | Observation only.
24 | 8 Drive | Loose skill files in the project folder on Drive | take-off-metal-frame-drywall_FINAL_v80g.zip and _v80h.zip sit in 'Claude outputs / Barnes & Noble Colorado Springs' root | Rule: one folder per project, nothing loose or mixed | 2 files | Drive listing | - | Move the skill zips out of the project folder (manual, the service account cannot move).