## Walls
BARNES & NOBLE - COLORADO SPRINGS, CO - PARTITIONS TAKE-OFF, STEP 1 OF 4 (MEASUREMENT ONLY - NO MATERIALS)
Scale A-101: 1/8"=1'-0" (9 pt/ft) verified: grid C-D = 270 pt = 30'-0". Scale 1/A-221: 1/2"=1'-0" (36 pt/ft) verified: printed 28'-5 7/8" = 1025.6 pt. Lengths from PDF vectors, partition by particion.py mode 'eje'.
Wall ID | Partition Type | Sheet | Tag(s) on sheet | Location | Detail (N/SHEET) | Framing per type (schedule / detail) | LF | Height | Height source (N/SHEET) | Status | Notes
EXT-01 | 1A | A-101 | #0 | North facade, west end (behind Trash / Stock Room) | 1A/A-410 | 3-5/8" metal stud furring at split-faced CMU (gyp bd EXCLUDED) | 15.83 | 25'-0" | B.O. DECK EL. 25'-0" V.I.F. - 1/A-400A | [DERIVED] | West end = west furring face; east end = centerline of Type 2 wall W2-03 (1A/1 boundary not dimensioned -> RFI-02). Printed 15'-7" (A-101) to face of W2-03 supports boundary.
EXT-02 | 1 | A-101 | #1, #2 | North facade, Sales Area + Storage 112 (Adjacent Tenant side) | 1/A-410 | 3-5/8" metal stud furring at existing CMU (gyp bd EXCLUDED - by future tenant) | 158.57 | 25'-0" | B.O. DECK EL. 25'-0" V.I.F. - 1/A-400A | [DERIVED]
EXT-03 | 1A | A-101 | #5, #13 | West facade (Trash / Exterior side), opening inside wall per R70.3 | 1A/A-410 | 3-5/8" metal stud furring at split-faced CMU (gyp bd EXCLUDED) | 64.78 | 24'-0" | B.O. DECK EL. 24'-0" V.I.F. - 2/A-400B | [DERIVED]
EXT-04 | 1B | A-101 | #15 | West, angled wall at Loading Zone (overhead door 12 inside wall) | 1B/A-410 | 8" metal stud + 1/2" exterior gyp sheathing, stone at CMU (gyp bd EXCLUDED) | 13.2 | 24'-0" | B.O. DECK EL. 24'-0" V.I.F. - 2/A-400B | [DERIVED] | Angled; measured corner-to-corner on inner face points; door 12 opening inside the wall (R70.3).
EXT-05 | 1B | A-101 | #26 | West, long angled wall at Loading Zone / Stock Room 111 | 1B/A-410 | 8" metal stud + 1/2" exterior gyp sheathing, stone at CMU (gyp bd EXCLUDED) | 23.67 | 24'-0" | B.O. DECK EL. 24'-0" V.I.F. - 2/A-400B | [DERIVED] | Angled inner face vector line = 23.67'.
EXT-06 | 1B | A-101 | #36 | South facade, Stock Room 111 | 1B/A-410 | 8" metal stud + 1/2" exterior gyp sheathing, stone at CMU (gyp bd EXCLUDED) | 21.13 | 25'-0" | B.O. DECK EL. 25'-0" V.I.F. - 1/A-400B | [DERIVED] | East end = centerline of W2-03 (1B/1 boundary not dimensioned -> RFI-02).
EXT-07 | 1 | A-101 | #37 | South facade, Corridor 110 to Manager's Office 105 (corridor door inside wall) | 1/A-410 | 3-5/8" metal stud furring at existing CMU (gyp bd EXCLUDED - by future tenant) | 56.97 | 25'-0" | B.O. DECK EL. 25'-0" V.I.F. - 1/A-400B | [DERIVED]
EXT-08 | 1 | A-101 | #38 | South facade, Cafe Workroom 104 / Cafe 103 | 1/A-410 | 3-5/8" metal stud furring at existing CMU (gyp bd EXCLUDED - by future tenant) | 0 | 25'-0" | B.O. DECK EL. 25'-0" V.I.F. - 1/A-400B | [DERIVED] | Same line is tagged E1/E2 on 1/A-221 (6" stud wall). Counted ONCE under A-221 (C-E2, C-E1-S) -> 0 LF here. Delta if counted as Type 1 instead: 50.24 LF. RFI-05.
EXT-09 | 1B | A-101 | #34 | South facade, pier between storefronts (Cafe Seating 102) | 1B/A-410 | 8" metal stud + 1/2" exterior gyp sheathing, stone at CMU (gyp bd EXCLUDED) | 7.33 | 25'-0" | B.O. DECK EL. 25'-0" V.I.F. - 1/A-400B | [DERIVED]
EXT-10 | 1B | A-101 | #35 | South facade, SE corner pier | 1B/A-410 | 8" metal stud + 1/2" exterior gyp sheathing, stone at CMU (gyp bd EXCLUDED) | 12.03 | 25'-0" | B.O. DECK EL. 25'-0" V.I.F. - 1/A-400B | [DERIVED]
EXT-11 | 1B | A-101 | #33 | East facade, SE corner pier | 1B/A-410 | 8" metal stud + 1/2" exterior gyp sheathing, stone at CMU (gyp bd EXCLUDED) | 4.36 | 25'-7" | B.O. DECK EL. 25'-7" V.I.F. (high end of sloped deck) - 2/A-400A | [DERIVED]
EXT-12 | 1B | A-101 | #19 | East facade, pier south of Vestibule bump-out | 1B/A-410 | 8" metal stud + 1/2" exterior gyp sheathing, stone at CMU (gyp bd EXCLUDED) | 6.44 | 25'-7" | B.O. DECK EL. 25'-7" V.I.F. (high end of sloped deck) - 2/A-400A | [DERIVED]
EXT-13 | 1C | A-101 | #16 | East facade, south return of Vestibule bump-out | 1C/A-410 | 3-5/8" metal stud, stone at stud (gyp bd EXCLUDED) | 5.23 | 25'-7" | B.O. DECK EL. 25'-7" V.I.F. (high end of sloped deck) - 2/A-400A | [DERIVED]
EXT-14 | 1C | A-101 | #14 | East facade, bump-out face south of Vestibule storefront | 1C/A-410 | 3-5/8" metal stud, stone at stud (gyp bd EXCLUDED) | 4.24 | 25'-7" | B.O. DECK EL. 25'-7" V.I.F. (high end of sloped deck) - 2/A-400A | [DERIVED]
EXT-15 | 1C | A-101 | #9 | East facade, bump-out face north of Vestibule storefront | 1C/A-410 | 3-5/8" metal stud, stone at stud (gyp bd EXCLUDED) | 4.24 | 25'-7" | B.O. DECK EL. 25'-7" V.I.F. (high end of sloped deck) - 2/A-400A | [DERIVED]
EXT-16 | 1C | A-101 | #7 | East facade, north return of Vestibule bump-out | 1C/A-410 | 3-5/8" metal stud, stone at stud (gyp bd EXCLUDED) | 5.23 | 25'-7" | B.O. DECK EL. 25'-7" V.I.F. (high end of sloped deck) - 2/A-400A | [DERIVED]
EXT-17 | 1B | A-101 | #6 | East facade, pier north of Vestibule bump-out | 1B/A-410 | 8" metal stud + 1/2" exterior gyp sheathing, stone at CMU (gyp bd EXCLUDED) | 6.44 | 25'-7" | B.O. DECK EL. 25'-7" V.I.F. (high end of sloped deck) - 2/A-400A | [DERIVED]
EXT-18 | 1B | A-101 | #3 | East facade, NE corner pier (Storage 112) | 1B/A-410 | 8" metal stud + 1/2" exterior gyp sheathing, stone at CMU (gyp bd EXCLUDED) | 4.36 | 25'-7" | B.O. DECK EL. 25'-7" V.I.F. (high end of sloped deck) - 2/A-400A | [DERIVED]
W2-01 | 2 | A-101 | #4 | Storage 112 south wall (door 14, 3'-0" printed, inside wall) | 2/A-410 | 3-5/8" @16" O.C. to deck | 48.77 | 25'-0" | B.O. DECK EL. 25'-0" V.I.F. - 1/A-400A | [DERIVED] | Type 2 to deck > 22'-0": 3-5/8" 14 ga SJ @16" + DIAGONAL BRACING @32" O.C. TO STRUCTURE ABOVE (3/A-410 TYP.) - estimator decision (a), RFI-04.
W2-02 | 2 | A-101 | #4 | Storage 112 west wall | 2/A-410 | 3-5/8" @16" O.C. to deck | 4.99 | 25'-0" | B.O. DECK EL. 25'-0" V.I.F. - 1/A-400A | [DERIVED] | Type 2 to deck > 22'-0": 3-5/8" 14 ga SJ @16" + DIAGONAL BRACING @32" O.C. TO STRUCTURE ABOVE (3/A-410 TYP.) - estimator decision (a), RFI-04.
W2-03 | 2 | A-101 | #12, #22 | Stock Room 111 / Sales + Corridor 110 (door 11 inside wall) | 2/A-410 | 3-5/8" @16" O.C. to deck | 94.24 | 25'-0" | B.O. DECK EL. 25'-0" V.I.F. - 1/A-400B | [DERIVED] | Type 2 to deck > 22'-0": 3-5/8" 14 ga SJ @16" + DIAGONAL BRACING @32" O.C. TO STRUCTURE ABOVE (3/A-410 TYP.) - estimator decision (a), RFI-04. Two tags on one line = one wall.
W2-04 | 2 | A-101 | #23, #24, #25 | BOH north wall: Corridor 110 to Manager's Office 105 (Sales side) | 2/A-410 | 3-5/8" @16" O.C. to deck | 56.76 | 25'-0" | B.O. DECK EL. 25'-0" V.I.F. - 1/A-400B | [DERIVED] | Type 2 to deck > 22'-0": 3-5/8" 14 ga SJ @16" + DIAGONAL BRACING @32" O.C. TO STRUCTURE ABOVE (3/A-410 TYP.) - estimator decision (a), RFI-04. East end = start of Cafe wall H1 (A-221).
W2-05 | 2 | A-101 | #28 | Corridor 110 / Women's 109 (door 4 inside wall) | 2/A-410 | 3-5/8" @16" O.C. to deck | 12.92 | 25'-0" | B.O. DECK EL. 25'-0" V.I.F. - 1/A-400B | [DERIVED] | Type 2 to deck > 22'-0": 3-5/8" 14 ga SJ @16" + DIAGONAL BRACING @32" O.C. TO STRUCTURE ABOVE (3/A-410 TYP.) - estimator decision (a), RFI-04. Printed 12'-11" (A-101) = 12.92' check OK.
W2-06 | 2 | A-101 | #29, #30 | Restrooms 108/109 + Janitor 107 north run with chase jog (doors 9, 8, 7 inside) | 2/A-410 | 3-5/8" @16" O.C. to deck | 25.86 | 25'-0" | B.O. DECK EL. 25'-0" V.I.F. - 1/A-400B | [DERIVED] | Type 2 to deck > 22'-0": 3-5/8" 14 ga SJ @16" + DIAGONAL BRACING @32" O.C. TO STRUCTURE ABOVE (3/A-410 TYP.) - estimator decision (a), RFI-04. Run with jog; untagged segments join the tagged jog (rule 3).
W2-07 | 2 | A-101 | #31 | Men's 108 / Janitor 107 | 2/A-410 | 3-5/8" @16" O.C. to deck | 7.51 | 25'-0" | B.O. DECK EL. 25'-0" V.I.F. - 1/A-400B | [DERIVED] | Type 2 to deck > 22'-0": 3-5/8" 14 ga SJ @16" + DIAGONAL BRACING @32" O.C. TO STRUCTURE ABOVE (3/A-410 TYP.) - estimator decision (a), RFI-04.
W2-08 | 2 | A-101 | #31 | Janitor 107 / Break Room 106 (door 5 inside wall) | 2/A-410 | 3-5/8" @16" O.C. to deck | 12.92 | 25'-0" | B.O. DECK EL. 25'-0" V.I.F. - 1/A-400B | [DERIVED] | Type 2 to deck > 22'-0": 3-5/8" 14 ga SJ @16" + DIAGONAL BRACING @32" O.C. TO STRUCTURE ABOVE (3/A-410 TYP.) - estimator decision (a), RFI-04. 12'-11" confirmed on 7/A-412.
W2-09 | 2 | A-101 | #27 | Break Room 106 / Manager's Office 105 (door 6 inside wall) | 2/A-410 | 3-5/8" @16" O.C. to deck | 12.92 | 25'-0" | B.O. DECK EL. 25'-0" V.I.F. - 1/A-400B | [DERIVED] | Type 2 to deck > 22'-0": 3-5/8" 14 ga SJ @16" + DIAGONAL BRACING @32" O.C. TO STRUCTURE ABOVE (3/A-410 TYP.) - estimator decision (a), RFI-04. 12'-11" confirmed on 1/A-412.
W5-01 | 5 | A-101 | #32 | Plumbing wall between Women's 109 / Men's 108 | 5/A-410 | 6" @16" O.C. to deck | 5.7 | 25'-0" | B.O. DECK EL. 25'-0" V.I.F. - 1/A-400B | [DERIVED] | 6" @16" to deck (5/A-410).
W3-01 | 3 | A-101 | #17 | Cafe Seating 102, west low wall - west end post | 3/A-410 | 3-5/8" @16" O.C. to 8'-0" AFF | 3.67 | 8'-0" AFF | 8'-0" A.F.F. T.O. WALL printed - 3/A-410 | [CONFIRMED] | 3'-8" printed (A-101).
W3-02 | 3 | A-101 | #20 | Cafe Seating 102, west low wall - run | 3/A-410 | 3-5/8" @16" O.C. to 8'-0" AFF | 12 | 8'-0" AFF | 8'-0" A.F.F. T.O. WALL printed - 3/A-410 | [CONFIRMED] | 12'-0" printed (A-101).
W3-05 | 3 | A-101 | #20 TYP. | Cafe Seating 102, west low wall - east end post | 3/A-410 | 3-5/8" @16" O.C. to 8'-0" AFF | 3.67 | 8'-0" AFF | 8'-0" A.F.F. T.O. WALL printed - 3/A-410 | [CONFIRMED] | No own tag ('TYP.'); T-joint, not end-to-end -> own wall per particion.py eje. 3'-8" printed.
W3-03 | 3 | A-101 | #21 | Cafe Seating 102, east low wall - run | 3/A-410 | 3-5/8" @16" O.C. to 8'-0" AFF | 12 | 8'-0" AFF | 8'-0" A.F.F. T.O. WALL printed - 3/A-410 | [CONFIRMED] | 12'-0" printed (A-101).
W3-06 | 3 | A-101 | #21 TYP. | Cafe Seating 102, east low wall - west end post | 3/A-410 | 3-5/8" @16" O.C. to 8'-0" AFF | 3.67 | 8'-0" AFF | 8'-0" A.F.F. T.O. WALL printed - 3/A-410 | [CONFIRMED] | No own tag ('TYP.'); T-joint -> own wall per particion.py eje. 3'-8" printed.
W3-04 | 3 | A-101 | #18 | Cafe Seating 102, east low wall - east end post | 3/A-410 | 3-5/8" @16" O.C. to 8'-0" AFF | 3.67 | 8'-0" AFF | 8'-0" A.F.F. T.O. WALL printed - 3/A-410 | [CONFIRMED] | 3'-8" printed (A-101).
W4-01 | 4 | A-101 | #11 | Sales Area center feature - north cap box (9'-0" printed) | 4/A-410 | 3-5/8" @16" O.C. to 7'-6" AFF | 19.96 | 7'-6" AFF | 7'-6" A.F.F. T.O. WALL printed - 4/A-410 | [DERIVED] | Closed box = one wall; LF = centerline perimeter 2x(77.3+12.5) pt.
W4-02 | 4 | A-101 | #11 | Sales Area center feature - west curved wall (R32'-9") | 4/A-410 | 3-5/8" @16" O.C. to 7'-6" AFF | 23.86 | 7'-6" AFF | 7'-6" A.F.F. T.O. WALL printed - 4/A-410 | [DERIVED] | Arc length by Bezier vector, trimmed to cap faces.
W4-03 | 4 | A-101 | #11 | Sales Area center feature - east curved wall (R32'-9") | 4/A-410 | 3-5/8" @16" O.C. to 7'-6" AFF | 23.9 | 7'-6" AFF | 7'-6" A.F.F. T.O. WALL printed - 4/A-410 | [DERIVED] | Arc length by Bezier vector, trimmed to cap faces.
W4-04 | 4 | A-101 | #11 TYP. | Sales Area center feature - south cap box (TYP. per tag #11) | 4/A-410 | 3-5/8" @16" O.C. to 7'-6" AFF | 19.97 | 7'-6" AFF | 7'-6" A.F.F. T.O. WALL printed - 4/A-410 | [DERIVED] | No own tag; 'TYP.' under tag #11. Closed box = one wall.
C-H1-N | H1 | A-221 | H1 (#8) | Cafe Workroom 104 north wall (to Sales / Grab & Go) | G/A-221 | 6" stud @16" O.C., 5/8" GWB + 5/8" FRT plywood | 29.98 | PENDING | No height printed on detail (break line at top) -> RFI-06 | [PENDING] | LF DERIVED (vectors); height PENDING.
C-H1-W | H1 | A-221 | H1 (#17) | Cafe Workroom 104 west wall | G/A-221 | 6" stud @16" O.C., 5/8" GWB + 5/8" FRT plywood | 12.17 | PENDING | No height printed on detail (break line at top) -> RFI-06 | [PENDING] | LF = 12'-2" printed (1/A-221) CONFIRMED; height PENDING.
C-H2a | H2a | A-221 | H2a (#9) | Cafe Workroom 104 / Cafe Sales (4'-0" door inside wall) | G/A-221 | 3-5/8" stud @16" O.C., 5/8" GWB / 5/8" FRT plywood | 12.17 | PENDING | No height printed on detail (break line at top) -> RFI-06 | [PENDING] | LF = 12'-2" printed; height PENDING.
C-H2b | H2b | A-221 | H2b (#20) | Cafe Workroom 104 stub wall | G/A-221 | 3-5/8" stud @16" O.C., 5/8" FRT plywood both sides | 1.95 | PENDING | No height printed on detail (break line at top) -> RFI-06 | [PENDING]
C-H3a | H3a | A-221 | H3a (#2) | Grab & Go north wall | H/A-221 | 6" stud @16" O.C., 5/8" gyp bd + plywood to top of WD-1 | 4.08 | PENDING | No height printed on detail (break line at top) -> RFI-06 | [PENDING] | 'I' tag (#0, SIM.) = finish at wall end face, 0 LF.
C-H3b | H3b | A-221 | H3b (#1) | Grab & Go west wall | H/A-221 | 6" stud @16" O.C., 5/8" gyp bd + plywood up to 8'-0" | 6.17 | PENDING | No height printed on detail (break line at top) -> RFI-06 | [PENDING] | LF = 6'-2" HOLD printed; height PENDING.
C-E2 | E2 | A-221 | E2 (#22) | South wall, Cafe Workroom 104 (in front of demising / exterior wall) | E/A-221 | 6" @16" O.C. to underside of deck, 5/8" FRT plywood | 29.3 | 25'-0" | '6" METAL STUDS @16" O.C. TO UNDERSIDE OF DECK' E/A-221 + B.O. DECK EL. 25'-0" V.I.F. 1/A-400B | [DERIVED] | Overlaps A-101 Type 1 (#38) line -> counted once here (RFI-05). East end = H2a centerline.
C-E1-S | E1 | A-221 | E1 (#21) | South wall, Cafe Sales 103 (in front of exterior wall) | E/A-221 | 6" @16" O.C. to underside of deck, 1/2" cement board | 23.46 | 25'-0" | '6" METAL STUDS @16" O.C. TO UNDERSIDE OF DECK' E/A-221 + B.O. DECK EL. 25'-0" V.I.F. 1/A-400B | [DERIVED] | Overlaps A-101 Type 1 (#38) -> counted once here (RFI-05).
C-E1-P | E1 | A-221 | E1 (#19) | Pier at Workroom door (1'-0" x 2'-8" HOLD printed) | E/A-221 | 6" @16" O.C. to underside of deck, 1/2" cement board | 3.11 | 25'-0" | '6" METAL STUDS @16" O.C. TO UNDERSIDE OF DECK' E/A-221 + B.O. DECK EL. 25'-0" V.I.F. 1/A-400B | [DERIVED] | 'I' tag (#18) = inside face finish, 0 LF.
C-E1-B | E1 | A-221 | E1 (#21) | Box at SE corner of Cafe Sales - west side | E/A-221 | 6" @16" O.C. to underside of deck, 1/2" cement board | 2.31 | 25'-0" | '6" METAL STUDS @16" O.C. TO UNDERSIDE OF DECK' E/A-221 + B.O. DECK EL. 25'-0" V.I.F. 1/A-400B | [DERIVED]
C-F | F | A-221 | F (#23) | Box at SE corner of Cafe Sales - north side (3'-3" printed) | F/A-221 | 3-5/8" @16" O.C. to bottom of nested stud bracing, 5/8" FRT plywood | 3.26 | PENDING | 'TO BOTTOM OF NESTED STUD BRACING' - F/A-221, elevation not printed -> RFI-06 | [PENDING]
C-I | I | A-221 | I (#24) | Box at SE corner of Cafe Sales - east side | I/A-221 | 6" stud @16" O.C., 5/8" FRT plywood one side | 2.31 | PENDING | No height printed on detail (break line at top) -> RFI-06 | [PENDING] | Tags I #0 / #7 (SIM.) and #18 mark end/inside faces of other walls: 0 LF.
C-A-1 | A | A-221 | A (#12) | Front counter - straight run | A/A-221 | 3-5/8" @16" O.C. counter wall (front counter) | 9.89 | 2'-8 1/2" | 2'-8 1/2" B.O. SLAB TO T.O. STUD printed - A/A-221 | [DERIVED] | Height CONFIRMED; LF DERIVED (vectors).
C-A-2 | A | A-221 | A (#13) | Front counter - 45 deg segment | A/A-221 | 3-5/8" @16" O.C. counter wall (front counter) | 4.14 | 2'-8 1/2" | A/A-221 | [DERIVED]
C-A-3 | A | A-221 | A (#16) | Front counter - east run to box | A/A-221 | 3-5/8" @16" O.C. counter wall (front counter) | 6.24 | 2'-8 1/2" | A/A-221 | [DERIVED] | 6'-4 1/8" printed to outer corner checks vector.
C-B | B | A-221 | B (#10) | Pastry counter - west leg | B/A-221 | 3-5/8" @16" O.C. counter wall | 3.17 | 2'-8 1/2" | B/A-221 | [DERIVED] | B+D+C outer = 6'-1 3/4" printed check OK.
C-D | D | A-221 | D (#14) | Pastry counter - south (between legs) | D/A-221 | 3-5/8" @16" O.C. counter wall (1'-0") | 5.14 | 1'-0" | 1'-0" B.O. SLAB TO T.O. STUD printed - D/A-221 | [DERIVED]
C-C | C | A-221 | C (#11) | Pastry counter - east leg | C/A-221 | 3-5/8" @16" O.C. counter wall | 3.17 | 2'-8 1/2" | C/A-221 | [DERIVED]

## Totals by Type
Partition Type | Sheet | Detail | Walls (count) | Total LF | Heights | Notes
1A | A-101 | 1A/A-410 | 2 | 80.61 | 24'-0", 25'-0"
1 | A-101 | 1/A-410 | 3 | 215.54 | 25'-0" | Excludes Cafe portion (EXT-08, 50.24 LF) counted as E1/E2 - RFI-05
1B | A-101 | 1B/A-410 | 9 | 98.96 | 24'-0", 25'-0", 25'-7" | 9 tags found on A-101 (order said 8) - RFI-07
1C | A-101 | 1C/A-410 | 4 | 18.94 | 25'-7"
2 | A-101 | 2/A-410 | 9 | 276.89 | 25'-0" | All > 22'-0": 14 ga SJ + diagonal bracing @32" O.C. - RFI-04
5 | A-101 | 5/A-410 | 1 | 5.7 | 25'-0"
3 | A-101 | 3/A-410 | 6 | 38.68 | 8'-0" AFF | 6 walls per particion.py (2 untagged end posts, TYP.)
4 | A-101 | 4/A-410 | 4 | 87.69 | 7'-6" AFF | Includes 2 curved walls (R32'-9") and untagged south cap box (TYP.)
H1 | A-221 | G/A-221 | 2 | 42.15 | PENDING
H2a | A-221 | G/A-221 | 1 | 12.17 | PENDING
H2b | A-221 | G/A-221 | 1 | 1.95 | PENDING
H3a | A-221 | H/A-221 | 1 | 4.08 | PENDING
H3b | A-221 | H/A-221 | 1 | 6.17 | PENDING
E2 | A-221 | E/A-221 | 1 | 29.3 | 25'-0"
E1 | A-221 | E/A-221 | 3 | 28.88 | 25'-0"
F | A-221 | F/A-221 | 1 | 3.26 | PENDING
I | A-221 | I/A-221 | 1 | 2.31 | PENDING
A | A-221 | A/A-221 | 3 | 20.27 | 2'-8 1/2"
B | A-221 | B/A-221 | 1 | 3.17 | 2'-8 1/2"
D | A-221 | D/A-221 | 1 | 5.14 | 1'-0"
C | A-221 | C/A-221 | 1 | 3.17 | 2'-8 1/2"
GRAND TOTAL |  |  | 56 | 985.03

## RFIs
RFI | Subject | Question | Assumption used | Delta of alternatives
RFI-01 | Exterior types 1/1A/1B/1C gyp bd | Details 1, 1A, 1B, 1C/A-410 show 5/8" gyp bd 'BY FUTURE TENANT'. Confirm framing is in our scope and gyp bd is not. | Framing INCLUDED, gyp bd EXCLUDED (estimator decision c). | If gyp bd included: + board on 414.05 LF of exterior walls (1: 215.54, 1A: 80.61, 1B: 98.96, 1C: 18.94) x height.
RFI-02 | Type boundaries along a facade | A-101 does not dimension where 1A changes to 1 (north facade) nor where 1B changes to 1 (south facade). | Boundary at centerline of Type 2 wall W2-03 (x of Stock Room / Corridor wall). North: printed 15'-7" supports it. | South: if boundary at corridor door jamb instead: +1.54 LF 1B / -1.54 LF 1. North: LF moves 1A<->1 only (same 3-5/8" framing).
RFI-03 | Deck elevation (all walls to deck) | B.O. deck is V.I.F. and sloped: 25'-0" (1/A-400A, 1/A-400B), 25'-7" (2/A-400A), 24'-0" (2/A-400B). Confirm height per wall. | N/S facades + interior to-deck walls 25'-0"; east facade 25'-7" (high end); west facade 24'-0". | East walls at 24'-0" instead of 25'-7": -1'-7" x 40.54 LF; interior at 24'-0": -1'-0" x LF of types 2, 5, E1, E2.
RFI-04 | Type 2 above schedule limit | Type 2 (3-5/8" @16" to deck) height 25'-0" exceeds 22'-0" max (3-5/8" 14 ga SJ @16", Metal Stud Schedule A-410). | 3-5/8" 14 ga SJ @16" + DIAGONAL BRACING @32" O.C. TO STRUCTURE ABOVE (3/A-410 TYP.) - estimator decision (a). Note: the bracing callout text was seen next to 8/A-410 Top Track Detail - confirm reference. | Alternative 6" stud (6" 20 ga SJ up to 26'-8"): stud size change on 276.89 LF.
RFI-05 | Cafe overlap A-101 vs 1/A-221 | Cafe south wall is tagged Type 1 on A-101 (#38) and E1/E2 on 1/A-221. Are these one wall or furring + 6" stud wall? No A-221 wall coincides with Type 3/4 tags of A-101 (Type 3 walls are in Cafe Seating 102, outside 1/A-221). | Counted ONCE as E1/E2 (A-221 governs): E2 29.30 LF + E1 23.46 LF; Type 1 portion (EXT-08) = 0 LF. | If both exist: + 50.24 LF Type 1 furring (A-101 x 1011.24 to 1463.4 pt).
RFI-06 | Cafe wall heights not printed | Sections G (H1/H2), H (H3), I and F/A-221 show no top-of-stud elevation (refer to A-225, not in this step). F: 'to bottom of nested stud bracing'. | Height [PENDING]. | 72.09 LF pending (H1 42.15, H2a 12.17, H2b 1.95, H3a 4.08, H3b 6.17, I 2.31, F 3.26): to deck 25'-0" vs. ceiling height.
RFI-07 | Tag count 1B | Order lists 8 tags 1B; sweep of A-101 found 9 (#3, #6, #15, #19, #26, #33, #34, #35, #36). | All 9 measured. | If one is not 1B: minus that wall's LF from 1B.
NOTE | Vestibule | Vestibule 100 is storefront with stud posts + box beam (A-210) - not a partition. | Excluded from this step. | -
NOTE | 'I' tags on A-221 | Tags I #0, #7 (SIM.) and #18 point to wall end / inside faces (finish). | 0 LF; only I #24 (box east side) measured. | -